## PVT WBS (hidden)
Responsibility | (All)
Sum of AMT KEUR | Column Labels | [5 empty] | Sum of FTE | Column Labels
Row Labels | A | B | C | D | E/F | Grand Total | Row Labels | A | B | C | D | E/F
MGT | 117.0918 | 655.8169 | 811.9392 | 1311.6338 | 140.5873 | 3037.069 | MGT | 1.6333 | 2.7 | 5 | 4 | 0.5
Manpower | 117.0918 | 655.8169 | 811.9392 | 1311.6338 | 140.5873 | 3037.069 | MISSION | 4.5 | 4.9 | 8.5 | 5.5 | 0.4
MISSION | 540.1628 | 1163.608 | 1304.0666 | 1759.1159 | 93.6734 | 4860.6267 | Grand Total | 6.1333 | 7.6 | 13.5 | 9.5 | 0.9
Manpower | 540.1628 | 1163.608 | 1304.0666 | 1759.1159 | 93.6734 | 4860.6267
Grand Total | 657.2546 | 1819.4249 | 2116.0059 | 3070.7497 | 234.2608 | 7897.6957

## VESPUP WBS v1-8 (hidden)
VESPUP WBS and WP numbering
1.2
Please go down to 3rd or 4th level, no lower
1 | 2
[9 empty] | 2020Q1 | 2020Q2 | 2020Q1 | 2020Q2
WBS | WP | T8 Code | Cost Category | Cost Type | Partner WP# | Responsibility | Country | Phase | AMT KEUR |  | FTE
100000 | Project Management and SE
110000 | Project Management | A1 | MGT | Manpower
110100 | ClearSpace Project Management | A1 | MGT | Manpower |  | ClearSpace | CH | A | 78.0612 |  | 1.3333
110100 | ClearSpace Project Management | A1 | MGT | Manpower |  | ClearSpace | CH | B | 499.6945 |  | 2
110100 | ClearSpace Project Management | A1 | MGT | Manpower |  | ClearSpace | CH | C | 499.6945 |  | 3
110100 | ClearSpace Project Management | A1 | MGT | Manpower |  | ClearSpace | CH | D | 687.1443 |  | 2
110100 | ClearSpace Project Management | A1 | MGT | Manpower |  | ClearSpace | CH | E/F | 140.5873 |  | 0.5
110110 | Project & contractor management | A1 | MGT | Manpower
110120 | Project planning, cost and schedule management | A1 | MGT | Manpower
110130 | Risk management | A1 | MGT | Manpower
110140 | Documentation management | A1 | MGT | Manpower
110150 | Integrated logistics | A1 | MGT | Manpower
110160 | Legal & UN coordination | A1 | MGT | Manpower
110170 | Financial reporting, procurements & negociation | A1 | MGT | Manpower
110180 | Admin and IT | A1 | MGT | Manpower
110190 | PR & External communication | A1 | MGT | Manpower
110200 | OHB-Se Projet Management | A1 | MGT | Manpower | 110200 | OHB-Sweden | SE | A
110300 | Airbus DS Projet Management | A1 | MGT | Manpower |  | Airbus DS | DE
110400 | APCO-Techn Project Management | A1 | MGT | Manpower |  | APCO-Technologies | CH
110500 | Syderal-Swiss Project Management | A1 | MGT | Manpower |  | Syderal Swiss | CH
110600 | RUAG-Space Project Management | A1 | MGT | Manpower |  | Ruag-Space | CH
110700 | EPFL Project Management | A1 | MGT | Manpower |  | EPFL | CH
110800 | AIUB Project management | A1 | MGT | Manpower |  | AIUB | CH
120000 | Project System Engineering | A3 | MISSION | Manpower
120100 | Project level system engineering | A3 | MISSION | Manpower |  | ClearSpace | CH | A | 83.2824 |  | 0.7
120100 | Project level system engineering | A3 | MISSION | Manpower |  | ClearSpace | CH | B | 166.5648 |  | 0.7
120100 | Project level system engineering | A3 | MISSION | Manpower |  | ClearSpace | CH | C | 166.5648 |  | 1
120100 | Project level system engineering | A3 | MISSION | Manpower |  | ClearSpace | CH | D | 333.1297 |  | 1
120100 | Project level system engineering | A3 | MISSION | Manpower |  | ClearSpace | CH | E/F | 0 |  | 0
120110 | System engineering planning & management | A3 | MISSION | Manpower
120111 | Project life cycle assessment | A3 | MISSION | Manpower |  | EPFL | CH
120120 | Systems planning, cost and scheduling | A3 | MISSION | Manpower
120130 | Risk assessment and management | A3 | MISSION | Manpower
120140 | Specifications and requirements management | A3 | MISSION | Manpower
120150 | Interfaces control and management | A3 | MISSION | Manpower
120160 | Changes and non-conformance control | A3 | MISSION | Manpower
120170 | Industrial design | A3 | MISSION | Manpower
120180 | Licenses and registrations | A3 | MISSION | Manpower |  | ClearSpace | CH
120190 | Launch procurement management | A3 | MISSION | Manpower
120200 | ESA expertise and test observations | A3 | MISSION | Manpower |  | ClearSpace | CH | A | 78.0612 |  | 0.7
120200 | ESA expertise and test observations | A3 | MISSION | Manpower |  | ClearSpace | CH | B | 156.1224 |  | 0.7
120200 | ESA expertise and test observations | A3 | MISSION | Manpower |  | ClearSpace | CH | C | 156.1224 |  | 1
120200 | ESA expertise and test observations | A3 | MISSION | Manpower |  | ClearSpace | CH | D | 312.2447 |  | 1
120200 | ESA expertise and test observations | A3 | MISSION | Manpower |  | ClearSpace | CH | E/F | 93.6734 |  | 0.4
130000 | PA/QA | A2 | MGT | Manpower
130100 | PA/QA - ClearSpace | A2 | MGT | Manpower |  | ClearSpace | CH | A | 39.0306 |  | 0.3
130100 | PA/QA - ClearSpace | A2 | MGT | Manpower |  | ClearSpace | CH | B | 156.1224 |  | 0.7
130100 | PA/QA - ClearSpace | A2 | MGT | Manpower |  | ClearSpace | CH | C | 312.2447 |  | 2
130100 | PA/QA - ClearSpace | A2 | MGT | Manpower |  | ClearSpace | CH | D | 624.4894 |  | 2
130100 | PA/QA - ClearSpace | A2 | MGT | Manpower |  | ClearSpace | CH | E/F | 0 |  | 0
130110 | SW Product Assurance | A2 | MGT | Manpower
130120 | HW and AIT Product Assurance | A2 | MGT | Manpower
130200 | PA/QA - OHB-Sweden | A2 | MGT | Manpower |  | OHB-Sweden | SE
130210 | SW Product Assurance | A2 | MGT | Manpower
130220 | HW and AIT Product Assurance | A2 | MGT | Manpower
130300 | PA/QA - Airbus DS | A2 | MGT | Manpower |  | Airbus DS | DE
130400 | APCO-Techn Product Assurance | A2 | MGT | Manpower |  | APCO-Technologies | CH
130500 | PA/QA - Syderal Swiss | A2 | MGT | Manpower |  | Syderal Swiss | CH
130600 | RUAG-Space product Assurance | A2 | MGT | Manpower
140000 | Commercial, scalability and industrialisation requirements | A3 | MISSION | Manpower |  | ClearSpace | CH | A | 39.0306 |  | 0.3
140000 | Commercial, scalability and industrialisation requirements | A3 | MISSION | Manpower |  | ClearSpace | CH | B | 78.0612 |  | 0.3
140000 | Commercial, scalability and industrialisation requirements | A3 | MISSION | Manpower |  | ClearSpace | CH | C | 78.0612 |  | 0.5
140000 | Commercial, scalability and industrialisation requirements | A3 | MISSION | Manpower |  | ClearSpace | CH | D | 156.1224 |  | 0.5
140100 | Definition of commercial costumer requirements | A3 | MISSION | Manpower
140200 | Commercial service mission architectures | A3 | MISSION | Manpower
140300 | Scalability analysis of space and ground segment | A3 | MISSION | Manpower
140400 | Industrialisation and commercial operational plan | A3 | MISSION | Manpower
140410 | Industrialisation plan | A3 | MISSION | Manpower |  | RUAG-Space | CH
140420 | Operational plan | A3 | MISSION | Manpower |  | ClearSpace | CH
200000 | Mission Engineering | A3 | MISSION | Manpower
210000 | Mission analysis | A3 | MISSION | Manpower |  | ClearSpace | CH | A | 66.6259 |  | 0.5
210000 | Mission analysis | A3 | MISSION | Manpower |  | ClearSpace | CH | B | 133.2519 |  | 0.5
210000 | Mission analysis | A3 | MISSION | Manpower |  | ClearSpace | CH | C | 133.2519 |  | 0.8
210000 | Mission analysis | A3 | MISSION | Manpower |  | ClearSpace | CH | D | 166.5648 |  | 0.5
210100 | Mission analysis -Preliminary | A3 | MISSION | Manpower |  | ClearSpace | CH
210200 | Mission analysis - Detailed | A3 | MISSION | Manpower |  | ClearSpace | CH
210300 | Support to mission analyses | A3 | MISSION | Manpower |  | OHB-Sweden | SE
210400 | Flight dynamics software - definition | A3 | MISSION | Manpower |  | ClearSpace | CH
220000 | Space environment analyses | A3 | MISSION | Manpower |  | ClearSpace | CH | A | 15.6122 |  | 0.1
220000 | Space environment analyses | A3 | MISSION | Manpower |  | ClearSpace | CH | B | 31.2245 |  | 0.1
220000 | Space environment analyses | A3 | MISSION | Manpower |  | ClearSpace | CH | C | 31.2245 |  | 0.2
220100 | Radiation environment definition and analyses - Preliminary | A3 | MISSION | Manpower |  | ClearSpace | CH
220200 | Radiation environment definition and analyses - Detailed | A3 | MISSION | Manpower |  | ClearSpace | CH
220300 | Space charging analyses | A3 | MISSION | Manpower |  | ClearSpace | CH
230000 | Mission operations planning | A3 | MISSION | Manpower |  | ClearSpace | CH | A | 41.6412 |  | 0.3
230000 | Mission operations planning | A3 | MISSION | Manpower |  | ClearSpace | CH | B | 166.5648 |  | 0.7
230000 | Mission operations planning | A3 | MISSION | Manpower |  | ClearSpace | CH | C | 166.5648 |  | 1
230000 | Mission operations planning | A3 | MISSION | Manpower |  | ClearSpace | CH | D | 333.1297 |  | 1
230100 | Requirements analyses and preliminary mission operations concept | A3 | MISSION | Manpower |  | ClearSpace | CH
230200 | Operational analysis and concept development | A3 | MISSION | Manpower |  | ClearSpace | CH
230300 | Operational engineering planning | A3 | MISSION | Manpower |  | ClearSpace | CH
230400 | Support to mission planning and operations | A3 | MISSION | Manpower |  | OHB-Sweden | SE
240000 | Mission data products | A3 | MISSION | Manpower |  | ClearSpace | CH | C | 78.0612 |  | 0.5
240100 | RV GNC data product and tools definition | A3 | MISSION | Manpower |  | ClearSpace | CH
240200 | RV Capture data product and tools definition | A3 | MISSION | Manpower |  | ClearSpace | CH
300000 | Launch vehicle
310000 | Launch specification | A3 | MISSION | Manpower
310100 | Launch environment definition | A3 | MISSION | Manpower |  | ClearSpace | CH | A | 39.0306 |  | 0.3
310100 | Launch environment definition | A3 | MISSION | Manpower |  | ClearSpace | CH | B | 78.0612 |  | 0.3
310100 | Launch environment definition | A3 | MISSION | Manpower |  | ClearSpace | CH | C | 78.0612 |  | 0.5
310110 | Support to launch environment definition | A3 | MISSION | Manpower |  | APCO-Technologies | CH
310200 | Launch specifications for equipments | A3 | MISSION | Manpower |  | APCO-Technologies | CH
320000 | Launch procurement | D | 0 | Procurement |  | ClearSpace | CH
400000 | Flight Segment
401000 | Flight System engineering | A4 | MISSION | Manpower |  | ClearSpace | CH
401100 | Flight System engineering and management | A4 | MISSION | Manpower |  | ClearSpace | CH | A | 145.6799 |  | 1.3
401100 | Flight System engineering and management | A4 | MISSION | Manpower |  | ClearSpace | CH | B | 291.3598 |  | 1.3
401100 | Flight System engineering and management | A4 | MISSION | Manpower |  | ClearSpace | CH | C | 291.3598 |  | 2
401100 | Flight System engineering and management | A4 | MISSION | Manpower |  | ClearSpace | CH | D | 333.1297 |  | 1
401100 | Flight System planning, cost and scheduling | A4 | MISSION | Manpower
401100 | Specifications and requirements management | A4 | MISSION | Manpower
401100 | Interfaces control and management | A4 | MISSION | Manpower
401100 | Risk assessment and management | A4 | MISSION | Manpower
401100 | Changes and non-conformance control | A4 | MISSION | Manpower
401200 | Flight Engineering Simulator (FES) | A4 | MISSION | Manpower |  | ClearSpace | CH | A | 31.1987 |  | 0.3
401200 | Flight Engineering Simulator (FES) | A4 | MISSION | Manpower |  | ClearSpace | CH | B | 62.3975 |  | 0.3
401200 | Flight Engineering Simulator (FES) | A4 | MISSION | Manpower |  | ClearSpace | CH | C | 124.7949 |  | 1
401200 | Flight Engineering Simulator (FES) | A4 | MISSION | Manpower |  | ClearSpace | CH | D | 124.7949 |  | 0.5
401200 | FES Preliminary Design | A4 | MISSION | Manpower
401200 | FES Detailed design and production | A4 | MISSION | Manpower
401200 | FES Validation | A4 | MISSION | Manpower
401300 | System level Fault Detection, Isolation and Recovery | A4 | MISSION | Manpower |  | ClearSpace | CH | A | 39.0306 |  | 0.3
401300 | System level Fault Detection, Isolation and Recovery | A4 | MISSION | Manpower |  | ClearSpace | CH | B | 156.1224 |  | 0.7
401300 | System level Fault Detection, Isolation and Recovery | A4 | MISSION | Manpower |  | ClearSpace | CH | C | 156.1224 |  | 1
401300 | System level Fault Detection, Isolation and Recovery | A4 | MISSION | Manpower |  | ClearSpace | CH | D | 79.0306 |  | 0.3
401300 | PD - Preliminary design and specifications | A4 | MISSION | Manpower
401300 | Model predictive FDIR | A4 | MISSION | Manpower
401400 | System mechanical and thermal architecture, SE | A4 | MISSION | Manpower |  | ClearSpace | CH | A | #REF! |  | 1.3333
401400 | System mechanical and thermal architecture, SE | A4 | MISSION | Manpower |  | ClearSpace | CH | B | #REF! |  | 1.3333
401400 | System mechanical and thermal architecture, SE | A4 | MISSION | Manpower |  | ClearSpace | CH | C | #REF! |  | 2
401400 | System mechanical and thermal architecture, SE | A4 | MISSION | Manpower |  | ClearSpace | CH | D | #REF! |  | 1.5
401410 | PD - Preliminary design | A4 | MISSION | Manpower
401411 | System optimisation and demisabilty | A4 | MISSION | Manpower
401412 | VESPA Mock-up design and manufacture | A4 | MISSION | Manpower
401413 | Satellite accomodation and re-entry simulations | A4 | MISSION | Manpower |  | Provision university/Belstead
401420 | DD - Detailed accomodation and integration | A4 | MISSION | Manpower
401422 | Mechanical parts procurement (in ME) | C12 | TECH | Procurement
401423 | SADM | C12 | TECH | Procurement
401500 | System electrical and data architecture, SE | A4 | MISSION | Manpower
401510 | PD - Preliminary design | A4 | MISSION | Manpower
401510 | Solar Panels specifications | A4 | MISSION | Manpower
401510 | EMC/ESD requirements and analyses | A4 | MISSION | Manpower
401520 | DD - Detailed design and integration | C12 | TECH | Procurement
401520 | Solar Panels detailed design and MAIT | C12 | TECH | Procurement
401520 | EMC/ESD detailed design and tests | C12 | TECH | Procurement
401530 | FlatSat and PFM Harness SE | A4 | MISSION | Manpower
401531 | Design and justification | A4 | MISSION | Manpower |  | ClearSpace | CH
401532 | SE and system level brakets | A4 | MISSION | Manpower |  | ClearSpace | CH
401533 | CAPT/RVS/COM harness | C12 | TECH | Procurement |  | ClearSpace | CH
401534 | EPS/OBDH/COM harness | C12 | TECH | Procurement |  | Airbus DS | DE
401535 | GNC and propulsion harness | C12 | TECH | Procurement |  | OHB-Sweden | SE
401536 | THERM harness | C12 | TECH | Procurement |  | APCO-Technologies | CH
401600 | System Rendezvous architecture, SE | A4 | MISSION | Manpower
401600 | HW architecture | A4 | MISSION | Manpower
401600 | SW architecture | A4 | MISSION | Manpower
401600 | Propulsion | A4 | MISSION | Manpower
401700 | MBSE VEPUP model | A4 | MISSION | Manpower |  | EPFL | CH
410000 | Flight Software (FSw) | B11 | TECH | Manpower |  | ClearSpace | CH
410100 | Flight software architecture and SE | B11 | TECH | Manpower |  | ClearSpace | CH
410200 | Application layer FSw - Preliminary design | B11 | TECH | Manpower |  | ClearSpace | CH
410210 | FLP FSw support - training | B11 | TECH | Manpower |  | Airbus DS | DE
410300 | Low level FSW - Preliminary design | B11 | TECH | Manpower |  | ClearSpace | CH
410400 | System level FDIR FSw- Preliminary design | B11 | TECH | Manpower |  | ClearSpace | CH
410500 | Application layer FSw - Implementation and Unit Testing | B11 | TECH | Manpower |  | ClearSpace | CH
410510 | FLP FSw support - integration | B11 | TECH | Manpower |  | Airbus DS | DE
410600 | Low level FSW - Design and production | B11 | TECH | Manpower |  | ClearSpace | CH
410700 | System level FDIR FSw - Design and production | B11 | TECH | Manpower |  | ClearSpace | CH
410800 | FSw implementation and validation | B11 | TECH | Manpower |  | ClearSpace | CH
410900 | FSw verification | B11 | TECH | Manpower |  | ClearSpace | CH
420000 | Electrical Power System (EPS) | B31 | MISSION | Manpower |  | Airbus DS | DE
420100 | EPS Systems Engineering and design | B31 | MISSION | Manpower |  | Airbus DS | DE
420200 | EPS Preliminary Design | B31 | MISSION | Manpower |  | Airbus DS | DE
420300 | EPS Detailed Design | B31 | MISSION | Manpower |  | Airbus DS | DE
420400 | EPS Verification | B31 | MISSION | Manpower |  | Airbus DS | DE
420800 | EPS AI&V support | B31 | MISSION | Manpower |  | Airbus DS | DE
430000 | On-Board Data Handling (OBDH) | B21 | MISSION | Manpower |  | Airbus DS | DE
430100 | OBDH Systems Engineering and design | B21 | MISSION | Manpower |  | Airbus DS | DE
430200 | OBDH Preliminary Design Updates | B21 | MISSION | Manpower |  | Airbus DS | DE
430300 | OBDH Detailed Design and procurement | B21 | MISSION | Manpower |  | Airbus DS | DE
430400 | OBDH Verification | B21 | MISSION | Manpower |  | Airbus DS | DE
430500 | OBDH AI&V support | B21 | MISSION | Manpower |  | Airbus DS | DE
440000 | Telecom | B41 | MISSION | Manpower
440100 | Telecom SE and design | B41 | MISSION | Manpower |  | ClearSpace | CH
440200 | S-band TM/TC | B41 | MISSION | Manpower |  | Airbus DS | DE
440210 | TM/TC Preliminary design | B41 | MISSION | Manpower
440220 | TM/TC Detailed design and procurement | B41 | MISSION | Manpower
440230 | TM/TC Software updates | B41 | MISSION | Manpower
440240 | TM/TC Verification | B41 | MISSION | Manpower
440250 | TM/TC AI&V support | B41 | MISSION | Manpower
440260 | … | B41 | MISSION | Manpower
440300 | Direct-Downlink System | B41 | MISSION | Manpower |  | ClearSpace | CH
440310 | DDS Preliminary design | B41 | MISSION | Manpower
440320 | DDS Detailed design and procurement | B41 | MISSION | Manpower
440330 | DDS Software | B41 | MISSION | Manpower
440340 | DDS Verification | B41 | MISSION | Manpower
440350 | DDS AI&V support | B41 | MISSION | Manpower
440360 | … | B41 | MISSION | Manpower
440400 | Subsystem Compatibility tests | B41 | MISSION | Manpower |  | ClearSpace | CH
450000 | Guidance Navigation & Control (GNC) | B51 | MISSION | Manpower |  | OHB-Sweden | SE
450100 | GNC Requirements and engineering | B51 | MISSION | Manpower |  | OHB-Sweden | SE
450110 | PD System Engineering Support | B51 | MISSION | Manpower |  | ClearSpace | CH
450200 | GNC Preliminary Design | B51 | MISSION | Manpower |  | OHB-Sweden | SE
450210 | Inputs to Preliminary Design | B51 | MISSION | Manpower |  | ClearSpace | CH
450300 | GNC DD Systems Engineering | B51 | MISSION | Manpower |  | OHB-Sweden | SE
450310 | DD System Enginnering Support | B51 | MISSION | Manpower |  | ClearSpace | CH
450400 | GNC Detailed Design | B51 | MISSION | Manpower |  | OHB-Sweden | SE
450410 | Inputs to Detailed Design | B51 | MISSION | Manpower |  | ClearSpace | CH
450500 | GNC Software Development |  | #N/A | #N/A |  | OHB-Sweden | SE
450510 | SW architectural design |  | #N/A | #N/A |  | OHB-Sweden | SE
450520 | SW detailed design and unit test |  | #N/A | #N/A |  | OHB-Sweden | SE
450521 | Inputs to SW detailed design and unit test |  | #N/A | #N/A |  | ClearSpace | CH
450530 | SW scenario testing |  | #N/A | #N/A |  | OHB-Sweden | SE
450531 | Inputs to SW scenario testing |  | #N/A | #N/A |  | ClearSpace | CH
450600 | Simulators |  | #N/A | #N/A |  | OHB-Sweden | SE
450610 | MIL/SIL simulator |  | #N/A | #N/A |  | OHB-Sweden | SE
450611 | Inputs to MIL/SIL simulator |  | #N/A | #N/A |  | ClearSpace | CH
450620 | Inputs to PIL-simulator |  | #N/A | #N/A |  | OHB-Sweden | SE
450630 | Inputs to HIL-simulator |  | #N/A | #N/A |  | OHB-Sweden | SE
450700 | Equipment procurement |  | #N/A | #N/A |  | OHB-Sweden | SE
450800 | GNC verification |  | #N/A | #N/A |  | OHB-Sweden | SE
450810 | Inputs to GNC verification |  | #N/A | #N/A |  | ClearSpace | CH
450900 | GNC AI&V support |  | #N/A | #N/A |  | OHB-Sweden | SE
460000 | Rendezvous Sensors and Processing (RVSP) |  |  |  |  | ClearSpace | CH
460100 | Systems Engineering | C11 | TECH | Manpower |  | ClearSpace | CH
460200 | PD - Onboard Processing Algorithms | C11 | TECH | Manpower |  | ClearSpace | CH
460201 | Development of synthetic images database | C11 | TECH | Manpower |  | EPFL | CH
460202 | Development of 6DoF target pose estimation algorithms | C11 | TECH | Manpower |  | EPFL | CH
460203 | FPGA based algorithms implementation | C11 | TECH | Manpower |  | EPFL | CH
460204 | Stereo imaging | C11 | TECH | Manpower |  | EPFL | CH
460300 | PD - Ground Support Tools | C11 | TECH | Manpower |  | ClearSpace | CH
460400 | DD - Onboard Processing Algorithms | C11 | TECH | Manpower |  | ClearSpace | CH
460500 | DD - Ground Support Tools | C11 | TECH | Manpower |  | ClearSpace | CH
460600 | Flight Software | C11 | TECH | Manpower |  | ClearSpace | CH
460610 | Architectural Design | C11 | TECH | Manpower
460620 | Implementation and Unit Testing | C11 | TECH | Manpower
460630 | Performance Validation | C11 | TECH | Manpower
460700 | Ground Support and Analysis Tools | C11 | TECH | Manpower |  | ClearSpace | CH
460800 | Simulation and Testing Tools | C11 | TECH | Manpower |  | ClearSpace | CH
460810 | Development Environment | C11 | TECH | Manpower
460820 | MIL/SIL Sensor Simulator | C11 | TECH | Manpower
460830 | Inputs to PIL-simulator | C11 | TECH | Manpower
460840 | Inputs to HIL-simulator | C11 | TECH | Manpower
460850 | Testing Framework | C11 | TECH | Manpower
460900 | Sensor Suite | C11 | TECH | Manpower |  | ClearSpace | CH
460901 | GNC RV Sensor suits requirements analysis | C11 | TECH | Manpower
460902 | Preliminary Architecture and Sensor Selection | C11 | TECH | Manpower
460903 | Preliminary Characterization and Modeling | C11 | TECH | Manpower
460904 | Preliminary SW Interfaces | C11 | TECH | Manpower
460905 | GNC RV Sensor suit technical specification | C11 | TECH | Manpower
460906 | Characterization and Modeling consolidation | C11 | TECH | Manpower
460907 | SW Interfaces consolidation | C11 | TECH | Manpower
460908 | Procurement Phase A/B | C11 | TECH | Manpower
460909 | GNC RV Sensor suits detailed definition | C11 | TECH | Manpower
460910 | Detailed characterization and Modeling | C11 | TECH | Manpower
460911 | Detailed SW interfaces | C11 | TECH | Manpower
460912 | Verification and Testing Phase A/B | C11 | TECH | Manpower
460913 | AI&V support Phase A/B | C11 | TECH | Manpower
460914 | Procurement Phase C/D | C11 | TECH | Manpower
460915 | Verification and Testing Phase C/D | C11 | TECH | Manpower
460916 | AI&V support Phase C/D | C11 | TECH | Manpower
460917 | Phase E/F activities | C11 | TECH | Manpower
461000 | RV Sensors Data Processing Unit (RVSDPU) |  | #N/A | #N/A |  | Syderal Swiss | CH
461010 | RVSPU-EBB Preliminary Design |  | #N/A | #N/A
461020 | RVSPU-EQM Design, Production and Test |  | #N/A | #N/A
461030 | RVSPU-PFM Design, Production and Tests |  | #N/A | #N/A
461040 | Detailed design |  | #N/A | #N/A
461050 | QM & FM production and tests |  | #N/A | #N/A
461060 | Verification and qualification |  | #N/A | #N/A
461100 | Subsystem Tests and Validation |  | #N/A | #N/A |  | ClearSpace | CH
461200 | Subsystem AI&V |  | #N/A | #N/A |  | ClearSpace | CH
470000 | Propulsion | B61 | MISSION | Manpower |  | OHB-Sweden | SE
470100 | Propulsion Subsystem design definition | B61 | MISSION | Manpower
470200 | Propulsion Subsystem design consolidation and analysis | B61 | MISSION | Manpower
470210 | Consolidation and Analyses | B61 | MISSION | Manpower
470220 | Electrical I/F and engineering model design | B61 | MISSION | Manpower
470230 | Subsystem performance analysis | B61 | MISSION | Manpower
470300 | Structural and Thermal Model (STM) design | B61 | MISSION | Manpower
470400 | Subsystem manufacturing, Assembly and Integration (MAI) | B61 | MISSION | Manpower
470410 | Procedure, tooling, fixture and MGSE design and manufacture | B61 | MISSION | Manpower
470420 | Engineering model (EM) and EGSE design and manufacture | B61 | MISSION | Manpower
470430 | Protoflight model (PFM) manufacturing, assembly and integration | B61 | MISSION | Manpower
470500 | Verification and tests | B61 | MISSION | Manpower
470510 | Verification and test plan | B61 | MISSION | Manpower
470520 | PGSE design and manufacture | B61 | MISSION | Manpower
470530 | PFM testing | B61 | MISSION | Manpower
470540 | Support to Sat AIT | B61 | MISSION | Manpower
470550 | PFM sub-assembly MAIT incl. Piping | B61 | MISSION | Manpower
470560 | Equipment procurement | B61 | MISSION | Manpower
480000 | Capture system | C21 | TECH | Manpower |  | ClearSpace | CH
480100 | System Engineering | C21 | TECH | Manpower
480110 | CS PD System Engineering | C21 | TECH | Manpower
480120 | CS DD System Engineering | C21 | TECH | Manpower
480130 | CS System Engineering for QM | C21 | TECH | Manpower
480140 | CS System Engineering for FM | C21 | TECH | Manpower
480200 | CS Mechanism Design | C21 | TECH | Manpower
480210 | Preliminary CS Mechanism Design | C21 | TECH | Manpower
480211 | Preliminary design damping structure | C21 | TECH | Manpower |  | RUAG-Space | CH
480212 | Miniaturized proximity sensor | C21 | TECH | Manpower |  | EPFL | CH
480220 | Detailed CS Mechanism Design | C21 | TECH | Manpower
480221 | Detailed design damping structure | C21 | TECH | Manpower |  | RUAG-Space | CH
480300 | CS Electrical / Control Design | C21 | TECH | Manpower
480310 | Preliminary CS Electrical/Control Design | C21 | TECH | Manpower
480311 | Fast adaptive control for the capture | C21 | TECH | Manpower |  | EPFL | CH
480320 | Detailed CS Electrical / Control Design | C21 | TECH | Manpower
480400 | Dynamic Capture Simulation SW | C21 | TECH | Manpower
480410 | Dynamic Capture Simulation SW Design | C21 | TECH | Manpower
480411 | Contact dynamics analyses and simulator | C21 | TECH | Manpower |  | EPFL | CH
480420 | Dynamic Capture Simulation SW Validation | C21 | TECH | Manpower
480500 | CS GSE Design and production | C21 | TECH | Manpower
480600 | CS MAIT | C21 | TECH | Manpower
480610 | CS EM1 | C21 | TECH | Manpower
480620 | CS EM2 | C21 | TECH | Manpower
480630 | CS QM MAIT | C21 | TECH | Manpower
480640 | CS FM MAIT | C21 | TECH | Manpower
490000 | Platform Mechanical Systems |  |  |  |  | APCO-Technologies | CH
490100 | System engineering support | B71 | TECH | Manpower
490200 | Structure Subsystem preliminary design | B71 | TECH | Manpower
490300 | Structure Subsystem detailed design and (structural + thermal) analysis | B71 | TECH | Manpower
490400 | Structure Subsystem STM MAIT | B71 | TECH | Manpower
490410 | Primary Structure (incl. Services Launch Adapter) | B71 | TECH | Manpower
490420 | Secondary structure | B71 | TECH | Manpower
490430 | Tertiary structure (Brackets) | B71 | TECH | Manpower
490440 | STM AIT / AIV | B71 | TECH | Manpower
490500 | Structure Subsystem PFM MAIT | B71 | TECH | Manpower
490510 | Primary Structure (incl. Services Launch Adapter) | B71 | TECH | Manpower
490520 | Secondary structure | B71 | TECH | Manpower
490530 | Tertiary structure (Brackets) | B71 | TECH | Manpower
490540 | Solar panels structure and mechanisms | B91 | MISSION | Procurement
490540 | Substrates | B91 | MISSION | Procurement
490540 | HDRMs and hinges | B91 | MISSION | Procurement
490550 | PFM AIT / AIV | B71 | TECH | Manpower
490600 | Thermal HW | B81 | TECH | Manpower
490610 | Thermal HW procurement | B81 | TECH | Manpower
490620 | Thermal HW AIT / AIV | B81 | TECH | Manpower
4A0000 | Additional Payloads |  | #N/A | #N/A
4A1000 |  |  | #N/A | #N/A
4A2000 | OB 3D-360 Videos |  | #N/A | #N/A |  | ClearSpace | CH
4A3000 | Ground Immersive technologies |  | #N/A | #N/A |  | ClearSpace | CH
4A4000 | Space debris payload |  | #N/A | #N/A |  | X
500000 | Assembly, Integration & Verification |  | #N/A | #N/A
501000 | Systems engineering | A5 | MISSION | Manpower
501000 | Electrical systems AIV system engineering | A5 | MISSION | Manpower
501000 | Mechanical systems AIV System engineering | A5 | MISSION | Manpower
501000 | DLR Consultancy test facility and reviews | A5 | MISSION | Manpower
510000 | Ground support Equipment | A6 | MISSION | Procurement
510100 | EGSE | A6 | MISSION | Procurement |  | OHB-Sweden | SE
510200 | MGSE | A6 | MISSION | Procurement |  | APCO-Technologies | CH
510210 | MGSE preliminary design | A6 | MISSION | Procurement |  | APCO-Technologies | CH
510220 | MGSE detailed design analysis | A6 | MISSION | Procurement |  | APCO-Technologies | CH
510230 | MGSE MAIT | A6 | MISSION | Procurement |  | APCO-Technologies | CH
520000 | STM AI&T | A5 | MISSION | Manpower |  | ClearSpace | CH
520100 | STM dummies models design, production and shipment | A5 | MISSION | Manpower |  | ClearSpace | CH
520200 | STM AI | A5 | MISSION | Manpower |  | OHB-Sweden | SE
520210 | Structure preparation and integration | A5 | MISSION | Manpower |  | APCO-Technologies | CH
520220 | Thermal preparation and integration | A5 | MISSION | Manpower |  | APCO-Technologies | CH
520230 | Rendezvous payload preparation and integration | A5 | MISSION | Manpower |  | ClearSpace | CH
520300 | STM V | A5 | MISSION | Manpower |  | OHB-Sweden | SE
530000 | FlatSat AI&T | A5 | MISSION | Manpower
530100 | EM FlatSat AI&T | A5 | MISSION | Manpower
530110 | BB CDPI FlatSat integration and shipment | A5 | MISSION | Manpower |  | Airbus DS | DE
530200 | PFM FlatSat AI&T | A5 | MISSION | Manpower
530210 | FM CDPI FlatSat integration and shipment | A5 | MISSION | Manpower
530220 | End-to-end communication tests | A5 | MISSION | Manpower
530300 | RV payload integration | A5 | MISSION | Manpower
540000 | RV payload ground tests and validation | C3 | 0 | 0
540100 | PIL/HIL tests | C3 | 0 | 0
540200 | Sensor EPOS/GMV Robotic tests | C3 | 0 | 0
540300 | Capture tests | C3 | 0 | 0
540400 | Hardware qualification tests | C3 | 0 | 0
550000 | System PFM AI&V | A5 | MISSION | Manpower
550100 | PFM assembly, integration and tests | A5 | MISSION | Manpower |  | OHB-Sweden | SE
550200 | PFM system environmental validation | A5 | MISSION | Manpower |  | OHB-Sweden | SE
550300 | PFM AIV Support | A5 | MISSION | Manpower |  | APCO-Technologies | CH
550400 | PFM Rendezvous payload AIV support | A5 | MISSION | Manpower |  | ClearSpace | CH
600000 | Ground Segment
610000 | Ground systems definition | E1 | MISSION | Manpower |  | ClearSpace | CH
610100 | Ground systems requirements and definition | E1 | MISSION | Manpower
610200 | Ground systems design | E1 | MISSION | Manpower
610300 | Logistics support definition | E1 | MISSION | Manpower
610400 | Ground and space-to-ground communication design and costing | E1 | MISSION | Manpower
620000 | Ground systems production
620100 | Ground stations preparation and operations | E4 | MISSION | Procurement |  | ClearSpace | CH
620200 | Mission Control system |  | #N/A | #N/A
620210 | PUS Service and packet definition |  | #N/A | #N/A |  | ClearSpace | CH
620220 | RAMSES Customization and deployment |  | #N/A | #N/A |  | OHB-Sweden | SE
620230 | Mission TM/TC database conversion |  | #N/A | #N/A |  | OHB-Sweden | SE
620240 | Mission Archives database |  | #N/A | #N/A |  | ClearSpace | CH
620250 | RV specific database |  | #N/A | #N/A |  | ClearSpace | CH
620300 | Mission management and data processing system |  | #N/A | #N/A
620310 | Mission planning and scheduling |  | #N/A | #N/A |  | ClearSpace | CH
620320 | RV specific data processing tools implementation and verification |  | #N/A | #N/A |  | ClearSpace | CH
620320 | Preliminary design |  | #N/A | #N/A
620320 | Detailed design and implementation |  | #N/A | #N/A
620320 | Verification |  | #N/A | #N/A
620330 | Flight dynamics software - detailed design, I&T |  | #N/A | #N/A |  | ClearSpace | CH
620331 | Detailed design and implementation |  | #N/A | #N/A
620332 | Verification and validation |  | #N/A | #N/A
620334 | Support to flight dynamics software verification/validation |  | #N/A | #N/A |  | OHB-Sweden | SE
620400 | Communication system |  | #N/A | #N/A |  | ClearSpace | CH
620410 | Preliminary defintion |  | #N/A | #N/A
620420 | Detailed definition and implementation |  | #N/A | #N/A
620500 | Mission Operations Centers |  | #N/A | #N/A
620510 | ClearSpace MOC |  | #N/A | #N/A |  | ClearSpace | CH
620520 | OHB support Centre |  | #N/A | #N/A |  | OHB-Sweden | SE
630000 | Ground systems AI&V |  | #N/A | #N/A
630100 | Systems AI&T |  | #N/A | #N/A
630200 | Segment AI&V |  | #N/A | #N/A
630300 | RAMSES Training for AI&V |  | #N/A | #N/A
640000 | Ground systems maintenance and disposal |  | #N/A | #N/A
640100 | Maintenance |  | #N/A | #N/A |  | ClearSpace | CH
640110 | RAMSES maintenance |  | #N/A | #N/A |  | OHB-Sweden | SE
640200 | Disposal |  | #N/A | #N/A |  | ClearSpace | CH
650000 | Ground Observations | E3 | TECH | Manpower
650100 | Target precise orbit position determination | E3 | TECH | Manpower |  | AIUB | CH
650200 | Target precise attitude determination | E3 | TECH | Manpower |  | AIUB | CH
650300 | VESPUP operations support | E3 | TECH | Manpower |  | AIUB | CH
650400 | Space debris collission avoidance support | E3 | TECH | Manpower
700000 | Mission Operations
710000 | Operations engineering | E2 | MISSION | Manpower
710100 | Flight direction | E2 | MISSION | Manpower
710200 | Configuration management | E2 | MISSION | Manpower |  | ClearSpace | CH
720000 | Preparation activities |  | #N/A | #N/A
720100 | Operations data production |  | #N/A | #N/A |  | ClearSpace | CH
720110 | Flight Operation procedures support |  | #N/A | #N/A |  | OHB-Sweden | SE
720200 | Operations data validation, scenario testing |  | #N/A | #N/A |  | ClearSpace | CH
720300 | Training |  | #N/A | #N/A
720310 | RAMSES Training |  | #N/A | #N/A |  | OHB-Sweden | SE
730000 | Pre-launch activities |  | #N/A | #N/A
730100 | Satellite shipping and launch site check out and preparation (FRR) |  | #N/A | #N/A |  | OHB-Sweden | SE
730200 | Satellite check-up and preparation |  | #N/A | #N/A |  | ClearSpace | CH
740000 | Operations execution activities |  | #N/A | #N/A
740100 | FSw operations upgrades and maintenance |  | #N/A | #N/A
740200 | LEOP and commissioning |  | #N/A | #N/A |  | ClearSpace | CH
740210 | Mission planning |  | #N/A | #N/A
740220 | Satellite operations |  | #N/A | #N/A
740221 | OHB-Sweden On-site support |  | #N/A | #N/A |  | OHB-Sweden | SE
740230 | Flight dynamics |  | #N/A | #N/A
740240 | Experts |  | #N/A | #N/A
740300 | Routine operations |  | #N/A | #N/A |  | ClearSpace | CH
740310 | Mission planning |  | #N/A | #N/A
740320 | Satellite operations |  | #N/A | #N/A
740321 | OHB-Sweden Off-site support |  | #N/A | #N/A |  | OHB-Sweden | SE
740330 | Flight dynamics |  | #N/A | #N/A
740340 | Experts |  | #N/A | #N/A
740400 | Critical operations |  | #N/A | #N/A
740410 | Mission planning |  | #N/A | #N/A
740420 | Satellite operations |  | #N/A | #N/A
740421 | OHB-Sweden On-site support |  | #N/A | #N/A |  | OHB-Sweden | SE
740430 | Flight dynamics |  | #N/A | #N/A
740440 | Experts |  | #N/A | #N/A
740500 | Disposal operations |  | #N/A | #N/A
740510 | Mission planning |  | #N/A | #N/A
740520 | Satellite operations |  | #N/A | #N/A
740521 | OHB-Sweden On-site support |  | #N/A | #N/A |  | OHB-Sweden | SE
740530 | Flight dynamics |  | #N/A | #N/A
740540 | Experts |  | #N/A | #N/A
750000 | Mission Data Analyses |  | #N/A | #N/A
750000 | GNC data analyses |  | #N/A | #N/A
750000 | Capture system data analyses |  | #N/A | #N/A
Contingency CH
Contingency OHB

## LEO Link Assumptions
Slant Range |  |  | Frequency
Parameter | Value | Unit | Parameter | Value | Unit
Min. elevation | 5 | ° | S-band TM upper frequency | 2.29 | GHz
Max. elevation | 90 | ° | S-band TC upper frequency | 2.11 | GHz
Max slant range | 1803.7823 | km | X-band Commercial | 8.4 | GHz
Min slant range | 400 | km
ε: Elevation Angle
R_e: Earth Radius
a: Semi Major Axis
D: Slant Range
Orbit
Parameter | Value | Unit
Semi-major axis | 6771 | km
Inclination | 98.8 | °
Mean Local Time of Ascending Node: | 34.2 | °
Eccentricity: | 0.009468
Argument of pericentre | 52 | °
Earth radius | 6371 | km
𝐷=√((𝑅_𝑒 sin(𝜖))^2+𝑎^2−𝑅_𝑒^2 )−𝑅_𝑒 sin⁡(𝜖)

## LEO Link Budget
TC worst case
Parameter | Value | Unit | Notes
GND
Tx Power | 3 | dBW
Total Transmission Line Losses | 0.5 | dB
Tx Ant Gain | 32 | dBi | 1.7m Dish with 60% Efficiency
Antenna pointing loss | 0.5 | dB
EIRP | 34 | dBW
UPLINK
FSPL | 164.0593 | dB
Rain Loss | 0 | dB
Athmospheric Loss | 1 | dB | Conservative estimate
Received Signal Level at SAT | -131.0593 | dB
SAT
S/C antenna Gain | -4 | dBi
K (Boltzmann) | -228.6 | dBW/K*Hz
Antenna noise temperature | 150 | K | One antenna pointing at earth, one at dark night sky
3dB Hybrid | 3.5 | dB | 3dB from splitting signal 50:50, 0.5dB insertion loss
Hybrid Equiv. Noise Temperature | 359.2291 | K
Cable + Diplexer Losses | 3 | dB | Some cabling and diplexer insertion loss
Cable Equiv. Noise Temperature | 288.6261 | K
LNA Gain | 20 | dB
LNA Noise Figure | 1.5 | dB
LNA Noise Temperature | 119.6359 | K
Receiver Noise Figure | 9 | dB
Receiver system noise temperature | 2013.5519 | K
Equivalent Noise temperature | 937.6266 | K
| 29.7203 | dBK
Channel Symbol Rate | 32 | ksps
| 45.0515 | dBHz
Eb/N0 | 15.2689 | dB
Required Eb/N0 | 9.6 | dB | uncoded BPSK/QPSK, BER=10e-5
Link margin | 5.6689
TM worst case
Parameter | LowRate | Unit | Notes
SAT
Tx Power | 3 | dBW
Total Transmission Line | 2 | dB | Approx. 0.5m RF harness and Diplexer
3dB Hybrid | 3 | dB
Tx Ant Gain | -4 | dBi
EIRP | -6 | dBW
DOWNLINK
FSPL | 164.7704 | dB
Rain Loss | 0 | dB
Athmospheric Loss | 1 | dB
Received Signal Level at GND | -171.7704 | dB
GND
GND Antenna Pointing Loss | 0.5 | dB
Antenna gain | 32 | dBi | 3.2m Dish with 60% Efficiency
K (Boltzmann) | -228.6 | dBW/K*Hz
Antenna noise temperature | 50 | K | At min elevation some sidelobes are looking at the earth
Cable Losses | 0.5 | dB
Cable Equiv. Noise Temperature | 35.3854 | K
LNA Gain | 30 | dB
LNA Noise Figure | 0.8 | dB
LNA Noise Temperature | 58.6567 | K
Receiver Noise Figure | 9 | dB
Receiver system noise temperature | 2013.5519 | K
Equivalent Noise temperature | 146.0556 | K
| 21.6452 | dBK
Channel Symbol Rate | 512 | ksps
| 57.0927 | dBHz
Eb/N0 | 10.0917 | dB
Required Eb/N0 | 9.6 | dB | uncoded BPSK/QPSK, BER=10e-5
Link margin | 0.49173
Required Eb/N0 with RS+CC | 2.3 | dB | BPSK/QPSK with Reed-Solomon and Convolutional Code, BER=10e-5
Link margin with RS+CC | 7.7917
PDD worst case
Parameter | LowRate | Unit | Notes
SAT
Tx Power | 5 | dBW
Total Transmission Line | 2 | dB | Approx. 0.5m RF harness and Diplexer
Tx Ant Gain | 25 | dBi
EIRP | 28 | dBW
DOWNLINK
FSPL | 176.0593 | dB
Rain Loss | 0.2 | dB
Athmospheric Loss | 1 | dB
Received Signal Level at GND | -149.2593 | dB
GND
GND Antenna Pointing Loss | 0.5 | dB
Antenna gain | 43 | dBi | 1.7m Dish with 60% Efficiency
K (Boltzmann) | -228.6 | dBW/K*Hz
Antenna noise temperature | 50 | K | At min elevation some sidelobes are looking at the earth
Cable Losses | 0.5 | dB
Cable Equiv. Noise Temperature | 35.3854 | K
LNA Gain | 40 | dB
LNA Noise Figure | 0.8 | dB
LNA Noise Temperature | 58.6567 | K
Receiver Noise Figure | 9 | dB
Receiver system noise temperature | 2013.5519 | K
Equivalent Noise temperature | 144.2434 | K
| 21.591 | dBK
G/T | 21.409
Channel Symbol Rate | 500 | Msps
Useful Data Rate | 8000 | Mbps
Useful Data Rate with TurboCode | 16000 | Mbps
| 86.9897 | dBHz
Eb/N0 | 13.7601 | dB
Required Eb/N0 | 14 | dB | uncoded 32-QAM, BER=10e-5
Link margin | -0.23993
Required Eb/N0 with RS+CC | 5.5 | dB | 32-QAM with TurboCode R=0.5, BER=10e-5, coding gain approx 9.5dB
Link margin with RS+CC | 8.2601

## Deep Space Link Budget
X-band Uplink TC
Parameter | Value | Unit | Notes
GND
Tx Power | 10 | dBW |  | X-band uplink | 7.2 | GHz
Total Transmission Line Losses | 0 | dB |  | X-band downlink | 8.5 | GHz
Tx Ant Gain | 75 | dBi | 70m Dish with 60% Efficiency, NASA DeepSpace Network | Ka-band downlink | 32 | GHz
Antenna pointing loss | 1 | dB |  | Distance | 628000000 | km | Earth-Jupiter
EIRP | 84 | dBW
UPLINK
FSPL | 285.5558 | dB
Rain Loss | 0.3 | dB
Athmospheric Loss | 1 | dB | Conservative estimate
Received Signal Level at SAT | -202.8558 | dB
SAT
S/C antenna Gain | 49 | dBi | 3m dish with 60% efficiency
K (Boltzmann) | -228.6 | dBW/K*Hz
Antenna noise temperature | 10 | K | Essentially just night sky
Cable Losses | 1 | dB | Probably not enough, see block diagram
Cable Equiv. Noise Temperature | 75.0884 | K
LNA Gain | 40 | dB
LNA Noise Figure | 0.5 | dB
LNA Noise Temperature | 35.3854 | K
Receiver Noise Figure | 9 | dB
Receiver system noise temperature | 2013.5519 | K
Equivalent Noise temperature | 120.6751 | K
| 20.8162 | dBK
Channel Symbol Rate | 14 | ksps
| 41.4613 | dBHz
Eb/N0 | 12.4667 | dB
Required Eb/N0 | 18 | dB | uncoded QPSK, BER=10e-9
Link margin | -5.5333
Required Eb/N0 | 8.5 | dB | QPSK with TurboCode R=1/6, BER=10e-9
Link margin | 3.9667
X-band Downlink TM
Parameter | LowRate | Unit | Notes
SAT
Tx Power | 17 | dBW | 50W TWTA
Total Transmission Line | 2 | dB | Probably not enough, see block diagram
Tx Ant Gain | 49 | dBi | 3m dish with 60% efficiency
EIRP | 64 | dBW
DOWNLINK
FSPL | 286.9976 | dB
Rain Loss | 0 | dB
Athmospheric Loss | 1 | dB
Received Signal Level at GND | -223.9976 | dB
GND
GND Antenna Pointing Loss | 0.5 | dB
Antenna gain | 75 | dBi | 70m Dish with 60% Efficiency, NASA DeepSpace Network
K (Boltzmann) | -228.6 | dBW/K*Hz
Antenna noise temperature | 10 | K | Only pointing at night sky, DSN has stations all over the earth
Cable Losses | 1 | dB
Cable Equiv. Noise Temperature | 75.0884 | K
LNA Gain | 30 | dB
LNA Noise Figure | 0.8 | dB
LNA Noise Temperature | 58.6567 | K
Receiver Noise Figure | 9 | dB
Receiver system noise temperature | 2013.5519 | K
Equivalent Noise temperature | 145.7586 | K
| 21.6363 | dBK
Channel Symbol Rate | 14 | ksps
| 41.4613 | dBHz
Eb/N0 | 16.5048 | dB
Required Eb/N0 | 18 | dB | uncoded QPSK, BER=10e-9
Link margin | -1.4952
Required Eb/N0 with RS+CC | 8.5 | dB | QPSK with TurboCode R=1/2, BER=10e-9
Link margin with RS+CC | 8.0048
Ka-Band Payload Downlink
Parameter | LowRate | Unit | Notes
SAT
Tx Power | 20 | dBW | TWTA
Total Transmission Line | 2 | dB | Probably not enough, see block diagram
Tx Ant Gain | 58 | dBi | 3m dish with 60% efficiency
EIRP | 76 | dBW
DOWNLINK
FSPL | 298.5122 | dB
Rain Loss | 2 | dB | Usually stations without rain can be chosen. DSN has many locations
Athmospheric Loss | 2 | dB
Received Signal Level at GND | -226.5122 | dB
GND
GND Antenna Pointing Loss | 0.5 | dB
Antenna gain | 86 | dBi | 70m Dish with 60% Efficiency, NASA DeepSpace Network
K (Boltzmann) | -228.6 | dBW/K*Hz
Antenna noise temperature | 50 | K | Only pointing at night sky, DSN has stations all over the earth
Cable Losses | 1 | dB
Cable Equiv. Noise Temperature | 75.0884 | K
LNA Gain | 30 | dB
LNA Noise Figure | 0.8 | dB
LNA Noise Temperature | 58.6567 | K
Receiver Noise Figure | 9 | dB
Receiver system noise temperature | 2013.5519 | K
Equivalent Noise temperature | 185.7586 | K
| 22.6895 | dBK
Channel Symbol Rate | 512 | ksps
| 57.0927 | dBHz
Eb/N0 | 8.3056 | dB
Required Eb/N0 | 18 | dB | uncoded QPSK, BER=10e-9
Link margin | -9.6944
Required Eb/N0 with RS+CC | 8.5 | dB | QPSK with TurboCode R=0.5, BER=10e-9
Link margin with RS+CC | -0.19438

## Price Table 8 CS (hidden)
New Table 8 breakdown
Industrial Price
| Economic Conditions | 2019
| Currency | k€
[8 empty] | Year | 2020 |  |  |  | 2021 |  |  |  | 2022 |  |  |  | 2023 |  |  |  | 2024 |  |  |  | 2025 |  |  |  | TOTAL | VERIF
[8 empty] | Phase | Phase A |  |  | Phase B | [5 empty] | Phase C |  |  |  | Phase D | [7 empty] | Phase E/F
T8 CODE | Price Breakdown |  |  | CAT | TYPE | CONC | WP# | Q | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
| Space Segment | [6 empty] | Milestone | KO |  |  | MSRR
| Spacecraft | [7 empty] | 2020-02-01 | 2020-04-01 | 2020-06-30 | 2021-01-31
Project Office:
A1 | Management |  |  | MGT | Manpower | MGTManpower | 110000 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
A2 | Product Assurance |  |  | MGT | Manpower | MGTManpower | 130000 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
A3 | (Project & Mission) Engineering |  |  | MISSION | Manpower | MISSIONManpower | 120000 140000 200000 310000 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Total Cost (k€)
A4 | Flight Systems Engineering |  |  | MISSION | Manpower | MISSIONManpower | 401000 | - 401422, 401423, 401520, 401533 to 401536 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
A5 | (System level) Assembly, Integration and Testing,Verification |  |  | MISSION | Manpower | MISSIONManpower | 501000 520000 530000 550000 | includes OHB-Sweden | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
A6 | Ground Segment Equipment |  |  | MISSION | Procurement | MISSIONProcurement | 510000 | includes OHB-Sweden (PGSE?), APCO | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Total Cost (k€)
Platform Module Hardware/Software (HW/SW)
OB Flight Software
B11 | FSW - Manpower (M/y) tech |  |  | TECH | Manpower | TECHManpower | 410000 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
B12 | FSW - Manpower (M/y) mission |  |  | MISSION | Manpower | MISSIONManpower |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Total Cost (k€)
Data Handling
B21 | Data Handling - Engineering |  |  | MISSION | Manpower | MISSIONManpower | 430000 | includes ADS | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
B22 | Data Handling - HW procurements |  |  | MISSION | Procurement | MISSIONProcurement | 430000 | includes ADS | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Total Cost (k€)
Electrical Power
B31 | Electrical Power - Engineering and SW |  |  | MISSION | Manpower | MISSIONManpower | 420000 | includes ADS | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
B32 | Electrical Power - HW procurements |  |  | MISSION | Procurement | MISSIONProcurement | 420000 | includes ADS | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Total Cost (k€)
Communications
B41 | Communications - Engineering and SW |  |  | MISSION | Manpower | MISSIONManpower | 440000 | ADS CS | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
B42 | Communications - HW procurements |  |  | MISSION | Procurement | MISSIONProcurement | 440000 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Total Cost (k€)
AOCS / GNC
B51 | AOCS / GNC - Engineering and SW |  |  | MISSION | Manpower | MISSIONManpower | 450000 | - OHB 450500, 450600, 450800, 45900 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
B52 | AOCS / GNC - HW procurements |  |  | MISSION | Procurement | MISSIONProcurement | 450000 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Total Cost (k€)
Propulsion
B61 | Propulsion - Engineering |  |  | MISSION | Manpower | MISSIONManpower | 470000 | OHB | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
B62 | Propulsion - HW procurements |  |  | MISSION | Procurement | MISSIONProcurement | 470000 | OHB | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
|  |  | Total Cost (k€) | [5 empty] | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| Structure | [7 empty] | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
B71 | Structure - Engineering |  |  | TECH | Manpower | TECHManpower | 490100 to 49500 | - 490540 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
B72 | Structure - HW |  |  | TECH | Procurement | TECHProcurement | 490100 to 49500 | - 490540 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
|  |  | Total Cost (k€) | [5 empty] | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| Thermal Control | [7 empty] | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
B81 | Thermal Control - Engineering |  |  | TECH | Manpower | TECHManpower | 490600 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
B82 | Thermal Control - HW |  |  | TECH | Procurement | TECHProcurement | 490600 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Total Cost (k€)
Mechanisms & harness
B91 | Mechanisms - HW procurements |  |  | MISSION | Procurement | MISSIONProcurement | 490540 | + 401422, 401423, 401520, 401533 to 401536 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Total Cost (k€)
Service Module HW/SW
Rendezvous GNC, Sensors and Processing (RVSP)
C11 | RVSP - Engineering and SW |  |  | TECH | Manpower | TECHManpower | 460100 to 460900 461000 41100to412000 461000 SYD +OHB 450500 450600 450800 450900 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
C12 | RVSP - HW procurements |  |  | TECH | Procurement | TECHProcurement | 460100 to 460900 461000 SYD | + 401422, 401423, 401520, 401533 to 401536 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Total Cost (k€)
Capture System (CS)
C21 | CS - Engineering and SW |  |  | TECH | Manpower | TECHManpower | 480000 | CS EPFL | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
C22 | CS - HW procurements |  |  | TECH | Procurement | TECHProcurement | 480000 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Total Cost (k€)
C3 | Service Module Validation |  |  | TECH | Procurement | TECHProcurement | 540000 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Risk Contingency (e.g. Technical, Management Reserve)
[33 empty] | 0 | #REF!
D | Launcher |  |  | MISSION | Procurement | MISSIONProcurement | 320000 | [25 empty] | 0 | #REF!
[33 empty] | 0 | #REF!
[9 empty] | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| Ground Segment & Operations | [7 empty] | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
E1 | Ground Control Centre Development |  |  | MISSION | Manpower | MISSIONManpower | 610000 62000-620100 INCL. OHB 630000 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
E2 | Mission Operations |  |  | MISSION | Manpower | MISSIONManpower | 710000 720000 730000 740000 750000 640000 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
E3 | Ground observations & tools |  |  | TECH | Manpower | TECHManpower | 650000 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
E4 | Ground Stations |  |  | MISSION | Manpower | MISSIONManpower | 620100 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
E5 | Ground Segment - Procurement |  |  | MISSION | Procurement | MISSIONProcurement | 620100 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
F | Contingency | [7 empty] | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
| TOT EX Contingency | [7 empty] | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| TOT with contingency | [7 empty] | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
|  |  |  | MGT | Manpower | MGTManpower |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
|  |  |  | MISSION | Manpower | MISSIONManpower |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
|  |  |  | TECH | Manpower | TECHManpower |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
|  |  |  | MISSION | Procurement | MISSIONProcurement |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
|  |  |  | TECH | Procurement | TECHProcurement |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[9 empty] | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[11 empty] | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[6 empty] | ManpowerSOR submission stretch |  |  | #REF!
[6 empty] | ManpowerSOR submission stretch additional manpower |  |  | #REF!
Note on H10: Brigitte Allegra: Work Package number
Note on H18: Brigitte Allegra: we don,t have this granularity in CS
Note on H19: Brigitte Allegra: 550000 is procurement

## Price Table 8 Airbus (hidden)
New Table 8 breakdown
Industrial Price
| Economic Conditions | 2019
| Currency | k€
[8 empty] | Year | 2020 |  |  |  | 2021 |  |  |  | 2022 |  |  |  | 2023 |  |  |  | 2024 |  |  |  | 2025 |  |  |  | TOTAL
[8 empty] | Phase | Phase A |  |  | Phase B
T8 CODE | Price Breakdown |  |  | CAT | TYPE | CONC | WP# | Q | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
| Space Segment | [6 empty] | Milestone | KO |  |  | MSRR
| Spacecraft | [7 empty] | 2020-02-01 | 2020-04-01 | 2020-06-30
Project Office:
A1 | Management |  |  | MGT | Manpower | MGTManpower | 110000 |  |  |  | 41.1217 | 116.229 | 118.9482 | 118.9482 | 118.9482 | 118.9482 | 121.7373 | 101.4392 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 856.32 | 0
A2 | Product Assurance |  |  | MGT | Manpower | MGTManpower | 130000 |  |  |  | 24.9336 | 72.5041 | 74.3154 | 67.3982 | 33.1775 | 21.2617 | 21.7924 | 21.7924 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 337.1752 | 0
A3 | (Project & Mission) Engineering |  |  | MISSION | Manpower | MISSIONManpower | 120000 140000 200000 310000 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0
Total Cost (k€)
A4 | Flight Systems Engineering |  |  | MISSION | Manpower | MISSIONManpower | 401000 | - 401422, 401423, 401520, 401533 to 401536 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0
A5 | (System level) Assembly, Integration and Testing,Verification |  |  | MISSION | Manpower | MISSIONManpower | 501000 520000 530000 550000 | includes OHB-Sweden |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0
A6 | Ground Segment Equipment |  |  | MISSION | Procurement | MISSIONProcurement | 510000 | includes OHB-Sweden (PGSE?), APCO | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0
Total Cost (k€)
Platform Module Hardware/Software (HW/SW)
OB Flight Software
B11 | FSW - Manpower (M/y) tech |  |  | TECH | Manpower | TECHManpower | 410000 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0
B12 | FSW - Manpower (M/y) mission |  |  | MISSION | Manpower | MISSIONManpower | ADS WP to see |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0
Total Cost (k€)
| CDPI | Combine & call CDPI
B21 | Data Handling - Engineering |  |  | MISSION | Manpower | MISSIONManpower | 430000 | includes ADS |  |  | 143.6502 | 469.1447 | 544.2542 | 126.6202 | 899.8942 | 589.7677 | 627.8258 | 380.9113 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 3782.0685 | 0
B22 | Data Handling - HW procurements |  |  | MISSION | Procurement | MISSIONProcurement | 430000 | includes ADS |  |  | 136.161 | 1093.8179 | 328.8729 | 929.7359 | 136.161 | 195.1996 | 0 | 2.3156 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 2822.264 | 0
Total Cost (k€)
Electrical Power
B31 | Electrical Power - Engineering and SW |  |  | MISSION | Manpower | MISSIONManpower | 420000 | includes ADS |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0
B32 | Electrical Power - HW procurements |  |  | MISSION | Procurement | MISSIONProcurement | 420000 | includes ADS |  |  | 0 | 92.988 | 92.988 | 79.704 | 106.272 | 0 | 159.408 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 531.36 | 0
Total Cost (k€)
Communications
B41 | Communications - Engineering and SW |  |  | MISSION | Manpower | MISSIONManpower | 440000 | ADS CS |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0
B42 | Communications - HW procurements |  |  | MISSION | Procurement | MISSIONProcurement | 440000 | ADS CS |  |  | 0 | 288.927 | 0 | 0 | 0 | 0 | 288.927 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 577.854 | 0
Total Cost (k€)
AOCS / GNC
B51 | AOCS / GNC - Engineering and SW |  |  | MISSION | Manpower | MISSIONManpower | 450000 | - OHB 450500, 450600, 450800, 45900 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0
B52 | AOCS / GNC - HW procurements |  |  | MISSION | Procurement | MISSIONProcurement | 450000 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0
Total Cost (k€)
Propulsion
B61 | Propulsion - Engineering |  |  | MISSION | Manpower | MISSIONManpower | 470000 | OHB |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0
B62 | Propulsion - HW procurements |  |  | MISSION | Procurement | MISSIONProcurement | 470000 | OHB |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0
Total Cost (k€)
Structure
B71 | Structure - Engineering |  |  | TECH | Manpower | TECHManpower | 490100 to 49500 | - 490540 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0
B72 | Structure - HW |  |  | TECH | Procurement | TECHProcurement | 490100 to 49500 | - 490540 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0
Total Cost (k€)
Thermal Control
B81 | Thermal Control - Engineering |  |  | TECH | Manpower | TECHManpower | 490600 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0
B82 | Thermal Control - HW |  |  | TECH | Procurement | TECHProcurement | 490600 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0
Total Cost (k€)
Mechanisms
B91 | Mechanisms - HW procurements |  |  | MISSION | Procurement | MISSIONProcurement | 490540 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0
Total Cost (k€)
Service Module HW/SW
Rendezvous GNC, Sensors and Processing (RVSP)
C11 | RVSP - Engineering and SW |  |  | TECH | Manpower | TECHManpower | 460100 to 460900 461000 41100to412000 461000 SYD +OHB 450500 450600 450800 450900 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0
C12 | RVSP - HW procurements |  |  | TECH | Procurement | TECHProcurement | 460100 to 460900 461000 SYD | + 401422, 401423, 401520, 401533 to 401536 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0
Total Cost (k€)
Capture System (CS)
C21 | CS - Engineering and SW |  |  | TECH | Manpower | TECHManpower | 480000 | CS EPFL |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0
C22 | CS - HW procurements |  |  | TECH | Procurement | TECHProcurement | 480000 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0
Total Cost (k€)
C3 | Service Module Validation |  |  | TECH | Procurement | TECHProcurement | 540000 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0
| Risk Contingency (e.g. Technical, Management Reserve) | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0
D | Launcher |  |  | MISSION | Procurement | MISSIONProcurement | 320000
Ground Segment & Operations
E1 | Ground Control Centre Development |  |  | MISSION | Manpower | MISSIONManpower | 610000 62000-620100 INCL. OHB 630000 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0
E2 | Mission Operations |  |  | MISSION | Manpower | MISSIONManpower | 710000 720000 730000 740000 750000 640000 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0
E3 | Ground observations & tools |  |  | TECH | Manpower | TECHManpower | 650000 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0
E4 | Ground Stations |  |  | MISSION | Procurement | MISSIONProcurement | 620100 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0
E5 | Ground Segment - Procurement |  |  | MISSION | Procurement | MISSIONProcurement | included in Flight SE and Ground Control Center Development |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0
F | Contingency | [9 empty] | 52.4264 | 164.4694 | 184.3794 | 78.2416 | 263.005 | 182.4944 | 192.8389 | 126.0357 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 1243.8909 | 0 | 12.25%
[33 empty] | 10150.9326 | 0
|  |  |  | MGT | Manpower | MGTManpower |  |  | 0 | 0 | 66.0553 | 188.7331 | 193.2636 | 186.3464 | 152.1257 | 140.2099 | 143.5297 | 123.2315 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1193.4952
|  |  |  | MISSION | Manpower | MISSIONManpower |  |  | 0 | 0 | 143.6502 | 469.1447 | 544.2542 | 126.6202 | 899.8942 | 589.7677 | 627.8258 | 380.9113 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3782.0685
|  |  |  | TECH | Manpower | TECHManpower |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | MISSION | Procurement | MISSIONProcurement |  |  | 0 | 0 | 136.161 | 1475.7329 | 421.8609 | 1009.4399 | 242.433 | 195.1996 | 448.335 | 2.3156 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3931.478
|  |  |  | TECH | Procurement | TECHProcurement |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[9 empty] | 0 | 0 | 345.8666 | 2133.6107 | 1159.3787 | 1322.4065 | 1294.4529 | 925.1772 | 1219.6906 | 506.4585 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8907.0417
[11 empty] | 398.293 | 2298.0802 | 1343.7581 | 1400.6482 | 1557.4579 | 1107.6716 | 1412.5294 | 632.4942 | [14 empty] | 10150.9326
Note on H10: Brigitte Allegra: Work Package number

## Airbus (hidden)
From Airbus email
Industrial Price
[5 empty] | Economic Conditions | 2019
[5 empty] | Currency | k€ |  |  | KO
[8 empty] | SOR SUBMED | 2020 Q1 | 2020 Q2 | 2020 Q3 | 2020 Q4 | 2021 Q1 | 2021 Q2 | 2021 Q3 | 2021 Q4 | 2022 Q1 | 2022 Q2 | 2022 Q3 | 2022 Q4
Euro, not K€!
[8 empty] | Launch Shift to 2025 |  | 2020 Q3 | 2020 Q4 | 2021 Q1 | 2021 Q2 | 2021 Q3 | 2021 Q4 | 2022 Q1 | 2022 Q2 | 2022 Q3 | 2022 Q4 | 2023 Q1
T8 Code | T8 Description | LEVEL | TYPE | WP element # | Price Breakdown |  |  | Development (Design and Manufacture) | bar: 2020 Q3; 2021 Q1; 2021 Q3; 2022 Q1; 2022 Q3; 2023 Q1
[5 empty] | Space Segment |  |  | 10196467 |  | 401744 | 2310138 | 1359215 | 1399435 | 1580054 | 1105953 | 1406678 | 633250 | 0 | 0 | 0
[5 empty] | Spacecraft |  |  | 7036989 |  | 265583 | 1053653 | 1266227 | 609243 | 1337621 | 913069 | 958343 | 633250 | 0 | 0 | 0
[5 empty] | Project Office |  |  | 0 |  | 2021 Q1: 0; 2022 Q3: 0
|  |  |  | 110400.1 |  | Management |  | 1077331 |  | 51735 | 146227 | 149648 | 149648 | 149648 | 149648 | 153157 | 127620 | 0 |  |  | 1077331
|  |  |  | 130400.1 |  | Product Assurance |  | 424417 |  | 31385 | 91264 | 93544 | 84837 | 41762 | 26763 | 27431 | 27431 | 0 |  |  | 424417
|  |  |  | 120400.1 420000.1 430000.1 440200.1 | - | Engineering: - System Engineering - Functional and Verification Engineering - Mechanical Engineering (OBC housing) - Electrical Engineering |  | 3328593 |  | 152949 | 495576 | 594284 | 32954 | 1007239 | 399288 | 363810 | 282493 | 0 |  |  | 3328593
|  |  |  | 12 | [5 empty] | 111729 | 348688 | 362033 | 507005 | 152537 | 152537 | 156351 | 133524 |  |  |  | 1924404 | 57.81%
|  |  |  | 42 | [5 empty] | 21170 | 190942 | 63911 | 59362 | 57088 | 249971 | 58516 | 39011 |  |  |  | 739971 | 22.23%
| 6260531 |  |  | 42 total | [5 empty] | 21170 | 217510 | 63911 | 99214 | 163360 | 249971 | 217924 | 39011
|  |  |  | 43 no HW | [5 empty] | 11190 | -70939 | 140783 | -556421 | 776881 | -30847 | 117073 | 88711 |  |  |  | 476431 | 14.31%
|  |  |  | 43 total | [5 empty] | 147351 | 803631 | 140783 | 154067 | 913042 | 162037 | 117073 | 88711
|  |  |  | 44 no HW | [5 empty] | 8860 | 26885 | 27557 | 23008 | 20733 | 27627 | 31870 | 21247 |  |  |  | 187787 | 5.642%
|  |  |  | 44 total | [5 empty] | 8860 | 315812 | 27557 | 23008 | 20733 | 27627 | 320797 | 21247
|  |  |  | 530000.1 | Assembly, Integration and Testing, and Verification |  |  | 1430190 |  | 29514 | 100072 | 97979 | 121290 | 138972 | 335041 | 413945 | 193377 | 0 |  |  | 1430190
|  |  |  | 53 total | [5 empty] | 29514 | 387006 | 521739 | 381656 | 138972 | 337370 | 413945 | 195706
|  |  |  | 530000.1 | Ground Support Equipment |  |  | 776458 |  | 2020 Q4: 220514; 2021 Q1: 330772; 2021 Q2: 220514; 2021 Q3: 0; 2021 Q4: 2329; 2022 Q2: 2329 | 776458
[5 empty] | Platform Module Hardware/Software (HW/SW) |  |  | 3159478 |  | 136161 | 1256485 | 92988 | 790192 | 242433 | 192884 | 448335 | 0 | 0 | 0 | 0
[5 empty] | CDPI + Transceiver + Battery |  |  | 0 |  | 2021 Q1: 0
[5 empty] | High Level sub-element |  |  | 0 |  | 2021 Q1: 0
|  |  |  | 430000.1 |  | CDPI/CPU boards |  | 544644 |  | 2020 Q3: 136161; 2020 Q4: 272322; 2021 Q2: 0; 2021 Q3: 136161 | 544644
|  |  |  | 430000.1 |  | CDPI/peripherie boards |  | 1104443 |  | 2020 Q4: 441777; 2021 Q1: 0; 2021 Q2: 662666; 2021 Q4: 0; 2022 Q2: 0 | 1104443
|  |  |  | 430000.1 |  | CDPI/MMU |  | 79704 |  | 2020 Q4: 31882; 2021 Q1: 0; 2021 Q2: 47822; 2021 Q4: 0; 2022 Q2: 0 | 79704
|  |  |  | 430000.1 |  | CDPI/PCDU |  | 321473 |  | 2020 Q4: 128589; 2021 Q1: 0; 2021 Q2: 0; 2021 Q4: 192884; 2022 Q2: 0
|  |  |  | 420000.1 |  | CDPI/power converter boards |  | 66420 |  | 2020 Q4: 26568; 2021 Q1: 0; 2021 Q2: 39852; 2021 Q4: 0; 2022 Q2: 0
|  |  |  | 420000.1 |  | Battery |  | 265680 |  | 2020 Q4: 0; 2021 Q2: 0; 2021 Q3: 106272; 2021 Q4: 0; 2022 Q1: 159408; 2022 Q2: 0
|  |  |  | 440200.1 |  | Transceiver + antennas |  | 577854 |  | 2020 Q4: 288927; 2021 Q1: 0; 2021 Q2: 0; 2021 Q4: 0; 2022 Q1: 288927; 2022 Q2: 0
|  |  |  | 530000.1 |  | Subassembly harness |  | 132840 |  | 2020 Q4: 66420; 2021 Q1: 66420; 2021 Q2: 0; 2021 Q4: 0; 2022 Q2: 0
|  |  |  | 530000.1 |  | CDPI/OBC Housing |  | 66420 |  | 2020 Q4: 0; 2021 Q1: 26568; 2021 Q2: 39852; 2021 Q4: 0; 2022 Q2: 0
[5 empty] | Risk Contingency (e.g. Technical, Management Reserve) |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[5 empty] | Industrial Price |  |  |  |  | 4.595% | 14.89% | 17.85% | 0.99% | 30.26% | 12% | 10.93% | 8.487%
[5 empty] | Economic Conditions | 2019
[5 empty] | Currency | k€ |  |  | KO
[8 empty] | SOR SUBMED | 2020 Q1 | 2020 Q2 | 2020 Q3 | 2020 Q4 | 2021 Q1 | 2021 Q2 | 2021 Q3 | 2021 Q4 | 2022 Q1 | 2022 Q2 | 2022 Q3 | 2022 Q4
[8 empty] | Launch Shift |  | 2020 Q3 | 2020 Q4 | 2021 Q1 | 2021 Q2 | 2021 Q3 | 2021 Q4 | 2022 Q1 | 2022 Q2 | 2022 Q3 | 2022 Q4
T8 Code | T8 Description | LEVEL | TYPE | WP element # | Price Breakdown |  |  | Development (Design and Manufacture) | [11 empty] | S2 | bar: KO 2020 Q2 2020 Q3; KO 2020 Q4 2021 Q1; KO 2021 Q2 2021 Q3; KO 2021 Q4 2022 Q1; KO 2022 Q2 2022 Q3
[5 empty] | Space Segment |  |  | 10150.9326 |  | 345.8666 | 2133.6107 | 1159.3787 | 1322.4065 | 1294.4529 | 925.1772 | 1219.6906 | 506.4585 | 0 | 0 | 0
[5 empty] | Spacecraft |  |  | 5747.5637 |  | 209.7056 | 877.1257 | 1066.3907 | 532.2145 | 1052.0199 | 732.2932 | 771.3556 | 506.4585 | 0 | 0 | 0
Project Office
A1 | Management | MGT | Manpower | 110400.1 |  | Management |  | 856.32 |  | 41.1217 | 116.229 | 118.9482 | 118.9482 | 118.9482 | 118.9482 | 121.7373 | 101.4392 | 0 | 0 | 0
A2 | Product Assurance | MGT | Manpower | 130400.1 |  | Product Assurance |  | 337.1752 |  | 24.9336 | 72.5041 | 74.3154 | 67.3982 | 33.1775 | 21.2617 | 21.7924 | 21.7924 | 0 | 0 | 0
B21 | Data Handling - Engineering | MISSION | Manpower | 120400.1 |  | System Engineering |  | 1498.2956 |  | 68.8467 | 223.073 | 267.5043 | 14.8335 | 453.3873 | 179.731 | 163.7614 | 127.1582 | 0 | 0 | 0
B21 | Data Handling - Engineering | MISSION | Manpower | 420000.1 |  | Functional and Verification Engineering |  | 576.124 |  | 26.4729 | 85.7759 | 102.8607 | 5.7038 | 174.3363 | 69.1101 | 62.9694 | 48.8948 | 0 | 0 | 0
B21 | Data Handling - Engineering | MISSION | Manpower | 430000.1 |  | Mechanical Engineering (OBC housing) |  | 370.9379 |  | 17.0446 | 55.2269 | 66.2269 | 3.6724 | 112.2466 | 44.4966 | 40.5429 | 31.481 | 0 | 0 | 0
B21 | Data Handling - Engineering | MISSION | Manpower | 440000.1 |  | Electrical Engineering |  | 146.2065 |  | 6.7182 | 21.7679 | 26.1036 | 1.4475 | 44.2424 | 17.5385 | 15.9801 | 12.4083 | 0 | 0 | 0
B21 | Data Handling - Engineering | MISSION | Manpower | 530000.1 | Assembly, Integration and Testing, and Verification |  |  | 1190.5045 |  | 24.5677 | 83.3009 | 81.5587 | 100.963 | 115.6817 | 278.8915 | 344.572 | 160.969 | 0 | 0 | 0
B22 | Data Handling - HW procurements | MISSION | Procurement | 530000.1 | Ground Support Equipment |  |  | 772 |  | 0 | 219.2479 | 328.8729 | 219.2479 | 0 | 2.3156 | 0 | 2.3156 | 0 | 0 | 0
[5 empty] | Platform Module Hardware/Software (HW/SW) |  |  | 3159.478 |  | 136.161 | 1256.485 | 92.988 | 790.192 | 242.433 | 192.884 | 448.335 | 0 | 0 | 0 | 0
CDPI + Transceiver + Battery
High Level sub-element
B22 | Data Handling - HW procurements | MISSION | Procurement | 430000.1 |  | CDPI/CPU boards |  | 544.644 |  | 136.161 | 272.322 | 0 | 0 | 136.161 | 0 | 0 | 0 | 0 | 0 | 0
B22 | Data Handling - HW procurements | MISSION | Procurement | 430000.1 |  | CDPI/peripherie boards |  | 1104.443 |  | 0 | 441.777 | 0 | 662.666 | 0 | 0 | 0 | 0 | 0 | 0 | 0
B22 | Data Handling - HW procurements | MISSION | Procurement | 430000.1 |  | CDPI/MMU |  | 79.704 |  | 0 | 31.882 | 0 | 47.822 | 0 | 0 | 0 | 0 | 0 | 0 | 0
B22 | Data Handling - HW procurements | MISSION | Procurement | 430000.1 |  | CDPI/PCDU |  | 321.473 |  | 0 | 128.589 | 0 | 0 | 0 | 192.884 | 0 | 0 | 0 | 0 | 0
B32 | Electrical Power - HW procurements | MISSION | Procurement | 420000.1 |  | CDPI/power converter boards |  | 66.42 |  | 0 | 26.568 | 0 | 39.852 | 0 | 0 | 0 | 0 | 0 | 0 | 0
B32 | Electrical Power - HW procurements | MISSION | Procurement | 420000.1 |  | Battery |  | 265.68 |  | 0 | 0 | 0 | 0 | 106.272 | 0 | 159.408 | 0 | 0 | 0 | 0
B42 | Communications - HW procurements | MISSION | Procurement | 440200.1 |  | Transceiver + antennas |  | 577.854 |  | 0 | 288.927 | 0 | 0 | 0 | 0 | 288.927 | 0 | 0 | 0 | 0
B32 | Electrical Power - HW procurements | MISSION | Procurement | 530000.1 |  | Subassembly harness |  | 132.84 |  | 0 | 66.42 | 66.42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
B32 | Electrical Power - HW procurements | MISSION | Procurement | 530000.1 |  | CDPI/OBC Housing |  | 66.42 |  | 0 | 0 | 26.568 | 39.852 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F | Contingency | 0 | 0 |  | Risk Contingency (e.g. Technical, Management Reserve) |  |  | 1243.8909 |  | 52.4264 | 164.4694 | 184.3794 | 78.2416 | 263.005 | 182.4944 | 192.8389 | 126.0357 | 0 | 0 | 0
[7 empty] | Manpower | 4730.869 | 4975.5637 | 25% | 25% | 25% | 25% | 25% | 25% | 25% | 25%
[7 empty] | Procurement | 3931.478 | 0.8
25%
Industrial Price
[5 empty] | Economic Conditions | 2019
[5 empty] | Currency | k€
[8 empty] | TOTAL SUBMITTED | 2020 | KO 2020 Q3 2020 Q4: 2021; KO 2021 Q1 2021 Q2: 2022; KO 2021 Q3 2021 Q4: TOTAL SUBMITTED; KO 2021 Q4 2022 Q1: VERIF
|  |  |  | WP element # | Price Breakdown |  |  | Development (Design and Manufacture) | S1 | bar: KO 2020 Q2 2020 Q3 to KO 2021 Q2 2021 Q3
[5 empty] | Space Segment |  |  | 10150.733 | 1396.859 | 2943.681 | 3057.224 | 2121.535 | 631.462 | 0 | 10150.761 |  | FALSE
[5 empty] | Spacecraft |  |  | 6991.255 | 372.24 | 2382.131 | 1971.162 | 1636.103 | 629.651 | 0 | 6991.287
[5 empty] | Project Office |  |  |  |  | KO 2021 Q3 2021 Q4: 0
|  |  |  | 110400.1 |  | Management |  | 1070.4 | 51.735 | KO 2020 Q2 2020 Q3: 292.452; KO 2020 Q3 2020 Q4: 299.296; KO 2020 Q4 2021 Q1: 299.296; KO 2021 Q1 2021 Q2: 127.62; KO 2021 Q3 2021 Q4: 1070.399
|  |  |  | 130400.1 |  | Product Assurance |  | 421.469 | 31.385 | KO 2020 Q2 2020 Q3: 182.528; KO 2020 Q3 2020 Q4: 126.599; KO 2020 Q4 2021 Q1: 53.526; KO 2021 Q1 2021 Q2: 27.431; KO 2021 Q3 2021 Q4: 421.469
|  |  |  | 120400.1 420000.1 430000.1 440200.1 |  | Engineering: - System Engineering - Functional and Verification Engineering - Mechanical Engineering (OBC housing) - Electrical Engineering |  | 3239.455 | 149.349 | KO 2020 Q2 2020 Q3: 1024.027; KO 2020 Q3 2020 Q4: 1245.153; KO 2020 Q4 2021 Q1: 542.065; KO 2021 Q1 2021 Q2: 278.894; KO 2021 Q3 2021 Q4: 3239.488
|  |  |  | 530000.1 | Assembly, Integration and Testing, and Verification |  |  | 1488.1306 | 29.514 | KO 2020 Q2 2020 Q3: 221.58; KO 2020 Q3 2020 Q4: 300.114; KO 2020 Q4 2021 Q1: 741.216; KO 2021 Q1 2021 Q2: 195.706; KO 2021 Q3 2021 Q4: 1488.13
|  |  |  | 530000.1 | Ground Support Equipment |  |  | 771.8004 | 110.257 | KO 2020 Q2 2020 Q3: 661.544; KO 2020 Q3 2020 Q4: 0; KO 2020 Q4 2021 Q1: 0; KO 2021 Q1 2021 Q2: 0; KO 2021 Q3 2021 Q4: 771.801
[5 empty] | Platform Module Hardware/Software (HW/SW) |  |  | 3159.478 | 1024.619 | 561.55 | 1086.062 | 485.432 | 1.811 | 0 | 3159.474
[5 empty] | CDPI + Transceiver + Battery |  |  |  |  | KO 2021 Q3 2021 Q4: 0
[5 empty] | High Level sub-element |  |  |  |  | KO 2021 Q3 2021 Q4: 0
|  |  |  | 430000.1 |  | CDPI/CPU boards |  | 544.644 | 133.444 | KO 2020 Q2 2020 Q3: 269.302; KO 2020 Q3 2020 Q4: 136.462; KO 2020 Q4 2021 Q1: 3.622; KO 2021 Q1 2021 Q2: 1.811; KO 2021 Q3 2021 Q4: 544.641
|  |  |  | 430000.1 |  | CDPI/peripherie boards |  | 1104.443 | 441.777 | KO 2020 Q2 2020 Q3: 0; KO 2020 Q3 2020 Q4: 662.666; KO 2020 Q4 2021 Q1: 0; KO 2021 Q1 2021 Q2: 0; KO 2021 Q3 2021 Q4: 1104.443
|  |  |  | 430000.1 |  | CDPI/MMU |  | 79.704 | 31.882 | KO 2020 Q2 2020 Q3: 0; KO 2020 Q3 2020 Q4: 47.822; KO 2020 Q4 2021 Q1: 0; KO 2021 Q1 2021 Q2: 0; KO 2021 Q3 2021 Q4: 79.704
|  |  |  | 430000.1 |  | CDPI/PCDU |  | 321.473 | 128.589 | KO 2020 Q2 2020 Q3: 0; KO 2020 Q3 2020 Q4: 0; KO 2020 Q4 2021 Q1: 192.883; KO 2021 Q1 2021 Q2: 0; KO 2021 Q3 2021 Q4: 321.472
|  |  |  | 420000.1 |  | CDPI/power converter boards |  | 66.42 | 0 | KO 2020 Q2 2020 Q3: 26.568; KO 2020 Q3 2020 Q4: 39.852; KO 2020 Q4 2021 Q1: 0; KO 2021 Q1 2021 Q2: 0; KO 2021 Q3 2021 Q4: 66.42
|  |  |  | 420000.1 |  | Battery |  | 265.68 | 0 | KO 2020 Q2 2020 Q3: 106.272; KO 2020 Q3 2020 Q4: 159.408; KO 2020 Q4 2021 Q1: 0; KO 2021 Q1 2021 Q2: 0; KO 2021 Q3 2021 Q4: 265.68
|  |  |  | 440200.1 |  | Transceiver + antennas |  | 577.854 | 288.927 | KO 2020 Q2 2020 Q3: 0; KO 2020 Q3 2020 Q4: 0; KO 2020 Q4 2021 Q1: 288.927; KO 2021 Q1 2021 Q2: 0; KO 2021 Q3 2021 Q4: 577.854
|  |  |  | 530000.1 |  | Subassembly harness |  | 132.84 | 0 | KO 2020 Q2 2020 Q3: 132.84; KO 2020 Q3 2020 Q4: 0; KO 2020 Q4 2021 Q1: 0; KO 2021 Q1 2021 Q2: 0; KO 2021 Q3 2021 Q4: 132.84
|  |  |  | 530000.1 |  | CDPI/OBC Housing |  | 66.42 | 0 | KO 2020 Q2 2020 Q3: 26.568; KO 2020 Q3 2020 Q4: 39.852; KO 2020 Q4 2021 Q1: 0; KO 2021 Q1 2021 Q2: 0; KO 2021 Q3 2021 Q4: 66.42
[5 empty] | Risk Contingency (e.g. Technical, Management Reserve) |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6219.4546
[7 empty] | FTE hours/ Year | 1650 | 412.5
[9 empty] | 2020 II | 2020 III | 2020 IV | 2021 I | 2021 II | 2021 III | 2021 IV | 2022 I | L2024
[7 empty] | CA T E G O R Y | WP TOTAL | 2021 I | 2021 II | 2021 III | 2021 IV | 2022 I | 2022 II | 2022 III | 2022 IV | L2025
[7 empty] | TOTAL DIRECT LABOUR HOURS | 34516 | 1505 | 4732 | 5221 | 6262 | 3704 | 4830 | 5194 | 3070
[7 empty] | 1. TOTAL DIRECT LABOUR COSTS | 5574409 | 242690 | 761426 | 835254 | 1009152 | 605065 | 776121 | 831257 | 513445
[7 empty] | 2. INT. SPECIAL FACILITIES | 67916 | 339 | 1356 | 1356 |  | 11253 | 16394 | 26016 | 11202
OTHER COST ELEMENTS
[7 empty] | FTE |  | 3.6485 | 11.4715 | 12.657 | 15.1806 | 8.9794 | 11.7091 | 12.5915 | 7.4424
[7 empty] | 3.1 - 3.4 MATERIAL COST | 714630 | 102090 | KO 2020 Q2 2020 Q3: 306270; KO 2020 Q3 2020 Q4: 306270
3.5 HIREL-PARTS
[7 empty] | 3.6 EXT. MAJOR PRODUCTS | 2925443 | 948721 | 333777 | 186177 | 75477 | 1078967 | 298968 | 1677 | 1677
3.7 EXTERNAL SERVICES
[7 empty] | 3.8 TRANSPORT/INSURANCE | 25625 |  | KO 2021 Q4 2022 Q1: 25625
[7 empty] | 3.9 TRAVELS | 44506 | 776 | 2329 | 2329 | 2329 | 2329 | 2329 | 2329 | 29758
3.10 MISCELLANEOUS
[7 empty] | 3. TOTAL OTHER DIRECT COST | 3710204 | 1051588 | 642376 | 494776 | 77806 | 1081296 | 301297 | 4006 | 57060
5.-7. GENERAL EXPENSES
[7 empty] | 8. TOTAL COST OF ALL WPS | 9352529 | 1294616 | 1405158 | 1331387 | 1086957 | 1697613 | 1093811 | 861280 | 581707
9. OVERHEADS ON SUBCONTRACTORS
[7 empty] | 10. * SUB - TOTAL (1. TO 9.) | 9352529 | 1294616 | 1405158 | 1331387 | 1086957 | 1697613 | 1093811 | 861280 | 581707
[7 empty] | 11. PROFIT ON SUB-TOTAL (10.) | 748202 | 103.569 | 112.413 | 106.511 | 86.957 | 135809 | 87505 | 68902 | 46537
[7 empty] | 12. COST WITHOUT ADD. CHARGE | 50000 | 2273 | 6818 | 6818 | 6818 | 6818 | 6818 | 6818 | 6818
[7 empty] | 13. ** TOTAL COMPANY PRICE | 10150732 | 1400458 | 1524389 | 1444716 | 1180732 | 1840240 | 1188134 | 937000 | 635061
14. SUB - CONTRACTS
[7 empty] | 15. *** GRAND TOTAL PRICE (LC) | 10150732 | 1400458 | 1524389 | 1444716 | 1180732 | 1840240 | 1188134 | 937000 | 635061
[9 empty] | 1400.458 | 1524.389 | 1444.716 | 1180.732 | 1840.24 | 1188.134 | 937 | 635.061
0.14319

## Price Table 8 AIUB (hidden)
New Table 8 breakdown
Industrial Price
| Economic Conditions | 2019
| Currency | k€ | please specify currency
[8 empty] | Year | 2020 |  |  |  | 2021 |  |  |  | 2022 |  |  |  | 2023 |  |  |  | 2024 |  |  |  | 2025 |  |  |  | TOTAL
[8 empty] | Phase | Phase A |  |  | Phase B
T8 CODE | Price Breakdown |  |  | CAT | TYPE | CONC | WP# | Q | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
| Space Segment | [6 empty] | Milestone | KO |  |  | MSRR
| Spacecraft | [7 empty] | 2020-02-01 | 2020-04-01 | 2020-06-30 | 2021-01-31
Project Office:
A1 | Management |  |  | MGT | Manpower | MGTManpower | 110000 | [25 empty] | 0
A2 | Product Assurance |  |  | MGT | Manpower | MGTManpower | 130000 |  | 0.84006 | 0.84006 | 0.84006 | 0.84006 | 0.84006 | 0.84006 | 0.84006 | 0.84006 | 0.84006 | 0.84006 | 0.84006 | 0.84006 | 0.84006 | 0.84006 | 0.84006 | 0.84006 | 1.433 | 1.433 | 1.433 | 1.433 | 1.4746 | 1.4746 | 1.4746 | 1.4746 | 25.0714
A3 | (Project & Mission) Engineering |  |  | MISSION | Manpower | MISSIONManpower | 120000 140000 200000 310000 | [25 empty] | 0
|  |  | Total Cost (k€) | [29 empty] | 0
A4 | Flight Systems Engineering |  |  | MISSION | Manpower | MISSIONManpower | 401000 | - 401422, 401423, 401520, 401533 to 401536 | [24 empty] | 0
A5 | (System level) Assembly, Integration and Testing,Verification |  |  | MISSION | Manpower | MISSIONManpower | 501000 520000 530000 550000 | includes OHB-Sweden | [24 empty] | 0
A6 | Ground Segment Equipment |  |  | MISSION | Procurement | MISSIONProcurement | 510000 | includes OHB-Sweden (PGSE?), APCO | [24 empty] | 0
|  |  | Total Cost (k€) | [29 empty] | 0
| Platform Module Hardware/Software (HW/SW) | [31 empty] | 0
| OB Flight Software | [31 empty] | 0
B11 | FSW - Manpower (M/y) tech |  |  | TECH | Manpower | TECHManpower | 410000 | [25 empty] | 0
B12 | FSW - Manpower (M/y) mission |  |  | MISSION | Manpower | MISSIONManpower | [26 empty] | 0
|  |  | Total Cost (k€) | [29 empty] | 0
| Data Handling | [31 empty] | 0
B21 | Data Handling - Engineering |  |  | MISSION | Manpower | MISSIONManpower | 430000 | includes ADS | [24 empty] | 0
B22 | Data Handling - HW procurements |  |  | MISSION | Procurement | MISSIONProcurement | 430000 | includes ADS | [24 empty] | 0
|  |  | Total Cost (k€) | [29 empty] | 0
| Electrical Power | [31 empty] | 0
B31 | Electrical Power - Engineering and SW |  |  | MISSION | Manpower | MISSIONManpower | 420000 | includes ADS | [24 empty] | 0
B32 | Electrical Power - HW procurements |  |  | MISSION | Procurement | MISSIONProcurement | 420000 | includes ADS | [24 empty] | 0
|  |  | Total Cost (k€) | [29 empty] | 0
| Communications | [31 empty] | 0
B41 | Communications - Engineering and SW |  |  | MISSION | Manpower | MISSIONManpower | 440000 | ADS CS | [24 empty] | 0
B42 | Communications - HW procurements |  |  | MISSION | Procurement | MISSIONProcurement | [26 empty] | 0
|  |  | Total Cost (k€) | [29 empty] | 0
| AOCS / GNC | [31 empty] | 0
B51 | AOCS / GNC - Engineering and SW |  |  | MISSION | Manpower | MISSIONManpower | 450000 | - OHB 450500, 450600, 450800, 45900 | [24 empty] | 0
B52 | AOCS / GNC - HW procurements |  |  | MISSION | Procurement | MISSIONProcurement | [26 empty] | 0
|  |  | Total Cost (k€) | [29 empty] | 0
| Propulsion | [31 empty] | 0
B61 | Propulsion - Engineering |  |  | MISSION | Manpower | MISSIONManpower | 470000 | OHB | [24 empty] | 0
B62 | Propulsion - HW procurements |  |  | MISSION | Procurement | MISSIONProcurement | 470000 | OHB | [24 empty] | 0
|  |  | Total Cost (k€) | [29 empty] | 0
| Structure | [31 empty] | 0
B71 | Structure - Engineering |  |  | TECH | Manpower | TECHManpower | 490100 to 49500 | - 490540 | [24 empty] | 0
B72 | Structure - HW |  |  | TECH | Procurement | TECHProcurement | 490100 to 49500 | - 490540 | [24 empty] | 0
|  |  | Total Cost (k€) | [29 empty] | 0
| Thermal Control | [31 empty] | 0
B81 | Thermal Control - Engineering |  |  | TECH | Manpower | TECHManpower | 490600 | [25 empty] | 0
B82 | Thermal Control - HW |  |  | TECH | Procurement | TECHProcurement | 490600 | [25 empty] | 0
|  |  | Total Cost (k€) | [29 empty] | 0
| Mechanisms | [31 empty] | 0
B91 | Mechanisms - HW procurements |  |  | MISSION | Procurement | MISSIONProcurement | 490540 | [25 empty] | 0
|  |  | Total Cost (k€) | [29 empty] | 0
| Service Module HW/SW | [31 empty] | 0
| Rendezvous GNC, Sensors and Processing (RVSP) | [31 empty] | 0
C11 | RVSP - Engineering and SW |  |  | TECH | Manpower | TECHManpower | 460100 to 460900 461000 41100to412000 461000 SYD +OHB 450500 450600 450800 450900 | [25 empty] | 0
C12 | RVSP - HW procurements |  |  | TECH | Procurement | TECHProcurement | 460100 to 460900 461000 SYD | + 401422, 401423, 401520, 401533 to 401536 | [24 empty] | 0
|  |  | Total Cost (k€) | [29 empty] | 0
| Capture System (CS) | [31 empty] | 0
C21 | CS - Engineering and SW |  |  | TECH | Manpower | TECHManpower | 480000 | CS EPFL | [24 empty] | 0
C22 | CS - HW procurements |  |  | TECH | Procurement | TECHProcurement | 480000 | [25 empty] | 0
|  |  | Total Cost (k€) | [29 empty] | 0
C3 | Service Module Validation |  |  | TECH | Procurement | TECHProcurement | 540000 | [25 empty] | 0
| Risk Contingency (e.g. Technical, Management Reserve) | [31 empty] | 0
0
D | Launcher |  |  | MISSION | Procurement | MISSIONProcurement | 320000 | [25 empty] | 0
0
0
| Ground Segment & Operations | [31 empty] | 0
E1 | Ground Control Centre Development |  |  | MISSION | Manpower | MISSIONManpower | 610000 62000-620100 INCL. OHB 630000 | [25 empty] | 0
E2 | Mission Operations |  |  | MISSION | Manpower | MISSIONManpower | 710000 720000 730000 740000 750000 640000 | [25 empty] | 0
E3 | Ground observations & tools |  |  | TECH | Manpower | TECHManpower | 650000 |  | 20.4107 | 20.4107 | 20.4107 | 20.4107 | 20.4107 | 20.4107 | 20.4107 | 20.4107 | 20.4107 | 20.4107 | 20.4107 | 20.4107 | 20.4107 | 20.4107 | 20.4107 | 20.4107 | 34.8183 | 34.8183 | 34.8183 | 34.8183 | 35.8268 | 35.8268 | 35.8268 | 35.8268 | 609.1518
E4 | Ground Stations |  |  | MISSION | Procurement | MISSIONProcurement | 620100 | [25 empty] | 0
E5 | Ground Segment - Procurement |  |  | MISSION | Procurement | MISSIONProcurement | included in Flight SE and Ground Control Center Development | [25 empty] | 0
F | Contingency | [7 empty] | 4.2502 | 4.2502 | 4.2502 | 4.2502 | 4.2502 | 4.2502 | 4.2502 | 4.2502 | 4.2502 | 4.2502 | 4.2502 | 4.2502 | 4.2502 | 4.2502 | 4.2502 | 4.2502 | 7.2503 | 7.2503 | 7.2503 | 7.2503 | 7.4603 | 7.4603 | 7.4603 | 7.4603 | 126.8446
| TOT EX Contingency | [7 empty] | 21.2508 | 21.2508 | 21.2508 | 21.2508 | 21.2508 | 21.2508 | 21.2508 | 21.2508 | 21.2508 | 21.2508 | 21.2508 | 21.2508 | 21.2508 | 21.2508 | 21.2508 | 21.2508 | 36.2513 | 36.2513 | 36.2513 | 36.2513 | 37.3014 | 37.3014 | 37.3014 | 37.3014 | 634.2232 | 0
| TOT with contingency | [7 empty] | 25.5009 | 25.5009 | 25.5009 | 25.5009 | 25.5009 | 25.5009 | 25.5009 | 25.5009 | 25.5009 | 25.5009 | 25.5009 | 25.5009 | 25.5009 | 25.5009 | 25.5009 | 25.5009 | 43.5016 | 43.5016 | 43.5016 | 43.5016 | 44.7616 | 44.7616 | 44.7616 | 44.7616 | 761.0679
|  |  |  | MGT | Manpower | MGTManpower |  |  | 0.84006 | 0.84006 | 0.84006 | 0.84006 | 0.84006 | 0.84006 | 0.84006 | 0.84006 | 0.84006 | 0.84006 | 0.84006 | 0.84006 | 0.84006 | 0.84006 | 0.84006 | 0.84006 | 1.433 | 1.433 | 1.433 | 1.433 | 1.4746 | 1.4746 | 1.4746 | 1.4746 | 25.0714
|  |  |  | MISSION | Manpower | MISSIONManpower |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | TECH | Manpower | TECHManpower |  |  | 20.4107 | 20.4107 | 20.4107 | 20.4107 | 20.4107 | 20.4107 | 20.4107 | 20.4107 | 20.4107 | 20.4107 | 20.4107 | 20.4107 | 20.4107 | 20.4107 | 20.4107 | 20.4107 | 34.8183 | 34.8183 | 34.8183 | 34.8183 | 35.8268 | 35.8268 | 35.8268 | 35.8268 | 609.1518
|  |  |  | MISSION | Procurement | MISSIONProcurement |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | TECH | Procurement | TECHProcurement |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[9 empty] | 21.2508 | 21.2508 | 21.2508 | 21.2508 | 21.2508 | 21.2508 | 21.2508 | 21.2508 | 21.2508 | 21.2508 | 21.2508 | 21.2508 | 21.2508 | 21.2508 | 21.2508 | 21.2508 | 36.2513 | 36.2513 | 36.2513 | 36.2513 | 37.3014 | 37.3014 | 37.3014 | 37.3014 | 634.2232
Note on H10: Brigitte Allegra: Work Package number

## AIUB (hidden)
|  | Exchange Rate |  | CHF/EUR | 1.12
|  | START |  | 2020-02-01 | 2021-02-01 | 2022-02-01 | 2023-02-01 | 2024-02-01 | 2025-02-01
T8 code | T8 descr | END |  | 2021-01-01 | 2022-01-01 | 2023-01-01 | 2024-01-01 | 2025-01-01 | 2025-12-01
E3 | 650100 | R&D for precise orbit determination | manpower | 13.441 | 13.441 | 13.441 | 13.441 | 22.9288 | 23.5929 | 112320
E3 | 650200 | R&D for precise attitude determination | manpower | 13.441 | 13.441 | 13.441 | 13.441 | 22.9288 | 23.5929 | 112320
E3 | 650300 | VESPUP mission design support | manpower | 13.7733 | 13.7733 | 13.7733 | 13.7733 | 23.4956 | 24.1762 | 115096.67
E3 | 650300 | VESPUP operations support | manpower | 27.5466 | 27.5466 | 27.5466 | 27.5466 | 46.9912 | 48.3523 | 230193.33
E3 | 650300 | Space debris collision avoidance | manpower | 13.441 | 13.441 | 13.441 | 13.441 | 22.9288 | 23.5929 | 112320
A1 | 110800 | Project Management | manpower | 3.3603 | 3.3603 | 3.3603 | 3.3603 | 5.7322 | 5.8982 | 28080
|  | TOT |  | 85.0031 | 85.0031 | 85.0031 | 85.0031 | 145.0053 | 149.2055 | 710330
634.2232
|  | Exchange Rate |  | CHF/EUR | 1.12
|  | FTE hours/ Year |  |  | 1935 | [6 empty] | A-D ORR | A-D ORR | A MSSR - D FRR | E | A-E | A-E
|  | PERIOD |  | 1 | 2 | 3 | 4 | 5 | 6 |  |  | R&D for precise orbit determination | R&D for precise attitude determination | VESPUP mission design support | VESPUP operations support | Space debris collision avoidance | Project Management | TOT
|  | START |  | 2020-02-01 | 2021-02-01 | 2022-02-01 | 2023-02-01 | 2024-02-01 | 2025-02-01 |  |  | 650100 | 650200 | 650310 | 650320 | 650400 | 110800
|  | END |  | 2021-01-01 | 2022-01-01 | 2023-01-01 | 2024-01-01 | 2025-01-01 | 2025-12-01 |  | Hours | 1200 | 1200 | 800 | 1600 | 1200 | 200 | 6200
|  | MS |  | KO |  | RM |  | CRR | MCR |  | Labour Cost | 112320 | 112320 | 74880 | 149760 | 112320 | 28080 | 589680
|  | EXP |  | 85 | 85 | 85 | 85 | 145 | 149.2 |  | FTE | 3.1 | 3.1 | 3.1 | 3.1 | 3.1 | 0.1 | 3.2
|  | CUM |  | 85 | 170 | 255 | 340 | 485 | 634.2 |  | Internal facilities cost |  |  | 40216.67 | 80433.33 |  |  | 120650 | Telescope time (ZIMLAT, ZimMAIN, ZimTWIN); 50 nights
|  | PMT |  | 110 |  | 200 |  | 200 | 124.2 |  | TOT Direct Cost | 112320 | 112320 | 115096.67 | 230193.33 | 112320 | 28080 | 710330
|  | CUM |  | 110 | 110 | 310 | 310 | 510 | 634.2 |  | TOT EUR | 100285.71 | 100285.71 | 102764.88 | 205529.76 | 100285.71 | 25071.43 | 634223.2
|  | BAL |  | 25 | -60 | 55 | -30 | 25 | 0 |  |  | 112320 | 112320 | 115096.67 | 230193.33 | 112320 | 28080
|  | HOURS |  | 873.3333 | 873.3333 | 873.3333 | 873.3333 | 873.3333 | 1833.3333
|  | FTE given |  | 3.2 | 3.2 | 3.2 | 3.2 | 3.2 | 3.2
|  | FTE calc |  | 0.45134 | 0.45134 | 0.45134 | 0.45134 | 0.45134 | 0.94746
|  |  |  | 95.2 | 95.2 | 95.2 | 95.2 | 162.4 | 167.104

## Price Table 8 APCO (hidden)
New Table 8 breakdown
Industrial Price
| Economic Conditions | 2019
| Currency | k€ | [6 empty] | 3 | 6 | 9 | 12 | 15 | 18 | 21 | 24 | 27 | 30 | 33 | 36 | 39 | 42 | 45 | 48 | 51 | 54 | 57 | 60 | 63 | 66 | 69 | 72
[8 empty] | Year | 3: 2020; 15: 2021; 27: 2022; 39: 2023; 51: 2024; 63: 2025 | TOTAL
[8 empty] | Phase | 3: Phase A; 12: Phase B
T8 CODE | Price Breakdown |  |  | CAT | TYPE | CONC | WP# | Q | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
| Space Segment | [6 empty] | Milestone | 3: KO; 12: MSRR
| Spacecraft | [7 empty] | 3: 2020-02-01; 6: 2020-04-01; 9: 2020-06-30; 12: 2021-01-31
Project Office:
A1 | Management |  |  | MGT | Manpower | MGTManpower | 110000 |  | 0 | 0 | 21.4402 | 17.6373 | 21.4402 | 17.6373 | 21.4402 | 17.6373 | 21.4402 | 17.6373 | 21.4402 | 17.6373 | 21.4402 | 17.6373 | 21.4402 | 17.6373 | 21.4402 | 17.6373 | 21.4402 | 21.4402 | 0 | 0 | 0 | 0 | 355.5003
A2 | Product Assurance |  |  | MGT | Manpower | MGTManpower | 130000 |  | 0 | 0 | 5.186 | 5.186 | 5.186 | 5.186 | 5.186 | 5.186 | 5.186 | 5.186 | 5.186 | 5.186 | 5.186 | 5.186 | 5.186 | 5.186 | 5.186 | 5.186 | 5.186 | 5.186 | 0 | 0 | 0 | 0 | 93.3479
A3 | (Project & Mission) Engineering |  |  | MISSION | Manpower | MISSIONManpower | 120000 140000 200000 310000 |  | 0 | 0 | 56.6951 | 56.6951 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 113.3902
Total Cost (k€)
A4 | Flight Systems Engineering |  |  | MISSION | Manpower | MISSIONManpower | 401000 | - 401422, 401423, 401520, 401533 to 401536 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
A5 | (System level) Assembly, Integration and Testing,Verification |  |  | MISSION | Manpower | MISSIONManpower | 501000 520000 530000 550000 | includes OHB-Sweden | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 257.9861 | 257.9861 | 0 | 0 | 45.0283 | 45.0283 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 606.0287
A6 | Ground Segment Equipment |  |  | MISSION | Procurement | MISSIONProcurement | 510000 | includes OHB-Sweden (PGSE?), APCO | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Cost (k€)
Platform Module Hardware/Software (HW/SW)
OB Flight Software
B11 | FSW - Manpower (M/y) tech |  |  | TECH | Manpower | TECHManpower | 410000 | [25 empty] | 0
B12 | FSW - Manpower (M/y) mission |  |  | MISSION | Manpower | MISSIONManpower | ADS WP to see | [25 empty] | 0
Total Cost (k€)
Data Handling
B21 | Data Handling - Engineering |  |  | MISSION | Manpower | MISSIONManpower | 430000 | includes ADS | [24 empty] | 0
B22 | Data Handling - HW procurements |  |  | MISSION | Procurement | MISSIONProcurement | 430000 | includes ADS | [24 empty] | 0
Total Cost (k€)
Electrical Power
B31 | Electrical Power - Engineering and SW |  |  | MISSION | Manpower | MISSIONManpower | 420000 | includes ADS | [24 empty] | 0
B32 | Electrical Power - HW procurements |  |  | MISSION | Procurement | MISSIONProcurement | 420000 | includes ADS | [24 empty] | 0
Total Cost (k€)
Communications
B41 | Communications - Engineering and SW |  |  | MISSION | Manpower | MISSIONManpower | 440000 | ADS CS | [24 empty] | 0
B42 | Communications - HW procurements |  |  | MISSION | Procurement | MISSIONProcurement | [26 empty] | 0
Total Cost (k€)
AOCS / GNC
B51 | AOCS / GNC - Engineering and SW |  |  | MISSION | Manpower | MISSIONManpower | 450000 | - OHB 450500, 450600, 450800, 45900 | [24 empty] | 0
B52 | AOCS / GNC - HW procurements |  |  | MISSION | Procurement | MISSIONProcurement | [26 empty] | 0
Total Cost (k€)
Propulsion
B61 | Propulsion - Engineering |  |  | MISSION | Manpower | MISSIONManpower | 470000 | OHB | [24 empty] | 0
B62 | Propulsion - HW procurements |  |  | MISSION | Procurement | MISSIONProcurement | 470000 | OHB | [24 empty] | 0
Total Cost (k€)
Structure
B71 | Structure - Engineering |  |  | TECH | Manpower | TECHManpower | 490100 to 49500 | - 490540 | 0 | 0 | 223.6838 | 223.6838 | 107.9158 | 107.9158 | 417.3707 | 334.7793 | 25.3243 | 111.4953 | 111.4953 | 25.3243 | 25.3243 | 25.3243 | 25.3243 | 25.3243 | 25.3243 | 25.3243 | 0 | 0 | 0 | 0 | 0 | 0 | 1840.9345
B72 | Structure - HW |  |  | TECH | Procurement | TECHProcurement | 490100 to 49500 | - 490540 | 0 | 0 | 0 | 0 | 0 | 332.6197 | 332.6197 | 332.6197 | 0 | 0 | 47.5352 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1045.3944
Total Cost (k€)
Thermal Control
B81 | Thermal Control - Engineering |  |  | TECH | Manpower | TECHManpower | 490600 | [25 empty] | 0
B82 | Thermal Control - HW |  |  | TECH | Procurement | TECHProcurement | 490600 | [25 empty] | 0
Total Cost (k€)
Mechanisms
B91 | Mechanisms - HW procurements |  |  | MISSION | Procurement | MISSIONProcurement | 490540 | [25 empty] | 0
Total Cost (k€)
Service Module HW/SW
Rendezvous GNC, Sensors and Processing (RVSP)
C11 | RVSP - Engineering and SW |  |  | TECH | Manpower | TECHManpower | 460100 to 460900 461000 41100to412000 461000 SYD +OHB 450500 450600 450800 450900 | [25 empty] | 0
C12 | RVSP - HW procurements |  |  | TECH | Procurement | TECHProcurement | 460100 to 460900 461000 SYD | + 401422, 401423, 401520, 401533 to 401536 | [24 empty] | 0
Total Cost (k€)
Capture System (CS)
C21 | CS - Engineering and SW |  |  | TECH | Manpower | TECHManpower | 480000 | CS EPFL | [24 empty] | 0
C22 | CS - HW procurements |  |  | TECH | Procurement | TECHProcurement | 480000 | [25 empty] | 0
Total Cost (k€)
C3 | Service Module Validation |  |  | TECH | Procurement | TECHProcurement | 540000 | [25 empty] | 0
| Risk Contingency (e.g. Technical, Management Reserve) | [31 empty] | 0
D | Launcher |  |  | MISSION | Procurement | MISSIONProcurement | 320000
Ground Segment & Operations
E1 | Ground Control Centre Development |  |  | MISSION | Manpower | MISSIONManpower | 610000 62000-620100 INCL. OHB 630000 | [25 empty] | 0
E2 | Mission Operations |  |  | MISSION | Manpower | MISSIONManpower | 710000 720000 730000 740000 750000 640000 | [25 empty] | 0
E3 | Ground observations & tools |  |  | TECH | Manpower | TECHManpower | 650000 | [25 empty] | 0
E4 | Ground Stations |  |  | MISSION | Procurement | MISSIONProcurement | 620100 | [25 empty] | 0
E5 | Ground Segment - Procurement |  |  | MISSION | Procurement | MISSIONProcurement | included in Flight SE and Ground Control Center Development | [25 empty] | 0
F | Contingency | [7 empty] | 0 | 0 | 61.401 | 60.6405 | 26.9084 | 92.6718 | 155.3233 | 138.0445 | 10.3901 | 78.4609 | 88.7285 | 9.6295 | 10.3901 | 18.6352 | 19.3958 | 9.6295 | 10.3901 | 9.6295 | 5.3252 | 5.3252 | 0 | 0 | 0 | 0 | 810.9192 |  | 810.9489
| TOT EX Contingency | [7 empty] | 0 | 0 | 307.0051 | 303.2023 | 134.5419 | 463.3588 | 776.6166 | 690.2223 | 51.9505 | 392.3047 | 443.6427 | 48.1477 | 51.9505 | 93.176 | 96.9788 | 48.1477 | 51.9505 | 48.1477 | 26.6262 | 26.6262 | 0 | 0 | 0 | 0 | 4054.596 | 0
| TOT with contingency | [7 empty] | 0 | 0 | 368.4061 | 363.8427 | 161.4503 | 556.0306 | 931.9399 | 828.2668 | 62.3406 | 470.7656 | 532.3712 | 57.7772 | 62.3406 | 111.8112 | 116.3745 | 57.7772 | 62.3406 | 57.7772 | 31.9514 | 31.9514 | 0 | 0 | 0 | 0 | 4865.5151
|  |  |  | MGT | Manpower | MGTManpower |  |  | 0 | 0 | 26.6262 | 22.8233 | 26.6262 | 22.8233 | 26.6262 | 22.8233 | 26.6262 | 22.8233 | 26.6262 | 22.8233 | 26.6262 | 22.8233 | 26.6262 | 22.8233 | 26.6262 | 22.8233 | 26.6262 | 26.6262 | 0 | 0 | 0 | 0 | 448.8483 |  | 448.9048
|  |  |  | MISSION | Manpower | MISSIONManpower |  |  | 0 | 0 | 56.6951 | 56.6951 | 0 | 0 | 0 | 0 | 0 | 257.9861 | 257.9861 | 0 | 0 | 45.0283 | 45.0283 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 719.4189 |  | 719.4923
|  |  |  | TECH | Manpower | TECHManpower |  |  | 0 | 0 | 223.6838 | 223.6838 | 107.9158 | 107.9158 | 417.3707 | 334.7793 | 25.3243 | 111.4953 | 111.4953 | 25.3243 | 25.3243 | 25.3243 | 25.3243 | 25.3243 | 25.3243 | 25.3243 | 0 | 0 | 0 | 0 | 0 | 0 | 1840.9345 |  | 1918.3895
|  |  |  | MISSION | Procurement | MISSIONProcurement |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  |  |  | TECH | Procurement | TECHProcurement |  |  | 0 | 0 | 0 | 0 | 0 | 332.6197 | 332.6197 | 332.6197 | 0 | 0 | 47.5352 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1045.3944 |  | 967.9577
[9 empty] | 0 | 0 | 307.0051 | 303.2023 | 134.5419 | 463.3588 | 776.6166 | 690.2223 | 51.9505 | 392.3047 | 443.6427 | 48.1477 | 51.9505 | 93.176 | 96.9788 | 48.1477 | 51.9505 | 48.1477 | 26.6262 | 26.6262 | 0 | 0 | 0 | 0 | 4054.596 |  | 4054.7444
Note on H10: Brigitte Allegra: Work Package number

## APCO NEW (hidden)
VESPUP APCO Work Packages
2019-08-23
[5 empty] | Project Management (Aver.) = |  |  |  |  | Engineers (Aver.) =
Gross Hourly Rate in Euro in 2019 E.C.
Travel and profit should be folded in "cost for hours"
Include escalation in "cost for hours"
|  | Contingencies can be folded in or not, please specify |  |  | Phase 1
[5 empty] | 2020 |  |  |  | 2021 |  |  |  | 2022 |  |  |  | 2023 |  |  |  | 2024 |  |  |  | 2025
[5 empty] | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
|  | Total (kEuro) = | 4033.1558
| Modified by MR 04.09.2019 |  | mech STM moved to 2020Q3
PFM moved to 2023Q1
Work Package no
& Description
T8 Code | T8 Desc | WP 110000 |  |  | 2020 Q1: Project extended - 2 quarter not quoted
|  | 110000 | Project Managment | hours |  |  | 135.7222 | 135.7222 | 135.7222 | 135.7222 | 135.7222 | 135.7222 | 135.7222 | 135.7222 | 135.7222 | 135.7222 | 135.7222 | 135.7222 | 135.7222 | 135.7222 | 135.7222 | 135.7222 | 135.7222 | 135.7222
A1 | Management | 110000 | Project Managment | cost for hours (kEUR) |  |  | 17.6373 | 17.6373 | 17.6373 | 17.6373 | 17.6373 | 17.6373 | 17.6373 | 17.6373 | 17.6373 | 17.6373 | 17.6373 | 17.6373 | 17.6373 | 17.6373 | 17.6373 | 17.6373 | 17.6373 | 17.6373
A1 | Management | 110000 | Project Managment | external costs/procurement (kEUR) | 2020 Q3: 3.8028; 2021 Q1: 3.8028; 2021 Q3: 3.8028; 2022 Q1: 3.8028; 2022 Q3: 3.8028; 2023 Q1: 3.8028; 2023 Q3: 3.8028; 2024 Q1: 3.8028; 2024 Q3: 3.8028; 2024 Q4: 3.8028
|  |  |  | sum (kEUR) |  |  | 21.4402 | 17.6373 | 21.4402 | 17.6373 | 21.4402 | 17.6373 | 21.4402 | 17.6373 | 21.4402 | 17.6373 | 21.4402 | 17.6373 | 21.4402 | 17.6373 | 21.4402 | 17.6373 | 21.4402 | 21.4402
|  | WP 130000 |  |  | 2020 Q1: Project extended - 1 quarter not quoted; 2023 Q2: ?
|  | 130000 | PA/QA | hours |  |  | 53.1667 | 53.1667 | 53.1667 | 53.1667 | 53.1667 | 53.1667 | 53.1667 | 53.1667 | 53.1667 | 53.1667 | 53.1667 | 53.1667 | 53.1667 | 53.1667 | 53.1667 | 53.1667 | 53.1667 | 53.1667
A2 | Product Assurance | 130000 | PA/QA | cost for hours (kEUR) |  |  | 5.186 | 5.186 | 5.186 | 5.186 | 5.186 | 5.186 | 5.186 | 5.186 | 5.186 | 5.186 | 5.186 | 5.186 | 5.186 | 5.186 | 5.186 | 5.186 | 5.186 | 5.186
|  | 130000 | PA/QA | external costs/procurement (kEUR)
|  |  |  | sum (kEUR) |  |  | 5.186 | 5.186 | 5.186 | 5.186 | 5.186 | 5.186 | 5.186 | 5.186 | 5.186 | 5.186 | 5.186 | 5.186 | 5.186 | 5.186 | 5.186 | 5.186 | 5.186 | 5.186
WP 310000 | bar: 2020 Q3 to 2020 Q4
|  | 310000 | Launch specifications | hours | 2020 Q3: 477.5; 2020 Q4: 477.5
A3 | (Project & Mission) Engineering | 310000 | Launch specifications | cost for hours (kEUR) | 2020 Q3: 56.6951; 2020 Q4: 56.6951
|  | 310000 | Launch specifications | external costs/procurement (kEUR)
|  |  |  | sum (kEUR) | 2020 Q3: 56.6951; 2020 Q4: 56.6951
WP 490000
Platform mechanical systems
?
|  | 490100 | System engineering support | hours |  |  | 194.875 | 194.875 | 194.875 | 194.875 | 194.875 | 194.875 | 194.875 | 194.875 | 194.875 | 194.875 | 194.875 | 194.875 | 194.875 | 194.875 | 194.875 | 194.875
B71 | Structure - Engineering | 490100 | System engineering support | cost for hours (kEUR) |  |  | 25.3243 | 25.3243 | 25.3243 | 25.3243 | 25.3243 | 25.3243 | 25.3243 | 25.3243 | 25.3243 | 25.3243 | 25.3243 | 25.3243 | 25.3243 | 25.3243 | 25.3243 | 25.3243
B72 | Structure - HW | 490100 | System engineering support | external costs/procurement (kEUR)
|  |  |  | sum (kEUR) |  |  | 25.3243 | 25.3243 | 25.3243 | 25.3243 | 25.3243 | 25.3243 | 25.3243 | 25.3243 | 25.3243 | 25.3243 | 25.3243 | 25.3243 | 25.3243 | 25.3243 | 25.3243 | 25.3243
|  | 490200 | Structure Subsystem preliminary design | hours | 2020 Q3: 1700; 2020 Q4: 1700
B71 | Structure - Engineering | 490200 | Structure Subsystem preliminary design | cost for hours (kEUR) | 2020 Q3: 198.3595; 2020 Q4: 198.3595
B72 | Structure - HW | 490200 | Structure Subsystem preliminary design | external costs/procurement (kEUR)
|  |  |  | sum (kEUR) | 2020 Q3: 198.3595; 2020 Q4: 198.3595
?
|  | 490300 | Structure Subsystem detailed design and (structural + thermal) analysis | hours | 2021 Q1: 711; 2021 Q2: 711; 2021 Q3: 711
B71 | Structure - Engineering | 490300 | Structure Subsystem detailed design and (structural + thermal) analysis | cost for hours (kEUR) | 2021 Q1: 82.5914; 2021 Q2: 82.5914; 2021 Q3: 82.5914
B72 | Structure - HW | 490300 | Structure Subsystem detailed design and (structural + thermal) analysis | external costs/procurement (kEUR)
|  |  |  | sum (kEUR) | 2021 Q1: 82.5914; 2021 Q2: 82.5914; 2021 Q3: 82.5914
STM Tests @OHB
|  | 490400 | Structure Subsystem STM MAIT | hours | 2021 Q3: 2797; 2021 Q4: 2797
B71 | Structure - Engineering | 490400 | Structure Subsystem STM MAIT | cost for hours (kEUR) | 2021 Q3: 309.4549; 2021 Q4: 309.4549
B72 | Structure - HW | 490400 | Structure Subsystem STM MAIT | external costs/procurement (kEUR) | 2021 Q2: 332.6197; 2021 Q3: 332.6197; 2021 Q4: 332.6197
|  |  |  | sum (kEUR) | 2021 Q2: 332.6197; 2021 Q3: 642.0747; 2021 Q4: 642.0747
Provision for refurbishment only, as previously agreed
|  | 490500 | Structure Subsystem PFM MAIT | hours | 2022 Q2: 779.5; 2022 Q3: 779.5
B71 | Structure - Engineering | 490500 | Structure Subsystem PFM MAIT | cost for hours (kEUR) | 2022 Q2: 86.1709; 2022 Q3: 86.1709
B72 | Structure - HW | 490500 | Structure Subsystem PFM MAIT | external costs/procurement (kEUR) | 2022 Q3: 47.5352
|  |  |  | sum (kEUR) | 2021 Q4: 0; 2022 Q1: 0; 2022 Q2: 86.1709; 2022 Q3: 133.7061
|  | WP 510000 |  |  | 2022 Q2: Engineering only, MAIT in New Member states
|  | 510000 | Ground support equipment | hours | 2022 Q2: 2352; 2022 Q3: 2352
A5 | (System level) Assembly, Integration and Testing,Verification | 510000 | Ground support equipment | cost for hours (kEUR) | 2022 Q2: 257.9861; 2022 Q3: 257.9861
|  | 510000 | Ground support equipment | external costs/procurement (kEUR)
|  |  |  | sum (kEUR) | 2022 Q2: 257.9861; 2022 Q3: 257.9861; 2022 Q4: 0; 2023 Q1: 0
|  | WP 540000 | moved back of 1 Q |  | 2022 Q3: ?; 2022 Q4: AIV support only
|  | 540000 | QM/FM integration | hours | 2023 Q2: 346.5; 2023 Q3: 346.5
A5 | (System level) Assembly, Integration and Testing,Verification | 540000 | QM/FM integration | cost for hours (kEUR) | 2023 Q2: 45.0283; 2023 Q3: 45.0283
|  | 540000 | QM/FM integration | external costs/procurement (kEUR)
|  |  |  | sum (kEUR) | 2023 Q2: 45.0283; 2023 Q3: 45.0283
Expected Payment Milestones (from ClearSpace to APCO-Tech)
|  |  |  | Milestone: | 2021 Q1: Example:; 2021 Q2: STM delivery
|  |  |  | Payment in k€: | 2021 Q1: Example:; 2021 Q2: 1100

## APCO OLD (hidden)
|  |  |  | Exchange rate CHF/EUR |  | 1.136
TOT CHF @ SOR Submission
[5 empty] | Months | 10 | 12 | 12 | 19 | 53 |  |  | 2020 |  |  |  | 2021 |  |  |  | 2022 |  |  |  | 2023 |  |  |  | 2024 |  |  |  | 2025
[6 empty] | PHASE A | PHASE B | PHASE C | PHASE D |  |  |  | PHASE A |  |  | PHASE B | [5 empty] | PHASE C |  |  |  | PHASE D | [7 empty] | PHASE E/F
T8 Code | T8 Descr | T8 type | WP# |  |  | 06/2020-04/2021 | 04/2021-05/2022 | 05/2022-05/2023 | 05/2023-11/2024 | CHF |  |  | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
A1 | Management | Manpower | 110000 | PM | manpower | 27740.5974 | 130900.9389 | 121163.6793 | 54169.4645 | 333974.68 |  |  | 8.1398 | 8.1398 | 8.1398 | 19.2049 | 19.2049 | 19.2049 | 19.2049 | 19.2049 | 19.2049 | 26.6645 | 26.6645 | 26.6645 | 26.6645 | 7.9474 | 7.9474 | 7.9474 | 7.9474 | 7.9474 | 7.9474
A2 | Product Assurance | Manpower | 130000 | PA / QA | manpower | 8157.2402 | 38491.9758 | 35628.6934 | 15928.7606 | 98206.67 |  |  | 2.3936 | 2.3936 | 2.3936 | 5.6473 | 5.6473 | 5.6473 | 5.6473 | 5.6473 | 5.6473 | 7.8408 | 7.8408 | 7.8408 | 7.8408 | 2.337 | 2.337 | 2.337 | 2.337 | 2.337 | 2.337
A3 | (Project & Mission) Engineering | Manpower | 310000 | Launch Spec. | manpower | 9907.8254 | 46752.5493 | 43274.7919 | 19347.1535 | 119282.32 |  |  | 2.9072 | 2.9072 | 2.9072 | 6.8592 | 6.8592 | 6.8592 | 6.8592 | 6.8592 | 6.8592 | 9.5235 | 9.5235 | 9.5235 | 9.5235 | 2.8385 | 2.8385 | 2.8385 | 2.8385 | 2.8385 | 2.8385
B71 | Structure - Engineering | Manpower | 490000 | P/F Mech. | manpower | 160842.0225 | 758973.2641 | 702515.9172 | 314078.5361 | 1936409.74 |  |  | 47.1954 | 47.1954 | 47.1954 | 111.3517 | 111.3517 | 111.3517 | 111.3517 | 111.3517 | 111.3517 | 154.603 | 154.603 | 154.603 | 154.603 | 46.0796 | 46.0796 | 46.0796 | 46.0796 | 46.0796 | 46.0796
A5 | (System level) Assembly, Integration and Testing,Verification | Manpower | 510000 | GSE Dec. | manpower | 45082.557 | 212733.3076 | 196908.8264 | 88033.359 | 542758.05 |  |  | 13.2284 | 13.2284 | 13.2284 | 31.2109 | 31.2109 | 31.2109 | 31.2109 | 31.2109 | 31.2109 | 43.3338 | 43.3338 | 43.3338 | 43.3338 | 12.9157 | 12.9157 | 12.9157 | 12.9157 | 12.9157 | 12.9157
A5 | (System level) Assembly, Integration and Testing,Verification | Manpower | 550300 | AIV Suppor | manpower | 7870.8683 | 37140.6582 | 34377.8955 | 15369.558 | 94758.98 |  |  | 2.3095 | 2.3095 | 2.3095 | 5.449 | 5.449 | 5.449 | 5.449 | 5.449 | 5.449 | 7.5656 | 7.5656 | 7.5656 | 7.5656 | 2.2549 | 2.2549 | 2.2549 | 2.2549 | 2.2549 | 2.2549
A1 | Management | Manpower | 110000 | PM | travel | 10000 | 10000 | 10000 | 10000 | 40000 |  |  | 2.9343 | 2.9343 | 2.9343 | 1.4671 | 1.4671 | 1.4671 | 1.4671 | 1.4671 | 1.4671 | 2.2007 | 2.2007 | 2.2007 | 2.2007 | 1.4671 | 1.4671 | 1.4671 | 1.4671 | 1.4671 | 1.4671
B72 | Structure - HW | Procurement | 490000 | P/F Mech. | Procurement |  |  | 467500 | 632100 | 1099600 |  |  | PHASE A Q1: 0; PHASE A Q2: 0; PHASE A Q3: 0; PHASE B Q4: 0; PHASE B Q1: 0; PHASE B Q2: 0; PHASE B Q3: 0; PHASE B Q4: 0; PHASE B Q1: 0; PHASE C Q2: 411.5317; PHASE D Q2: 556.4261
A1 | Management | Manpower | 110000 | PM | profit | 1891.1926 | 8663.2024 | 11303.4043 | 8060.1707 | 29917.97 |  |  | 0.55493 | 0.55493 | 0.55493 | 1.271 | 1.271 | 1.271 | 1.271 | 1.271 | 1.271 | 2.4875 | 2.4875 | 2.4875 | 2.4875 | 1.1825 | 1.1825 | 1.1825 | 1.1825 | 1.1825 | 1.1825
A2 | Product Assurance | Manpower | 130000 | PA / QA | profit | 496.6317 | 2274.9775 | 2968.3008 | 2116.62 | 7856.53 |  |  | 0.14573 | 0.14573 | 0.14573 | 0.33377 | 0.33377 | 0.33377 | 0.33377 | 0.33377 | 0.33377 | 0.65324 | 0.65324 | 0.65324 | 0.65324 | 0.31054 | 0.31054 | 0.31054 | 0.31054 | 0.31054 | 0.31054
A3 | (Project & Mission) Engineering | Manpower | 310000 | Launch Spec. | profit | 603.2119 | 2763.2018 | 3605.3166 | 2570.8597 | 9542.59 |  |  | 0.177 | 0.177 | 0.177 | 0.4054 | 0.4054 | 0.4054 | 0.4054 | 0.4054 | 0.4054 | 0.79342 | 0.79342 | 0.79342 | 0.79342 | 0.37718 | 0.37718 | 0.37718 | 0.37718 | 0.37718 | 0.37718
B71 | Structure - Engineering | Manpower | 490000 | P/F Mech. | profit | 15353.1248 | 70329.8172 | 91763.5671 | 65434.2709 | 242880.78 |  |  | 4.505 | 4.505 | 4.505 | 10.3183 | 10.3183 | 10.3183 | 10.3183 | 10.3183 | 10.3183 | 20.1944 | 20.1944 | 20.1944 | 20.1944 | 9.6001 | 9.6001 | 9.6001 | 9.6001 | 9.6001 | 9.6001
A5 | (System level) Assembly, Integration and Testing,Verification | Manpower | 510000 | GSE Dec. | profit | 2744.7314 | 12573.1055 | 16404.8914 | 11697.9117 | 43420.64 |  |  | 0.80538 | 0.80538 | 0.80538 | 1.8446 | 1.8446 | 1.8446 | 1.8446 | 1.8446 | 1.8446 | 3.6102 | 3.6102 | 3.6102 | 3.6102 | 1.7162 | 1.7162 | 1.7162 | 1.7162 | 1.7162 | 1.7162
A5 | (System level) Assembly, Integration and Testing,Verification | Manpower | 550300 | AIV Suppor | profit | 479.197 | 2195.1126 | 2864.0962 | 2042.3143 | 7580.72 |  |  | 0.14061 | 0.14061 | 0.14061 | 0.32205 | 0.32205 | 0.32205 | 0.32205 | 0.32205 | 0.32205 | 0.6303 | 0.6303 | 0.6303 | 0.6303 | 0.29964 | 0.29964 | 0.29964 | 0.29964 | 0.29964 | 0.29964
|  |  | TOT |  |  | 291169.2002 | 1333792.111 | 1740279.3798 | 1240948.9789 | 4606189.67 |  |  | 85.437 | 85.437 | 85.437 | 195.6855 | 195.6855 | 195.6855 | 195.6855 | 195.6855 | 195.6855 | 382.984 | 382.984 | 382.984 | 382.984 | 182.0641 | 182.0641 | 182.0641 | 182.0641 | 182.0641 | 182.0641
From PSS |  |  | Exchange rate | CHF/EUR | 1.136
|  |  | FTE Hours/Year |  | 1800
[5 empty] | TOT | PHASE A | PHASE B | PHASE C | PHASE D | TOT WBS | TOTCOST CHF | TOT COST EUR | PHASE A Q1: CHF/EUR; PHASE A Q2: 1.136; PHASE A Q3: TOT; PHASE B Q4: PM; PHASE B Q1: PA / QA; PHASE B Q2: Launch Spec.; PHASE B Q3: P/F Mech.; PHASE B Q4: GSE Dec.; PHASE B Q1: AIV Suppor; PHASE C Q2: TOT WBS; PHASE C Q3: TOTCOST CHF; PHASE C Q4: TOT COST EUR
[5 empty] | Gross H rate | 06/2020-04/2021 | 04/2021-05/2022 | 05/2022-05/2023 | 05/2023-11/2024 |  |  |  | PHASE A Q3: Gross H rate; PHASE B Q4: 110000; PHASE B Q1: 130000; PHASE B Q2: 310000; PHASE B Q3: 490000; PHASE B Q4: 510000; PHASE B Q1: 540000
|  |  | PROJECT MANAGER |  | 136.69 | 200 | 732 | 818 | 693 | 2443 |  |  | PHASE A Q1: PROJECT MANAGER; PHASE A Q3: 136.69; PHASE B Q4: 1914; PHASE B Q4: 530; PHASE C Q2: 2444
|  |  | SYSTEM ENGINEER |  | 136.69 | 1203 | 3938 | 2963 | 2079 | 10183 |  |  | PHASE A Q1: SYSTEM ENGINEER; PHASE A Q3: 136.69; PHASE B Q4: 529; PHASE B Q2: 446; PHASE B Q3: 8514; PHASE B Q1: 693; PHASE C Q2: 10182
|  |  | PRODUCT ASSURANCE ENGINEER |  | 102.6 | 101 | 337 | 810 | 346 | 1594 |  |  | PHASE A Q1: PRODUCT ASSURANCE ENGINEER; PHASE A Q3: 102.6; PHASE B Q1: 957; PHASE B Q4: 636; PHASE C Q2: 1593
|  |  | MECHANICAL ANALYSIS ENGINEER |  | 114.55 | 101 | 1631 | 856 | 173 | 2761 |  |  | PHASE A Q1: MECHANICAL ANALYSIS ENGINEER; PHASE A Q3: 114.55; PHASE B Q2: 509; PHASE B Q3: 1449; PHASE B Q4: 803; PHASE C Q2: 2761
|  |  | THERMAL ANALYSIS ENGINEER |  | 114.55 | 401 | 684 | 593 | 174 | 1852 |  |  | PHASE A Q1: THERMAL ANALYSIS ENGINEER; PHASE A Q3: 114.55; PHASE B Q3: 1851; PHASE C Q2: 1851
|  |  | MECHANICAL ENGINEER |  | 115.7 |  | 584 | 890 |  | 1474 |  |  | PHASE A Q1: MECHANICAL ENGINEER; PHASE A Q3: 115.7; PHASE B Q4: 1484; PHASE C Q2: 1484
|  |  | ELECTRICAL ENGINEER |  | 115.7 |  |  |  |  | 0 |  |  | PHASE A Q1: ELECTRICAL ENGINEER; PHASE A Q3: 115.7; PHASE C Q2: 0
|  |  | DRAUGHTSMAN |  | 115.7 |  | 747 | 813 | 0 | 1560 |  |  | PHASE A Q1: DRAUGHTSMAN; PHASE A Q3: 115.7; PHASE B Q3: 1158; PHASE B Q4: 403; PHASE C Q2: 1561
|  |  | PURCHASING |  | 120.6 |  | 218 | 614 | 174 | 1006 |  |  | PHASE A Q1: PURCHASING; PHASE A Q3: 120.6; PHASE B Q3: 582; PHASE B Q4: 424; PHASE C Q2: 1006
|  |  | QUALITY ASSURANCE ENGINEER |  | 102.6 |  | 428 | 424 | 0 | 852 |  |  | PHASE A Q1: QUALITY ASSURANCE ENGINEER; PHASE A Q3: 102.6; PHASE B Q3: 428; PHASE B Q4: 424; PHASE C Q2: 852
|  |  | QUALITY CONTROL |  | 102.6 |  | 82 | 71 | 0 | 153 |  |  | PHASE A Q1: QUALITY CONTROL; PHASE A Q3: 102.6; PHASE B Q3: 153; PHASE C Q2: 153
|  |  | WORKSHOP OPERATOR |  | 92.25 |  | 575 | 498 | 346 | 1419 |  |  | PHASE A Q1: WORKSHOP OPERATOR; PHASE A Q3: 92.25; PHASE B Q3: 1418; PHASE C Q2: 1418
|  |  | TOT DIRECT LABOUR HOURS |  |  | 2006 | 9956 | 9350 | 3983 | 25295 |  |  | PHASE A Q1: TOT DIRECT LABOUR HOURS; PHASE B Q4: 2443; PHASE B Q1: 957; PHASE B Q2: 955; PHASE B Q3: 15553; PHASE B Q4: 4704; PHASE B Q1: 693; PHASE C Q2: 25305
|  |  | PROJECT MANAGER |  | 136.69 | 27338 | 146400 | 598776 | 566874
|  |  | SYSTEM ENGINEER |  | 136.69 | 164438.07 | 4737414 | 11668294 | 6160077
|  |  | PRODUCT ASSURANCE ENGINEER |  | 102.6 | 10362.6 | 34037 | 272970 | 280260
|  |  | MECHANICAL ANALYSIS ENGINEER |  | 114.55 | 11569.55 | 164731 | 1396136 | 148088
|  |  | THERMAL ANALYSIS ENGINEER |  | 114.55 | 45934.55 | 274284 | 405612 | 103182
|  |  | MECHANICAL ENGINEER |  | 115.7 | 0 | 0 | 519760 | 0
|  |  | ELECTRICAL ENGINEER |  | 115.7 | 0 | 0 | 0 | 0
|  |  | DRAUGHTSMAN |  | 115.7 | 0 | 0 | 607311 | 0
|  |  | PURCHASING |  | 120.6 | 0 | 0 | 133852 | 106836
|  |  | QUALITY ASSURANCE ENGINEER |  | 102.6 | 0 | 0 | 181472 | 0
|  |  | QUALITY CONTROL |  | 102.6 | 0 | 0 | 5822 | 0
|  |  | WORKSHOP OPERATOR |  | 92.25 | 0 | 0 | 286350 | 172308
|  |  | TOT DIRECT LABOUR COST |  |  | 259601.11 | 1224992.69 | 1133869.8 | 506926.83 |  | 3125390.43 | 2751223.9701 | PHASE A Q1: TOT DIRECT LABOUR COST; PHASE B Q4: 333974.68; PHASE B Q1: 98206.67; PHASE B Q2: 119282.32; PHASE B Q3: 1936409.74; PHASE B Q4: 542758.05; PHASE B Q1: 94758.98; PHASE C Q3: 3125390.43; PHASE C Q4: 2751223.9701
|  |  | FTE |  |  | 1.1144 | 5.5311 | 0.5 | 8.6 |  |  |  | PHASE A Q1: FTE; PHASE B Q4: 1.4; PHASE B Q1: 0.5; PHASE B Q2: 0.5; PHASE B Q3: 8.6; PHASE B Q4: 2.6; PHASE B Q1: 0.4
|  |  | OTHER DIRECT COST | [9 empty] | PHASE A Q1: OTHER DIRECT COST
|  |  | Material Cost |  |  |  |  | 137500 | 208500 |  | 346000 | 304577.4648 | PHASE A Q1: Material Cost; PHASE B Q3: 346000; PHASE C Q3: 346000; PHASE C Q4: 304577.4648
|  |  | External Major Products |  |  |  |  | 80000 | 150000 |  | 230000 | 202464.7887 | PHASE A Q1: External Major Products; PHASE B Q3: 230000; PHASE C Q3: 230000; PHASE C Q4: 202464.7887
|  |  | Transport and Insurances | [5 empty] | 10000 |  | 10000 | 8802.8169 | PHASE A Q1: Transport and Insurances; PHASE B Q3: 10000; PHASE C Q3: 10000; PHASE C Q4: 8802.8169
|  |  | Travel and Subsistence |  |  | 10000 | 10000 | 10000 | 10000 |  | 40000 | 35211.2676 | PHASE A Q1: Travel and Subsistence; PHASE B Q4: 40000; PHASE C Q3: 40000; PHASE C Q4: 35211.2676
|  |  | Miscellaneous |  |  |  |  | 250000 | 263600 |  | 513600 | 452112.6761 | PHASE A Q1: Miscellaneous; PHASE B Q3: 513600; PHASE C Q3: 513600; PHASE C Q4: 452112.6761
|  |  | Total Other Direct Cost |  |  | 10000 | 10000 | 477500 | 642100 |  | 1139600 | 1003169.0141 | PHASE A Q1: Total Other Direct Cost; PHASE B Q4: 40000; PHASE B Q1: 0; PHASE B Q2: 0; PHASE B Q3: 1099600; PHASE B Q4: 0; PHASE B Q1: 0; PHASE C Q3: 1139600; PHASE C Q4: 1003169.0141
|  |  | SUB-TOTAL DIRECT COST |  |  | 269601.11 | 1234992.69 | 1611369.8 | 1149026.83 |  | 4264990.43 | 3754392.9842 | PHASE A Q1: SUB-TOTAL DIRECT COST; PHASE B Q4: 373974.68; PHASE B Q1: 98206.67; PHASE B Q2: 119282.32; PHASE B Q3: 3036009.74; PHASE B Q4: 542758.05; PHASE B Q1: 94758.98; PHASE C Q3: 4264990.43; PHASE C Q4: 3754392.9842
|  |  | PROFIT | 4 264 990.4 8.0% |  | 21568.09 | 98799.42 | 128909.58 | 91922.15 |  | 341199.24 | 300351.4437 | PHASE A Q1: PROFIT; PHASE A Q2: 4 264 990.4 8.0%; PHASE B Q4: 29917.97; PHASE B Q1: 7856.53; PHASE B Q2: 9542.59; PHASE B Q3: 242880.78; PHASE B Q4: 43420.64; PHASE B Q1: 7580.72; PHASE C Q3: 341199.23; PHASE C Q4: 300351.4349
|  |  | TOTAL PRICE FOR ESA |  |  | 291169.2 | 1333792.11 | 1740279.38 | 1240948.98 |  | 4606189.67 | 4054744.4278 | PHASE A Q1: TOTAL PRICE FOR ESA; PHASE B Q4: 403892.65; PHASE B Q1: 106063.2; PHASE B Q2: 128824.91; PHASE B Q3: 3278890.52; PHASE B Q4: 586178.69; PHASE B Q1: 102339.7; PHASE C Q3: 4606189.66; PHASE C Q4: 4054744.419
|  |  | TOT EUR |  |  | 256310.9155 | 1174112.7729 | 1531936.0739 | 1092384.6655 |  | 4054744.4278
[6 empty] | 256.3109 | 1174.1128 | 1531.9361 | 1092.3847
PROC <EUR
FTE |  |  |  |  | Months | 10 | 12 | 12 | 19 | 53
[6 empty] | PHASE A | PHASE B | PHASE C | PHASE D
T8 Code | T8 Descr | T8 type | WP# |  |  | 06/2020-04/2021 | 04/2021-05/2022 | 05/2022-05/2023 | 05/2023-11/2024 | FTE
A1 | Management | Manpower | 110000 | PM | manpower | 0.11629 | 0.54873 | 0.50791 | 0.22707 | 1.4
A2 | Product Assurance | Manpower | 130000 | PA / QA | manpower | 0.059069 | 0.19336 | 0.14549 | 0.10208 | 0.5
A3 | (Project & Mission) Engineering | Manpower | 310000 | Launch Spec. | manpower | 0.031681 | 0.016547 | 0.039772 | 0.016989 | 0.5
B71 | Structure - Engineering | Manpower | 490000 | P/F Mech. | manpower | 0.3146 | 1.3775 | 0.72293 | 0.14611 | 8.6
A5 | (System level) Assembly, Integration and Testing,Verification | Manpower | 510000 | GSE Dec. | manpower | 0.56296 | 0.17464 | 0.15141 | 0.044427 | 2.6
A5 | (System level) Assembly, Integration and Testing,Verification | Manpower | 550300 | AIV Suppor | manpower | 0 | 0.02294 | 0.03496 | 0 | 0.4

## Price Table 8 EPFL (hidden)
New Table 8 breakdown
Industrial Price
| Economic Conditions | 2019
| Currency | k€
[8 empty] | Year | 2020 |  |  |  | 2021 |  |  |  | 2022 |  |  |  | 2023 |  |  |  | 2024 |  |  |  | 2025 |  |  |  | TOTAL
[8 empty] | Phase | Phase A |  |  | Phase B | [5 empty] | Phase C
T8 CODE | Price Breakdown |  |  | CAT | TYPE | CONC | WP# | Q | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
| Space Segment | [6 empty] | Milestone | KO |  |  | MSRR
| Spacecraft | [7 empty] | 2020-02-01 | 2020-04-01 | 2020-06-30 | 2021-01-31
Project Office:
A1 | Management |  |  | MGT | Manpower | MGTManpower | 110000 |  | 21.4195 | 21.4195 | 21.4195 | 21.4195 | 21.4195 | 21.4195 | 21.4195 | 21.4195 | [16 empty] | 171.3563
A2 | Product Assurance |  |  | MGT | Manpower | MGTManpower | 130000 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [16 empty] | 0
A3 | (Project & Mission) Engineering |  |  | MISSION | Manpower | MISSIONManpower | 120000 140000 200000 310000 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [16 empty] | 0
Total Cost (k€)
A4 | Flight Systems Engineering |  |  | MISSION | Manpower | MISSIONManpower | 401000 | - 401422, 401423, 401520, 401533 to 401536 | 40.1529 | 40.1529 | 40.1529 | 40.1529 | 40.1529 | 40.1529 | 40.1529 | 40.1529 | [16 empty] | 321.2229
A5 | (System level) Assembly, Integration and Testing,Verification |  |  | MISSION | Manpower | MISSIONManpower | 501000 520000 530000 550000 | includes OHB-Sweden | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [16 empty] | 0
A6 | Ground Segment Equipment |  |  | MISSION | Procurement | MISSIONProcurement | 510000 | includes OHB-Sweden (PGSE?), APCO | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [16 empty] | 0
Total Cost (k€)
Platform Module Hardware/Software (HW/SW)
OB Flight Software
B11 | FSW - Manpower (M/y) tech |  |  | TECH | Manpower | TECHManpower | 410000 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [16 empty] | 0
B12 | FSW - Manpower (M/y) mission |  |  | MISSION | Manpower | MISSIONManpower | ADS WP to see |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [16 empty] | 0
Total Cost (k€)
Data Handling
B21 | Data Handling - Engineering |  |  | MISSION | Manpower | MISSIONManpower | 430000 | includes ADS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [16 empty] | 0
B22 | Data Handling - HW procurements |  |  | MISSION | Procurement | MISSIONProcurement | 430000 | includes ADS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [16 empty] | 0
Total Cost (k€)
Electrical Power
B31 | Electrical Power - Engineering and SW |  |  | MISSION | Manpower | MISSIONManpower | 420000 | includes ADS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [16 empty] | 0
B32 | Electrical Power - HW procurements |  |  | MISSION | Procurement | MISSIONProcurement | 420000 | includes ADS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [16 empty] | 0
Total Cost (k€)
Communications
B41 | Communications - Engineering and SW |  |  | MISSION | Manpower | MISSIONManpower | 440000 | ADS CS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [16 empty] | 0
B42 | Communications - HW procurements |  |  | MISSION | Procurement | MISSIONProcurement |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [16 empty] | 0
Total Cost (k€)
AOCS / GNC
B51 | AOCS / GNC - Engineering and SW |  |  | MISSION | Manpower | MISSIONManpower | 450000 | - OHB 450500, 450600, 450800, 45900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [16 empty] | 0
B52 | AOCS / GNC - HW procurements |  |  | MISSION | Procurement | MISSIONProcurement |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [16 empty] | 0
Total Cost (k€)
Propulsion
B61 | Propulsion - Engineering |  |  | MISSION | Manpower | MISSIONManpower | 470000 | OHB | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [16 empty] | 0
B62 | Propulsion - HW procurements |  |  | MISSION | Procurement | MISSIONProcurement | 470000 | OHB | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [16 empty] | 0
Total Cost (k€)
Structure
B71 | Structure - Engineering |  |  | TECH | Manpower | TECHManpower | 490100 to 49500 | - 490540 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [16 empty] | 0
B72 | Structure - HW |  |  | TECH | Procurement | TECHProcurement | 490100 to 49500 | - 490540 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [16 empty] | 0
Total Cost (k€)
Thermal Control
B81 | Thermal Control - Engineering |  |  | TECH | Manpower | TECHManpower | 490600 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [16 empty] | 0
B82 | Thermal Control - HW |  |  | TECH | Procurement | TECHProcurement | 490600 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [16 empty] | 0
Total Cost (k€)
Mechanisms
B91 | Mechanisms - HW procurements |  |  | MISSION | Procurement | MISSIONProcurement | 490540 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [16 empty] | 0
Total Cost (k€)
Service Module HW/SW
Rendezvous GNC, Sensors and Processing (RVSP)
C11 | RVSP - Engineering and SW |  |  | TECH | Manpower | TECHManpower | 460100 to 460900 461000 41100to412000 461000 SYD +OHB 450500 450600 450800 450900 |  | 0 | 0 | 0 | 107.1065 | 72.3341 | 72.3341 | 72.3341 | 0 | [16 empty] | 324.1088
C12 | RVSP - HW procurements |  |  | TECH | Procurement | TECHProcurement | 460100 to 460900 461000 SYD | + 401422, 401423, 401520, 401533 to 401536 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [16 empty] | 0
Total Cost (k€)
Capture System (CS)
C21 | CS - Engineering and SW |  |  | TECH | Manpower | TECHManpower | 480000 | CS EPFL | 149.1084 | 149.1084 | 149.1084 | 149.1084 | 149.1084 | 149.1084 | 69.5449 | 69.5449 | [16 empty] | 1033.74
C22 | CS - HW procurements |  |  | TECH | Procurement | TECHProcurement | 480000 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [16 empty] | 0
Total Cost (k€)
C3 | Service Module Validation |  |  | TECH | Procurement | TECHProcurement | 540000 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [16 empty] | 0
Risk Contingency (e.g. Technical, Management Reserve)
D | Launcher |  |  | MISSION | Procurement | MISSIONProcurement | 320000
Ground Segment & Operations
E1 | Ground Control Centre Development |  |  | MISSION | Manpower | MISSIONManpower | 610000 62000-620100 INCL. OHB 630000 | [25 empty] | 0
E2 | Mission Operations |  |  | MISSION | Manpower | MISSIONManpower | 710000 720000 730000 740000 750000 640000 | [25 empty] | 0
E3 | Ground observations & tools |  |  | TECH | Manpower | TECHManpower | 650000 | [25 empty] | 0
E4 | Ground Stations |  |  | MISSION | Procurement | MISSIONProcurement | 620100 | [25 empty] | 0
E5 | Ground Segment - Procurement |  |  | MISSION | Procurement | MISSIONProcurement | included in Flight SE and Ground Control Center Development | [25 empty] | 0
F | Contingency | [7 empty] | 42.1362 | 42.1362 | 42.1362 | 63.5575 | 56.603 | 56.603 | 40.6903 | 26.2235 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 370.0856
| TOT EX Contingency | [7 empty] | 210.6808 | 210.6808 | 210.6808 | 317.7873 | 283.0149 | 283.0149 | 203.4513 | 131.1173 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1850.4281 | 0
| TOT with contingency | [7 empty] | 252.817 | 252.817 | 252.817 | 381.3448 | 339.6179 | 339.6179 | 244.1416 | 157.3407 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2220.5137
|  |  |  | MGT | Manpower | MGTManpower |  |  | 21.4195 | 21.4195 | 21.4195 | 21.4195 | 21.4195 | 21.4195 | 21.4195 | 21.4195 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 171.3563
|  |  |  | MISSION | Manpower | MISSIONManpower |  |  | 40.1529 | 40.1529 | 40.1529 | 40.1529 | 40.1529 | 40.1529 | 40.1529 | 40.1529 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 321.2229
|  |  |  | TECH | Manpower | TECHManpower |  |  | 149.1084 | 149.1084 | 149.1084 | 256.2149 | 221.4425 | 221.4425 | 141.8789 | 69.5449 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1357.8488
|  |  |  | MISSION | Procurement | MISSIONProcurement |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | TECH | Procurement | TECHProcurement |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[9 empty] | 210.6808 | 210.6808 | 210.6808 | 317.7873 | 283.0149 | 283.0149 | 203.4513 | 131.1173 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1850.4281
Note on H10: Brigitte Allegra: Work Package number

## EPFL (hidden)
[9 empty] | 2020 |  |  |  | 2021
T8 Code |  | Start period | End period | Duration | Total amount in KEUR | COST TYPE |  |  | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
A1 | Management | 1 | 8 | 8 | 171.3563 | LABOUR COST | WP110700 | Project Management and SE | 21.4195 | 21.4195 | 21.4195 | 21.4195 | 21.4195 | 21.4195 | 21.4195 | 21.4195 | 171356.3409
[6 empty] | LABOUR HOURS | WP110700 | Project Management and SE | 245.75 | 245.75 | 245.75 | 245.75 | 245.75 | 245.75 | 245.75 | 245.75
[6 empty] | FTE | WP110700 | Project Management and SE | 0.15359 | 0.15359 | 0.15359 | 0.15359 | 0.15359 | 0.15359 | 0.15359 | 0.15359
A4 | Flight Systems Engineering | 1 | 8 | 8 | 321.2229 |  | WP401700 | MBSE VESPUP Model | 40.1529 | 40.1529 | 40.1529 | 40.1529 | 40.1529 | 40.1529 | 40.1529 | 40.1529 | 321222.887
C11 | RVSP - Engineering and SW | 1 | 4 | 4 | 34.7724 |  | WP460201 | Synthetic images database | 2020 Q1: 0; 2020 Q2: 0; 2020 Q3: 0; 2020 Q4: 34.7724 | 139089.7043
C11 | RVSP - Engineering and SW | 1 | 8 | 8 | 146.7467 |  | WP460202 | 6DoF target pose estimation algorithms | 2020 Q4: 36.6867; 2021 Q1: 36.6867; 2021 Q2: 36.6867; 2021 Q3: 36.6867 | 293493.3217
C11 | RVSP - Engineering and SW | 1 | 8 | 8 | 142.5897 |  | WP460203 | FPGA based vision algorithms implementation | 2020 Q4: 35.6474; 2021 Q1: 35.6474; 2021 Q2: 35.6474; 2021 Q3: 35.6474 | 285179.4087
C21 | CS - Engineering and SW | 1 | 8 | 8 | 278.1794 |  | WP480311 | Fast adaptive control for the capture | 34.7724 | 34.7724 | 34.7724 | 34.7724 | 34.7724 | 34.7724 | 34.7724 | 34.7724 | 278179.4087
C21 | CS - Engineering and SW | 1 | 6 | 6 | 268.7467 |  | WP480411 | Capture dynamic contact simulator and analyses | 44.7911 | 44.7911 | 44.7911 | 44.7911 | 44.7911 | 44.7911 |  |  | 268746.6626
C21 | CS - Engineering and SW | 1 | 8 | 8 | 278.1794 |  | WP480212A | Miniaturized proximity sensor - system and signal processing | 34.7724 | 34.7724 | 34.7724 | 34.7724 | 34.7724 | 34.7724 | 34.7724 | 34.7724 | 278179.4087
C21 | CS - Engineering and SW | 1 | 6 | 6 | 208.6346 |  | WP480212B | Miniaturized proximity sensor - antenna | 34.7724 | 34.7724 | 34.7724 | 34.7724 | 34.7724 | 34.7724 |  |  | 208634.5565
0
0
0
|  |  |  | Total | 1850.4281 |  |  |  | 210.6808 | 210.6808 | 210.6808 | 317.7873 | 283.0149 | 283.0149 | 203.4513 | 131.1173 | 2244081.6991
393.6519
Taken off to be offset
[7 empty] | WP460201 | Synthetic images database | 2020 Q1: 34.7724; 2020 Q2: 34.7724; 2020 Q3: 34.7724 | paid by Innosuisse up tp Sept 2010
[7 empty] | WP460202 | 6DoF target pose estimation algorithms | 2020 Q1: 36.6867; 2020 Q2: 36.6867; 2020 Q3: 36.6867; 2021 Q4: 36.6867 | starting 09.2019 paid until 09.2020
[7 empty] | WP460203 | FPGA based vision algorithms implementation | 2020 Q1: 35.6474; 2020 Q2: 35.6474; 2020 Q3: 35.6474; 2021 Q4: 35.6474
PMT PLAN
[8 empty] | Period | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
[8 empty] | Start [MM-YY] | 01-00 | 01-00 | 01-00 | 01-00 | 01-00 | 01-00 | 01-00 | 01-00 | 01-00 | 01-00 | 01-00 | 01-00
[8 empty] | End [MM-YY] | 01-00 | 01-00 | 01-00 | 01-00 | 01-00 | 01-00 | 01-00 | 01-00 | 01-00 | 01-00 | 01-00 | 01-00
[8 empty] | Milestones | KO | TRR |  | TPDR |  | TCDR |  | FR |  |  |  |  | Total
[8 empty] | Payment Plan Per Period in % | 10% | 20% |  | 30% |  | 20% |  | 20% |  |  |  |  | 100% | in %
[8 empty] | "Payment Plan Per Period in EURO" | 224 400 | 448 800 |  | 673 200 |  | 448 800 |  | 448 800 |  |  |  |  | 2 246 000 | in EURO | 280750

## Price Table 8 OHB (hidden)
New Table 8 breakdown
Industrial Price
| Economic Conditions | 2019
| Currency | k€
[8 empty] | Year | 2020 |  |  |  | 2021 |  |  |  | 2022 |  |  |  | 2023 |  |  |  | 2024 |  |  |  | 2025 |  |  |  | TOTAL | VERIF
[8 empty] | Phase | Phase A |  |  | Phase B | [5 empty] | Phase C |  |  |  | Phase D | [7 empty] | Phase E
T8 CODE | Price Breakdown |  |  | CAT | TYPE | CONC | WP# | Q | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 |  | 16175.9644
| Space Segment | [6 empty] | Milestone | KO |  |  | MSRR
| Spacecraft | [7 empty] | 2020-02-01 | 2020-04-01 | 2020-06-30 | 2021-01-31
Project Office:
A1 | Management |  |  | MGT | Manpower | MGTManpower | 110000 |  | 13.0952 | 19.6428 | 53.3531 | 53.3531 | 53.3531 | 53.3531 | 53.3531 | 53.3531 | 53.3531 | 53.3531 | 53.3531 | 53.3531 | 55.8531 | 55.8531 | 52.3531 | 52.3531 | 52.3531 | 52.3531 | 52.3531 | 52.3531 | 15.369 | 15.369 | 13.869 | 13.869 | 1050.5709 | 1050.5709
A2 | Product Assurance |  |  | MGT | Manpower | MGTManpower | 130000 |  | 0 | 0 | 0 | 83.0307 | 57.0688 | 57.0688 | 57.0688 | 57.0688 | 62.0688 | 62.0688 | 54.5688 | 54.5688 | 56.0549 | 56.0549 | 56.0549 | 56.0549 | 56.0549 | 56.0549 | 57.5497 | 57.5497 | 62.2833 | 21.1763 | 9.9653 | 9.9653 | 1099.4004 | 1099.4004
A3 | (Project & Mission) Engineering |  |  | MISSION | Manpower | MISSIONManpower | 120000 140000 200000 310000 |  | 74.7399 | 117.1099 | 117.1099 | 2.5 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 313.9596 | 313.9596
Total Cost (k€)
A4 | Flight Systems Engineering |  |  | MISSION | Manpower | MISSIONManpower | 401000 | - 401422, 401423, 401520, 401533 to 401536 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
A5 | (System level) Assembly, Integration and Testing,Verification |  |  | MISSION | Manpower | MISSIONManpower | 501000 520000 530000 550000 | includes OHB-Sweden | 0 | 0 | 0 | 0 | 0 | 0 | 185.5543 | 0 | 0 | 19.9306 | 19.9306 | 13.4532 | 13.4532 | 233.8931 | 233.8931 | 181.8931 | 181.8931 | 98.9318 | 273.222 | 49.8266 | 0 | 0 | 0 | 0 | 1505.8749 | 1505.8749
A6 | Ground Segment Equipment |  |  | MISSION | Procurement | MISSIONProcurement | 510000 | includes OHB-Sweden (PGSE?), APCO | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 10
Total Cost (k€)
Platform Module Hardware/Software (HW/SW)
OB Flight Software
B11 | FSW - Manpower (M/y) tech |  |  | TECH | Manpower | TECHManpower | 410000 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
B12 | FSW - Manpower (M/y) mission |  |  | MISSION | Manpower | MISSIONManpower | ADS WP to see |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Cost (k€)
Data Handling
B21 | Data Handling - Engineering |  |  | MISSION | Manpower | MISSIONManpower | 430000 | includes ADS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
B22 | Data Handling - HW procurements |  |  | MISSION | Procurement | MISSIONProcurement | 430000 | includes ADS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Cost (k€)
Electrical Power
B31 | Electrical Power - Engineering and SW |  |  | MISSION | Manpower | MISSIONManpower | 420000 | includes ADS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
B32 | Electrical Power - HW procurements |  |  | MISSION | Procurement | MISSIONProcurement | 420000 | includes ADS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Cost (k€)
Communications
B41 | Communications - Engineering and SW |  |  | MISSION | Manpower | MISSIONManpower | 440000 | ADS CS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
B42 | Communications - HW procurements |  |  | MISSION | Procurement | MISSIONProcurement |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Cost (k€)
AOCS / GNC
B51 | AOCS / GNC - Engineering and SW |  |  | MISSION | Manpower | MISSIONManpower | 450000 |  | 0 | 39.8613 | 120.5804 | 299.2586 | 345.2161 | 318.3097 | 321.5983 | 327.8764 | 303.9596 | 273.0671 | 211.0655 | 119.7832 | 34.779 | 35.8752 | 35.8752 | 35.8752 | 35.8752 | 35.8752 | 35.8752 | 0 | 0 | 0 | 0 | 0 | 2930.6061 | 2930.6061 |  | Manpower to Start in Q2
B52 | AOCS / GNC - HW procurements |  |  | MISSION | Procurement | MISSIONProcurement |  |  | 0 | 0 | 0 | 0 | 145.0625 | 145.0625 | 511.375 | 511.375 | 495.8125 | 495.8125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2304.5 | 2304.5 |  | procurement in Q3
Total Cost (k€)
Propulsion
B61 | Propulsion - Engineering |  |  | MISSION | Manpower | MISSIONManpower | 470000 | OHB | 0 | 0 | 23.9168 | 29.896 | 38.8648 | 129.5492 | 114.6012 | 162.4764 | 80.7607 | 131.5839 | 114.6428 | 8.9827 | 41.8544 | 124.3672 | 17.9376 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1019.4334 | 1019.4334 |  | Manpower to Start in Q2
B62 | Propulsion - HW procurements |  |  | MISSION | Procurement | MISSIONProcurement | 470000 | OHB | 0 | 0 | 0 | 0 | 10 | 105 | 0 | 252.5 | 536 | 722.7 | 720.8 | 217.6 | 10 | 118 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2692.6 | 2692.6 |  | procurement in Q3
Total Cost (k€)
Structure
B71 | Structure - Engineering |  |  | TECH | Manpower | TECHManpower | 490100 to 49500 | - 490540 | 0 | 0 | 0 | 0 | 0 | 0 | 52.8162 | 52.8162 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 105.6324 | 105.6324
B72 | Structure - HW |  |  | TECH | Procurement | TECHProcurement | 490100 to 49500 | - 490540 | 0 | 0 | 0 | 0 | 0 | 0 | 34.275 | 34.275 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 68.55 | 68.55
Total Cost (k€)
Thermal Control
B81 | Thermal Control - Engineering |  |  | TECH | Manpower | TECHManpower | 490600 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
B82 | Thermal Control - HW |  |  | TECH | Procurement | TECHProcurement | 490600 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Cost (k€)
Mechanisms
B91 | Mechanisms - HW procurements |  |  | MISSION | Procurement | MISSIONProcurement | 490540 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Cost (k€)
Service Module HW/SW
Rendezvous GNC, Sensors and Processing (RVSP)
C11 | RVSP - Engineering and SW |  |  | TECH | Manpower | TECHManpower | 460100 to 460900 461000 41100to412000 461000 SYD |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C12 | RVSP - HW procurements |  |  | TECH | Procurement | TECHProcurement | 460100 to 460900 461000 SYD | + 401422, 401423, 401520, 401533 to 401536 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Cost (k€)
Capture System (CS)
C21 | CS - Engineering and SW |  |  | TECH | Manpower | TECHManpower | 480000 | CS EPFL | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C22 | CS - HW procurements |  |  | TECH | Procurement | TECHProcurement | 480000 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Cost (k€)
C3 | Service Module Validation |  |  | TECH | Procurement | TECHProcurement | 540000 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Risk Contingency (e.g. Technical, Management Reserve)
D | Launcher |  |  | MISSION | Procurement | MISSIONProcurement | 320000
Ground Segment & Operations
E1 | Ground Control Centre Development |  |  | MISSION | Manpower | MISSIONManpower | 610000 62000-620100 INCL. OHB 630000 |  | 0 | 63.7781 | 112.6081 | 48.8301 | 52.8162 | 73.2451 | 73.2451 | 109.1203 | 109.1203 | 65.0237 | 61.0376 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31.9237 | 31.9237 | 0 | 0 | 0 | 832.672 | 832.672
E2 | Mission Operations |  |  | MISSION | Manpower | MISSIONManpower | 710000 720000 730000 740000 750000 640000 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12.4567 | 75.5704 | 75.5704 | 75.5704 | 5.647 | 5.647 | 12.4567 | 12.4567 | 190.3117 | 160.33 | 349.3192 | 349.3192 | 342.5096 | 1667.1647 | 1667.1647
E3 | Ground observations & tools |  |  | TECH | Manpower | TECHManpower | 650000 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E4 | Ground Stations |  |  | MISSION | Procurement | MISSIONProcurement | 620100 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E5 | Ground Segment - Procurement |  |  | MISSION | Procurement | MISSIONProcurement | included in Flight SE and Ground Control Center Development |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 397.5 | 177.5 | 0 | 0 | 0 | 575 | 575
F | Contingency | [7 empty] | 8.7835 | 24.0392 | 42.7568 | 51.6868 | 70.4881 | 88.1588 | 140.3887 | 156.0861 | 164.1075 | 183.354 | 123.5399 | 48.0198 | 28.7565 | 69.9614 | 47.1684 | 33.1823 | 33.1823 | 25.5672 | 43.1457 | 77.9465 | 44.7406 | 38.5865 | 37.3154 | 36.6344 | 1617.5964 | 1617.5964
| TOT EX Contingency | [7 empty] | 87.8351 | 240.3921 | 427.5683 | 516.8685 | 704.8815 | 881.5885 | 1403.887 | 1560.8612 | 1641.0751 | 1833.5398 | 1235.3985 | 480.1976 | 287.5649 | 699.6139 | 471.6843 | 331.8234 | 331.8234 | 255.6717 | 431.4567 | 779.4649 | 447.406 | 385.8645 | 373.1536 | 366.3439 | 16175.9644 | 16175.9644 | 0
| TOT with contingency | [7 empty] | 96.6187 | 264.4313 | 470.3251 | 568.5553 | 775.3696 | 969.7473 | 1544.2757 | 1716.9473 | 1805.1826 | 2016.8938 | 1358.9384 | 528.2174 | 316.3214 | 769.5753 | 518.8527 | 365.0057 | 365.0057 | 281.2389 | 474.6024 | 857.4114 | 492.1466 | 424.451 | 410.4689 | 402.9783 | 17793.5609 | 17793.5609
|  |  |  | MGT | Manpower | MGTManpower |  |  | 13.0952 | 19.6428 | 53.3531 | 136.3838 | 110.422 | 110.422 | 110.422 | 110.422 | 115.422 | 115.422 | 107.922 | 107.922 | 111.9081 | 111.9081 | 108.4081 | 108.4081 | 108.4081 | 108.4081 | 109.9029 | 109.9029 | 77.6523 | 36.5453 | 23.8344 | 23.8344 | 2149.9713
|  |  |  | MISSION | Manpower | MISSIONManpower |  |  | 74.7399 | 220.7492 | 374.2152 | 380.4846 | 439.397 | 521.104 | 694.9989 | 599.473 | 493.8406 | 489.6054 | 406.6766 | 154.6757 | 165.6569 | 469.7058 | 363.2762 | 223.4153 | 223.4153 | 147.2636 | 321.5538 | 272.062 | 192.2537 | 349.3192 | 349.3192 | 342.5096 | 8269.7107
|  |  |  | TECH | Manpower | TECHManpower |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 52.8162 | 52.8162 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 105.6324
|  |  |  | MISSION | Procurement | MISSIONProcurement |  |  | 0 | 0 | 0 | 0 | 155.0625 | 250.0625 | 511.375 | 763.875 | 1031.8125 | 1228.5125 | 720.8 | 217.6 | 10 | 118 | 0 | 0 | 0 | 0 | 0 | 397.5 | 177.5 | 0 | 0 | 0 | 5582.1
|  |  |  | TECH | Procurement | TECHProcurement |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 34.275 | 34.275 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 68.55
[9 empty] | 87.8351 | 240.3921 | 427.5683 | 516.8685 | 704.8815 | 881.5885 | 1403.887 | 1560.8612 | 1641.0751 | 1833.5398 | 1235.3985 | 480.1976 | 287.5649 | 699.6139 | 471.6843 | 331.8234 | 331.8234 | 255.6717 | 431.4567 | 779.4649 | 447.406 | 385.8645 | 373.1536 | 366.3439 | 16175.9644
Note on H10: Brigitte Allegra: Work Package number

## NEW Price Table 8 v2-1 (hidden)
New Table 8 breakdown
Industrial Price
| Economic Conditions | 2019
| Currency | k€
[8 empty] | Year | 2020 |  |  |  | 2021 |  |  |  | 2022 |  |  |  | 2023 |  |  |  | 2024 |  |  |  | 2025
[8 empty] | Q | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
T8 CODE | Price Breakdown |  |  | CAT | TYPE | CONC | WP# | Phase | Phase A |  |  | Phase B | [5 empty] | Phase C |  |  |  | Phase D | [7 empty] | Phase E/F |  |  | #REF!
| Space Segment | [6 empty] | Milestone | KO |  |  | MSRR
| Spacecraft | [7 empty] | 2020-02-01 | 2020-04-01 | 2020-06-30 | 2021-01-31
Project Office:
A1 | Management |  |  | MGT | Manpower | MGTManpower | 110000 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
A2 | Product Assurance |  |  | MGT | Manpower | MGTManpower | 130000 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
A3 | (Project & Mission) Engineering |  |  | MISSION | Manpower | MISSIONManpower | 120000 140000 200000 310000 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Total Cost (k€)
A4 | Flight Systems Engineering |  |  | MISSION | Manpower | MISSIONManpower | 401000 | - 401422, 401423, 401520, 401533 to 401536 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
A5 | (System level) Assembly, Integration and Testing,Verification |  |  | MISSION | Manpower | MISSIONManpower | 501000 520000 530000 550000 | includes OHB-Sweden | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
A6 | Ground Segment Equipment |  |  | MISSION | Procurement | MISSIONProcurement | 510000 | includes OHB-Sweden (PGSE?), APCO | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Total Cost (k€)
Platform Module Hardware/Software (HW/SW)
OB Flight Software
B11 | FSW - Manpower (M/y) tech |  |  | TECH | Manpower | TECHManpower | 410000 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
B12 | FSW - Manpower (M/y) mission |  |  | MISSION | Manpower | MISSIONManpower |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Total Cost (k€)
| Data Handling | Combine & call CDPI
B21 | Data Handling - Engineering |  |  | MISSION | Manpower | MISSIONManpower | 430000 | includes ADS | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
B22 | Data Handling - HW procurements |  |  | MISSION | Procurement | MISSIONProcurement | 430000 | includes ADS | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Total Cost (k€)
Electrical Power
B31 | Electrical Power - Engineering and SW |  |  | MISSION | Manpower | MISSIONManpower | 420000 | includes ADS | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
B32 | Electrical Power - HW procurements |  |  | MISSION | Procurement | MISSIONProcurement | 420000 | includes ADS | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Total Cost (k€)
Communications
B41 | Communications - Engineering and SW |  |  | MISSION | Manpower | MISSIONManpower | 440000 | ADS CS | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
B42 | Communications - HW procurements |  |  | MISSION | Procurement | MISSIONProcurement | 440000 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Total Cost (k€)
AOCS / GNC
B51 | AOCS / GNC - Engineering and SW |  |  | MISSION | Manpower | MISSIONManpower | 450000 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
B52 | AOCS / GNC - HW procurements |  |  | MISSION | Procurement | MISSIONProcurement | 450000 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Total Cost (k€)
Propulsion
B61 | Propulsion - Engineering |  |  | MISSION | Manpower | MISSIONManpower | 470000 | OHB | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
B62 | Propulsion - HW procurements |  |  | MISSION | Procurement | MISSIONProcurement | 470000 | OHB | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Total Cost (k€)
Structure
B71 | Structure - Engineering |  |  | TECH | Manpower | TECHManpower | 490100 to 49500 | - 490540 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
B72 | Structure - HW |  |  | TECH | Procurement | TECHProcurement | 490100 to 49500 | - 490540 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Total Cost (k€)
Thermal Control
B81 | Thermal Control - Engineering |  |  | TECH | Manpower | TECHManpower | 490600 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
B82 | Thermal Control - HW |  |  | TECH | Procurement | TECHProcurement | 490600 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Total Cost (k€)
Mechanisms & harness
B91 | Mechanisms - HW procurements |  |  | MISSION | Procurement | MISSIONProcurement | 490540 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Total Cost (k€)
Service Module HW/SW
Rendezvous GNC, Sensors and Processing (RVSP)
C11 | RVSP - Engineering and SW |  |  | TECH | Manpower | TECHManpower | 460100 to 460900 461000 41100to412000 461000 SYD |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
C12 | RVSP - HW procurements |  |  | TECH | Procurement | TECHProcurement | 460100 to 460900 461000 SYD | + 401422, 401423, 401520, 401533 to 401536 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Total Cost (k€)
Capture System (CS)
C21 | CS - Engineering and SW |  |  | TECH | Manpower | TECHManpower | 480000 | CS EPFL RUAG | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
C22 | CS - HW procurements |  |  | TECH | Procurement | TECHProcurement | 480000 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Total Cost (k€)
C3 | Service Module Validation |  |  | TECH | Procurement | TECHProcurement | 540000 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| Risk Contingency (e.g. Technical, Management Reserve) | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D | Launcher |  |  | MISSION | Procurement | MISSIONProcurement | 320000 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Ground Segment & Operations
E1 | Ground Control Centre Development |  |  | MISSION | Manpower | MISSIONManpower | 610000 62000-620100 INCL. OHB 630000 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
E2 | Ground Control Centre Operations |  |  | MISSION | Manpower | MISSIONManpower | 710000 720000 730000 740000 750000 640000 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
E3 | Ground observations & tools |  |  | TECH | Manpower | TECHManpower | 650000 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
E4 | Ground Stations |  |  | MISSION | Procurement | MISSIONProcurement | 620100 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
E5 | Ground Segment - Procurement |  |  | MISSION | Procurement | MISSIONProcurement | 620100 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF!
F | Contingency | [7 empty] | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| TOT EX Contingency | [7 empty] | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| TOT with contingency | [7 empty] | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
|  |  |  | MGT | Manpower | MGTManpower |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
|  |  |  | MISSION | Manpower | MISSIONManpower |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
|  |  |  | TECH | Manpower | TECHManpower |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
|  |  |  | MISSION | Procurement | MISSIONProcurement |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
|  |  |  | TECH | Procurement | TECHProcurement |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[9 empty] | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| TOT CH | [7 empty] | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| TO CH EX Contingency | [7 empty] | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| CH Contingency | [7 empty] | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| Airbus Contingency | [7 empty] | 0 | 0 | 52.4264 | 164.4694 | 184.3794 | 78.2416 | 263.005 | 182.4944 | 192.8389 | 126.0357 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1243.8909
| OHB Contingency | [7 empty] | 8.7835 | 24.0392 | 42.7568 | 51.6868 | 70.4881 | 88.1588 | 140.3887 | 156.0861 | 164.1075 | 183.354 | 123.5399 | 48.0198 | 28.7565 | 69.9614 | 47.1684 | 33.1823 | 33.1823 | 25.5672 | 43.1457 | 77.9465 | 44.7406 | 38.5865 | 37.3154 | 36.6344 | 1617.5964
| Arianespace Contingency | [12 empty] | 150 | [9 empty] | 1200 |  | 750 |  | 600 | 300 |  |  |  | 3000
Note on H10: Brigitte Allegra: Work Package number

## OHB NEW (hidden)
Colour Code
|  | WP per period of 6 months | [23 empty] | VESPUP Planning updates - 29-08-2019
Labour Hourly Rate
|  | Mgm, PA, Mission Analysis, GNC S/S, Propulsion S/S, Sat STM&PFM AIT, Ground Segment, Preparation&Operation Support (Work Area) per period of 6 months | [24 empty] | 2020 |  |  |  | 2021 |  |  |  | 2022 |  |  |  | 2023 |  |  |  | 2024 |  |  |  | 2025
|  | Sum of each Work Area or all Work Areas for the total contract period | [24 empty] | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
Sum of each Work Area or all Work Areas for the total contract period with 10 %
Total sum per period of 6 months
Payment Plan Data
|  | Procurement Plan/Supplier Costs | [5 empty] | KPG 1 |  |  | KPG 2 |  | KPG 3 |  |  |  | KPG 4
[7 empty] | H12020 | H22020 | H12021 | H22021 | H12022 | H22022 | H12023 | H22023 | H12024 | H22024 | H12025 | H22025
[6 empty] | Phase | A | B | B | C | C | D | D | D | D | D/E | E | E
Please scroll to the right
Travel and profit should be folded in "cost for hours"
Work Package no
& Description | [22 empty] | Changes
Gross Hourly Rate in Euro in 2019 E.C. | [5 empty] | Phase: Project Management =; B: 123.2804; C: Engineers=; D: 99.6532
[20 empty] | WP# | WP Descr. | WP 110200 | CS: Start Q2/2020 OHB SWE: Start from Feb KO | T8 code | T8 Descr
|  |  | hours |  |  |  | 225 | 825 | 825 | 825 | 825 | 825 | 825 | 825 | 825 | 825 | 225 | 225 |  | 110200 | Management & Reporting | hours |  |  |  |  | 90 | 135 | 412.5 | 412.5 | 412.5 | 412.5 | 412.5 | 412.5 | 412.5 | 412.5 | 412.5 | 412.5 | 412.5 | 412.5 | 412.5 | 412.5 | 412.5 | 412.5 | 412.5 | 412.5 | 112.5 | 112.5 | 112.5 | 112.5
WP no: 110200 |  |  | cost for hours (kEUR) |  |  |  | 27.7381 | 101.7063 | 101.7063 | 101.7063 | 101.7063 | 101.7063 | 101.7063 | 101.7063 | 101.7063 | 101.7063 | 27.7381 | 27.7381 |  | 110200 | Management & Reporting | cost for hours (kEUR) |  | A1 | Management |  | 11.0952 | 16.6428 | 50.8531 | 50.8531 | 50.8531 | 50.8531 | 50.8531 | 50.8531 | 50.8531 | 50.8531 | 50.8531 | 50.8531 | 50.8531 | 50.8531 | 50.8531 | 50.8531 | 50.8531 | 50.8531 | 50.8531 | 50.8531 | 13.869 | 13.869 | 13.869 | 13.869
Management & Reporting |  |  | external costs/procurement (kEUR) | [16 empty] | 110200 | Management & Reporting | external costs/procurement (kEUR) |  | A1 | Management
|  |  | travel (kEUR) |  |  |  | 5 | 5 | 5 | 5 | 5 | 5 | 10 | 3 | 3 | 3 | 3 |  |  | 110200 | Management & Reporting | travel (kEUR) |  | A1 | Management |  | 2 | 3 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 5 | 5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5
|  |  | sum (kEUR) |  |  |  | 32.7381 | 106.7063 | 106.7063 | 106.7063 | 106.7063 | 106.7063 | 111.7063 | 104.7063 | 104.7063 | 104.7063 | 30.7381 | 27.7381 | 1050.5709 |  |  | sum (kEUR) |  |  |  |  | 13.0952 | 19.6428 | 53.3531 | 53.3531 | 53.3531 | 53.3531 | 53.3531 | 53.3531 | 53.3531 | 53.3531 | 53.3531 | 53.3531 | 55.8531 | 55.8531 | 52.3531 | 52.3531 | 52.3531 | 52.3531 | 52.3531 | 52.3531 | 15.369 | 15.369 | 13.869 | 13.869 | 1050.5709
[19 empty] | 1155.628 |  |  | WP 130220 | CS: Start Q4/2020 OHB SWE: OK
WP no: 130220 |  |  | hours |  |  |  |  | 220 | 220 | 220 | 220 | 220 | 300 | 300 | 300 | 330 | 425 | 200 |  | 130220 | S/W PA | hours | [7 empty] | 220 | 110 | 110 | 110 | 110 | 110 | 110 | 110 | 110 | 150 | 150 | 150 | 150 | 150 | 150 | 165 | 165 | 212.5 | 212.5 | 100 | 100
S/W PA |  |  | cost for hours (kEUR) |  |  |  | 0 | 21.9237 | 21.9237 | 21.9237 | 21.9237 | 21.9237 | 29.896 | 29.896 | 29.896 | 32.8856 | 42.3526 | 19.9306 |  | 130220 | S/W PA | cost for hours (kEUR) |  | A2 | Product Assurance |  | 0 | 0 | 0 | 21.9237 | 10.9619 | 10.9619 | 10.9619 | 10.9619 | 10.9619 | 10.9619 | 10.9619 | 10.9619 | 14.948 | 14.948 | 14.948 | 14.948 | 14.948 | 14.948 | 16.4428 | 16.4428 | 21.1763 | 21.1763 | 9.9653 | 9.9653
|  |  | external costs/procurement (kEUR) | [16 empty] | 130220 | S/W PA | external costs/procurement (kEUR) |  | A2 | Product Assurance
|  |  | travel (kEUR) | [16 empty] | 130220 | S/W PA | travel (kEUR) |  | A2 | Product Assurance
|  |  | sum (kEUR) |  |  |  | 0 | 21.9237 | 21.9237 | 21.9237 | 21.9237 | 21.9237 | 29.896 | 29.896 | 29.896 | 32.8856 | 42.3526 | 19.9306 | 294.4752 |  |  | sum (kEUR) |  |  |  |  | 0 | 0 | 0 | 21.9237 | 10.9619 | 10.9619 | 10.9619 | 10.9619 | 10.9619 | 10.9619 | 10.9619 | 10.9619 | 14.948 | 14.948 | 14.948 | 14.948 | 14.948 | 14.948 | 16.4428 | 16.4428 | 21.1763 | 21.1763 | 9.9653 | 9.9653 | 294.4752
[22 empty] | WP 130210 | CS: Start Q4/2020 OHBSWE: OK
WP no: 130210 |  |  | hours |  |  |  | 0 | 825 | 825 | 825 | 825 | 825 | 825 | 825 | 825 | 825 |  |  |  | 130210 | H/W and AIT PA | hours | [7 empty] | 412.5 | 412.5 | 412.5 | 412.5 | 412.5 | 412.5 | 412.5 | 412.5 | 412.5 | 412.5 | 412.5 | 412.5 | 412.5 | 412.5 | 412.5 | 412.5 | 412.5 | 412.5
H/W and AIT PA |  |  | cost for hours (kEUR) |  |  |  | 0 | 82.2139 | 82.2139 | 82.2139 | 82.2139 | 82.2139 | 82.2139 | 82.2139 | 82.2139 | 82.2139 | 0 | 0 |  | 130210 | H/W and AIT PA | cost for hours (kEUR) |  | A2 | Product Assurance |  | 0 | 0 | 0 | 41.107 | 41.107 | 41.107 | 41.107 | 41.107 | 41.107 | 41.107 | 41.107 | 41.107 | 41.107 | 41.107 | 41.107 | 41.107 | 41.107 | 41.107 | 41.107 | 41.107 | 41.107 | 0 | 0 | 0
|  |  | external costs/procurement (kEUR) | [16 empty] | 130210 | H/W and AIT PA | external costs/procurement (kEUR) |  | A2 | Product Assurance
|  |  | travel (kEUR) |  |  | B: 20; B: 10; C: 10; C: 20; D: 5 |  | 130210 | H/W and AIT PA | travel (kEUR) |  | A2 | Product Assurance |  |  |  |  | 20 | 5 | 5 | 5 | 5 | 10 | 10 | 2.5 | 2.5
|  |  | sum (kEUR) |  |  |  | 0 | 102.2139 | 92.2139 | 92.2139 | 102.2139 | 87.2139 | 82.2139 | 82.2139 | 82.2139 | 82.2139 | 0 | 0 | 804.9251 |  |  | sum (kEUR) |  |  |  |  | 0 | 0 | 0 | 61.107 | 46.107 | 46.107 | 46.107 | 46.107 | 51.107 | 51.107 | 43.607 | 43.607 | 41.107 | 41.107 | 41.107 | 41.107 | 41.107 | 41.107 | 41.107 | 41.107 | 41.107 | 0 | 0 | 0 | 804.9251
PA Sum
PA Sum |  |  | hours |  |  |  | 0 | 1045 | 1045 | 1045 | 1045 | 1045 | 1125 | 1125 | 1125 | 1155 | 425 | 200 |  |  | PA Sum | hours |  |  |  |  | 0 | 0 | 0 | 632.5 | 522.5 | 522.5 | 522.5 | 522.5 | 522.5 | 522.5 | 522.5 | 522.5 | 562.5 | 562.5 | 562.5 | 562.5 | 562.5 | 562.5 | 577.5 | 577.5 | 625 | 212.5 | 100 | 100 | 10380
|  |  | cost for hours (kEUR) |  |  |  | 0 | 104.1376 | 104.1376 | 104.1376 | 104.1376 | 104.1376 | 112.1099 | 112.1099 | 112.1099 | 115.0995 | 42.3526 | 19.9306 |  |  | PA Sum | cost for hours (kEUR) |  |  |  |  | 0 | 0 | 0 | 63.0307 | 52.0688 | 52.0688 | 52.0688 | 52.0688 | 52.0688 | 52.0688 | 52.0688 | 52.0688 | 56.0549 | 56.0549 | 56.0549 | 56.0549 | 56.0549 | 56.0549 | 57.5497 | 57.5497 | 62.2833 | 21.1763 | 9.9653 | 9.9653 | 1034.4004
|  |  | external costs/procurement (kUR) |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | PA Sum | external costs/procurement (kUR) |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | travel (kEUR) |  |  |  | 0 | 20 | 10 | 10 | 20 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | PA Sum | travel (kEUR) |  |  |  |  | 0 | 0 | 0 | 20 | 5 | 5 | 5 | 5 | 10 | 10 | 2.5 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65
|  |  | sum (kEUR) |  |  |  | 0 | 124.1376 | 114.1376 | 114.1376 | 124.1376 | 109.1376 | 112.1099 | 112.1099 | 112.1099 | 115.0995 | 42.3526 | 19.9306 | 1099.4004 |  |  | sum (kEUR) |  |  |  |  | 0 | 0 | 0 | 83.0307 | 57.0688 | 57.0688 | 57.0688 | 57.0688 | 62.0688 | 62.0688 | 54.5688 | 54.5688 | 56.0549 | 56.0549 | 56.0549 | 56.0549 | 56.0549 | 56.0549 | 57.5497 | 57.5497 | 62.2833 | 21.1763 | 9.9653 | 9.9653 | 1099.4004
[19 empty] | 1209.3404 |  |  | WP 210300 | CS: Start Q2/2020 to KPG1 Per: Feb 2020 - sep 2020
WP no: 210300 |  |  | hours |  |  | A: 2000; B: 1000 |  | 210300 | Mission Analysis/ Design | hours |  |  |  |  | 750 | 1125 | 1125
Mission Analysis/ Design |  |  | cost for hours (kEUR) |  |  |  | 199.3064 | 99.6532 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 210300 | Mission Analysis/ Design | cost for hours (kEUR) |  | A3 | (Project & Mission) Engineering |  | 74.7399 | 112.1099 | 112.1099 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | external costs/procurement (kEUR) | [16 empty] | 210300 | Mission Analysis/ Design | external costs/procurement (kEUR) |  | A3 | (Project & Mission) Engineering
|  |  | travel (kEUR) |  |  | A: 10; B: 5 |  | 210300 | Mission Analysis/ Design | travel (kEUR) |  | A3 | (Project & Mission) Engineering |  |  | 5 | 5 | 2.5 | 2.5
|  |  | sum (kEUR) |  |  |  | 209.3064 | 104.6532 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 313.9596 |  |  | sum (kEUR) |  |  |  |  | 74.7399 | 117.1099 | 117.1099 | 2.5 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 313.9596
[19 empty] | 345.3556 |  |  | WP 450100 | CS: Start Q2/2020 till KPG1. Stretch to 9M instead of 6M Per: June 2020 - Okt 2020
WP no: 450100 |  |  | hours |  |  | B: 970 |  | 450100 | GNC Req. & Eng. | hours | [5 empty] | 400 | 550 | 20
GNC Req. & Eng. |  |  | cost for hours (kEUR) |  |  |  | 0 | 96.6636 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 450100 | GNC Req. & Eng. | cost for hours (kEUR) |  | B51 | AOCS / GNC - Engineering and SW |  | 0 | 39.8613 | 54.8093 | 1.9931 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | external costs/procurement (kEUR) | [16 empty] | 450100 | GNC Req. & Eng. | external costs/procurement (kEUR) |  | B52 | AOCS / GNC - HW procurements
|  |  | travel (kEUR) | [16 empty] | 450100 | GNC Req. & Eng. | travel (kEUR) |  | B51 | AOCS / GNC - Engineering and SW
|  |  | sum (kEUR) |  |  |  | 0 | 96.6636 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 96.6636 |  |  | sum (kEUR) |  |  |  |  | 0 | 39.8613 | 54.8093 | 1.9931 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 96.6636
[22 empty] | WP 450200 | CS: Start Q2/2020 till KPG1 Per: Jul 2020 - Okt 2020
WP no: 450200 |  |  | hours |  |  | B: 993 |  | 450200 | GNC Prel. Design | hours | [6 empty] | 660 | 333
GNC Prel. Design |  |  | cost for hours (kEUR) |  |  |  | 0 | 98.9556 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 450200 | GNC Prel. Design | cost for hours (kEUR) |  | B51 | AOCS / GNC - Engineering and SW |  | 0 | 0 | 65.7711 | 33.1845 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | external costs/procurement (kEUR) | [16 empty] | 450200 | GNC Prel. Design | external costs/procurement (kEUR) |  | B52 | AOCS / GNC - HW procurements
|  |  | travel (kEUR) | [16 empty] | 450200 | GNC Prel. Design | travel (kEUR) |  | B51 | AOCS / GNC - Engineering and SW
|  |  | sum (kEUR) |  |  |  | 0 | 98.9556 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 98.9556 |  |  | sum (kEUR) |  |  |  |  | 0 | 0 | 65.7711 | 33.1845 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 98.9556
[22 empty] | WP 450300 | CS: From KPG1 Per: Nov 2020 - Sep 2021
WP no: 450300 |  |  | hours |  |  | B: 290; C: 350 |  | 450300 | GNC System Eng. DD | hours | [7 empty] | 100 | 180 | 180 | 180
GNC System Eng. DD |  |  | cost for hours (kEUR) |  |  |  | 0 | 0 | 28.8994 | 34.8786 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 450300 | GNC System Eng. DD | cost for hours (kEUR) |  | B51 | AOCS / GNC - Engineering and SW |  | 0 | 0 | 0 | 9.9653 | 17.9376 | 17.9376 | 17.9376 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | external costs/procurement (kEUR) | [16 empty] | 450300 | GNC System Eng. DD | external costs/procurement (kEUR) |  | B52 | AOCS / GNC - HW procurements
|  |  | travel (kEUR) | [16 empty] | 450300 | GNC System Eng. DD | travel (kEUR) |  | B51 | AOCS / GNC - Engineering and SW
|  |  | sum(kEUR) |  |  |  | 0 | 0 | 28.8994 | 34.8786 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 63.7781 |  |  | sum (kEUR) |  |  |  |  | 0 | 0 | 0 | 9.9653 | 17.9376 | 17.9376 | 17.9376 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 63.7781
[22 empty] | WP 450400 | CS: from KPG1 or earlier? PER: Okt 2020 - Jan 2022
WP no: 450400 |  |  | hours |  |  | B: 500; B: 2670 |  | 450400 | GNC DD | hours | [7 empty] | 1050 | 1040 | 300 | 300 | 360 | 120
GNC DD |  |  | cost for hours(kEUR) |  |  |  | 0 | 49.8266 | 266.0741 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 450400 | GNC DD | cost for hours (kEUR) |  | B51 | AOCS / GNC - Engineering and SW |  | 0 | 0 | 0 | 104.6359 | 103.6393 | 29.896 | 29.896 | 35.8752 | 11.9584 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | external costs/procurement (kEUR) | [16 empty] | 450400 | GNC DD | external costs/procurement (kEUR) |  | B52 | AOCS / GNC - HW procurements
|  |  | travel (kEUR) | [16 empty] | 450400 | GNC DD | travel (kEUR) |  | B51 | AOCS / GNC - Engineering and SW
|  |  | sum (kEUR) |  |  |  | 0 | 49.8266 | 266.0741 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 315.9007 |  |  | sum (kEUR) |  |  |  |  | 0 | 0 | 0 | 104.6359 | 103.6393 | 29.896 | 29.896 | 35.8752 | 11.9584 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 315.9007
[22 empty] | WP 450510 | CS: OK? Per: Nov 2020 - Mar 2021
WP no: 450510 |  |  | hours |  |  | B: 640 |  | 450510 | GNC SW Arch. Design | hours | [7 empty] | 320 | 320
GNC SW Arch. Design |  |  | cost for hours (kEUR) |  |  |  | 0 | 0 | 63.7781 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 450510 | GNC SW Arch. Design | cost for hours (kEUR) |  | B51 | AOCS / GNC - Engineering and SW |  | 0 | 0 | 0 | 31.889 | 31.889 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | external costs/procurement (kEUR) | [16 empty] | 450510 | GNC SW Arch. Design | external costs/procurement (kEUR) |  | B52 | AOCS / GNC - HW procurements
|  |  | travel (kEUR) | [16 empty] | 450510 | GNC SW Arch. Design | travel (kEUR) |  | B51 | AOCS / GNC - Engineering and SW
|  |  | sum (kEUR) |  |  |  | 0 | 0 | 63.7781 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 63.7781 |  |  | sum (kEUR) |  |  |  |  | 0 | 0 | 0 | 31.889 | 31.889 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 63.7781
[22 empty] | WP 450520 | CS: Per: March 2021 - June 2022
WP no: 450520 |  |  | hours |  |  | B: 345; C: 1671; C: 1475; D: 500 |  | 450520 | GNC SW DD and Unit Test | hours | [8 empty] | 200 | 600 | 600 | 870 | 870 | 851
GNC SW DD and Unit Test |  | U. Test | cost for hours (kEUR) |  |  |  | 0 | 0 | 34.3804 | 166.5205 | 146.9885 | 49.8266 | 0 | 0 | 0 | 0 | 0 | 0 |  | 450520 | GNC SW DD and Unit Test | cost for hours (kEUR) |  | B51 | AOCS / GNC - Engineering and SW |  | 0 | 0 | 0 | 0 | 19.9306 | 59.7919 | 59.7919 | 86.6983 | 86.6983 | 84.8049 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | external costs/procurement (kEUR) | [16 empty] | 450520 | GNC SW DD and Unit Test | external costs/procurement (kEUR) |  | B52 | AOCS / GNC - HW procurements
|  |  | travel (kEUR) | [16 empty] | 450520 | GNC SW DD and Unit Test | travel (kEUR) |  | B51 | AOCS / GNC - Engineering and SW
|  |  | sum (kEUR) |  |  |  | 0 | 0 | 34.3804 | 166.5205 | 146.9885 | 49.8266 | 0 | 0 | 0 | 0 | 0 | 0 | 397.716 |  |  | sum (kEUR) |  |  |  |  | 0 | 0 | 0 | 0 | 19.9306 | 59.7919 | 59.7919 | 86.6983 | 86.6983 | 84.8049 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 397.716
[22 empty] | WP 450530 | CS: Per: June 2022 - Nov 2022
WP no: 450530 |  |  | hours |  |  | D: 1548; D: 640 |  | 450530 | GNC SW Scenario Tests | hours | [13 empty] | 143 | 1227 | 818
GNC SW Scenario Tests |  |  | cost for hours (kEUR) |  |  |  | 0 | 0 | 0 | 0 | 0 | 154.2632 | 63.7781 | 0 | 0 | 0 | 0 | 0 |  | 450530 | GNC SW Scenario Tests | cost for hours (kEUR) |  | B51 | AOCS / GNC - Engineering and SW |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14.2504 | 122.2745 | 81.5163 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | external costs/procurement (kEUR) | [16 empty] | 450530 | GNC SW Scenario Tests | external costs/procurement (kEUR) |  | B52 | AOCS / GNC - HW procurements
|  |  | travel (kEUR) | [16 empty] | 450530 | GNC SW Scenario Tests | travel (kEUR) |  | B51 | AOCS / GNC - Engineering and SW
|  |  | sum (kEUR) |  |  |  | 0 | 0 | 0 | 0 | 0 | 154.2632 | 63.7781 | 0 | 0 | 0 | 0 | 0 | 218.0412 |  |  | sum (kEUR) |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14.2504 | 122.2745 | 81.5163 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 218.0412
[22 empty] | WP 450610 | CS: Per: Okt 2020 - May 2022
WP no: 450610 |  |  | hours |  |  | B: 2140; B: 2140; C: 500 |  | 450610 | GNC-level MIL/SIL Sim. | hours | [7 empty] | 753 | 753 | 753 | 753 | 660 | 660 | 448
GNC-level MIL/SIL Sim. |  |  | cost for hours (kEUR) |  |  |  | 0 | 213.2579 | 213.2579 | 49.8266 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 450610 | GNC-level MIL/SIL Sim. | cost for hours (kEUR) |  | B51 | AOCS / GNC - Engineering and SW |  | 0 | 0 | 0 | 75.0389 | 75.0389 | 75.0389 | 75.0389 | 65.7711 | 65.7711 | 44.6446 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | external costs/procurement (kEUR) | [16 empty] | 450610 | GNC-level MIL/SIL Sim. | external costs/procurement (kEUR) |  | B52 | AOCS / GNC - HW procurements
|  |  | travel (kEUR) | [16 empty] | 450610 | GNC-level MIL/SIL Sim. | travel (kEUR) |  | B51 | AOCS / GNC - Engineering and SW
|  |  | sum (kEUR) |  |  |  | 0 | 213.2579 | 213.2579 | 49.8266 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 476.3424 |  |  | sum (kEUR) |  |  |  |  | 0 | 0 | 0 | 75.0389 | 75.0389 | 75.0389 | 75.0389 | 65.7711 | 65.7711 | 44.6446 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 476.3424
[22 empty] | WP 450620 | CS: Per: Okt 2020 - May 2022
WP no: 450620 |  |  | hours |  |  | B: 300; B: 600; C: 600; C: 444 |  | 450620 | GNC Inputs to PIL-S. | hours | [7 empty] | 264 | 264 | 264 | 264 | 330 | 330 | 228
GNC Inputs to PIL-S. |  |  | cost for hours (kEUR) |  |  |  | 0 | 29.896 | 59.7919 | 59.7919 | 44.246 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 450620 | GNC Inputs to PIL-S. | cost for hours (kEUR) |  | B51 | AOCS / GNC - Engineering and SW |  | 0 | 0 | 0 | 26.3084 | 26.3084 | 26.3084 | 26.3084 | 32.8856 | 32.8856 | 22.7209 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | external costs/procurement (kEUR) | [16 empty] | 450620 | GNC Inputs to PIL-S. | external costs/procurement (kEUR) |  | B52 | AOCS / GNC - HW procurements
|  |  | travel (kEUR) | [16 empty] | 450620 | GNC Inputs to PIL-S. | travel (kEUR) |  | B51 | AOCS / GNC - Engineering and SW
|  |  | sum (kEUR) |  |  |  | 0 | 29.896 | 59.7919 | 59.7919 | 44.246 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 193.7258 |  |  | sum (kEUR) |  |  |  |  | 0 | 0 | 0 | 26.3084 | 26.3084 | 26.3084 | 26.3084 | 32.8856 | 32.8856 | 22.7209 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 193.7258
[22 empty] | WP 450630 | CS: This one we are pushing to the right… Per: De 2020 - Dec 2022
WP no: 450630 |  |  | hours |  |  | B: 500; B: 600; C: 100; C: 0 |  | 450630 | GNC Inputs to HIL-sim. | hours | [10 empty] | 198 | 198 | 198 | 198 | 204 | 204
GNC Inputs to HIL-sim. |  |  | cost for hours (kEUR) |  |  |  | 0 | 49.8266 | 59.7919 | 9.9653 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 450630 | GNC Inputs to HIL-sim. | cost for hours (kEUR) |  | B51 | AOCS / GNC - Engineering and SW |  | 0 | 0 | 0 | 0 | 0 | 0 | 19.7313 | 19.7313 | 19.7313 | 19.7313 | 20.3293 | 20.3293 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | external costs/procurement (kEUR) | [16 empty] | 450630 | GNC Inputs to HIL-sim. | external costs/procurement (kEUR) |  | B52 | AOCS / GNC - HW procurements
|  |  | travel (kEUR) | [16 empty] | 450630 | GNC Inputs to HIL-sim. | travel (kEUR) |  | B51 | AOCS / GNC - Engineering and SW
|  |  | sum (kEUR) |  |  |  | 0 | 49.8266 | 59.7919 | 9.9653 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 119.5839 |  |  | sum (kEUR) |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 19.7313 | 19.7313 | 19.7313 | 19.7313 | 20.3293 | 20.3293 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 119.5839
[22 empty] | WP 450700 | CS: Please check viability & accuracy Per: Dec 2020 - Sep 2022
WP no: 450700 |  |  | hours |  |  | B: 1238; B: 1236; C: 1238 |  | 450700 | GNC Equip. Proc. | hours | [7 empty] | 163 | 507 | 507 | 507 | 507 | 507 | 507 | 507
GNC Equip. Proc. |  |  | cost for hours (kEUR) |  |  |  | 0 | 123.3707 | 123.1714 | 123.3707 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 450700 | GNC Equip. Proc. | cost for hours (kEUR) |  | B51 | AOCS / GNC - Engineering and SW |  | 0 | 0 | 0 | 16.2435 | 50.5242 | 50.5242 | 50.5242 | 50.5242 | 50.5242 | 50.5242 | 50.5242 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | external costs/procurement (kEUR) |  |  | B: 290.125; B: 1022.75; C: 991.625 |  | 450700 | GNC Equip. Proc. | external costs/procurement (kEUR) |  | B52 | AOCS / GNC - HW procurements | [5 empty] | 145.0625 | 145.0625 | 511.375 | 511.375 | 495.8125 | 495.8125
|  |  | travel (kEUR) |  |  | B: 10; B: 10; C: 10 |  | 450700 | GNC Equip. Proc. | travel (kEUR) |  | B51 | AOCS / GNC - Engineering and SW | [5 empty] | 5 | 5 | 5 | 5 | 5 | 5
|  |  | sum (kEUR) |  |  |  | 0 | 423.4957 | 1155.9214 | 1124.9957 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2704.4127 |  |  | sum (kEUR) |  |  |  |  | 0 | 0 | 0 | 16.2435 | 200.5867 | 200.5867 | 566.8992 | 566.8992 | 551.3367 | 551.3367 | 50.5242 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2704.4127
[22 empty] | WP 450800 | CS: Please check viability & accuracy Per: Mar 2021 - June 2022
WP no: 450800 |  |  | hours |  |  | B: 500; C: 1200; C: 310 |  | 450800 | GNC Verification | hours | [8 empty] | 150 | 540 | 375 | 315 | 315 | 315
GNC Verification |  |  | cost for hours (kEUR) |  |  |  | 0 | 0 | 49.8266 | 119.5839 | 30.8925 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 450800 | GNC Verification | cost for hours (kEUR) |  | B51 | AOCS / GNC - Engineering and SW |  | 0 | 0 | 0 | 0 | 14.948 | 53.8127 | 37.37 | 31.3908 | 31.3908 | 31.3908 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | external costs/procurement (kEUR) | [16 empty] | 450800 | GNC Verification | external costs/procurement (kEUR) |  | B52 | AOCS / GNC - HW procurements
|  |  | travel (kEUR) | [16 empty] | 450800 | GNC Verification | travel (kEUR) |  | B51 | AOCS / GNC - Engineering and SW
|  |  | sum (kEUR) |  |  |  | 0 | 0 | 49.8266 | 119.5839 | 30.8925 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200.303 |  |  | sum (kEUR) |  |  |  |  | 0 | 0 | 0 | 0 | 14.948 | 53.8127 | 37.37 | 31.3908 | 31.3908 | 31.3908 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200.303
[22 empty] | WP 450900 | CS: This one we are pushing to the right… but please advise Per: Jul 2022 - Sep 2024
WP no: 450900 |  |  | hours |  |  | D: 669; D: 1100; D: 1100 |  | 450900 | GNC AIV Support | hours | [14 empty] | 180 | 180 | 349 | 360 | 360 | 360 | 360 | 360 | 360
GNC AIV Support |  |  | cost for hours (kEUR) |  |  |  | 0 | 0 | 0 | 0 | 0 | 66.668 | 109.6185 | 109.6185 | 0 | 0 | 0 | 0 |  | 450900 | GNC AIV Support | cost for hours (kEUR) |  | B51 | AOCS / GNC - Engineering and SW |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17.9376 | 17.9376 | 34.779 | 35.8752 | 35.8752 | 35.8752 | 35.8752 | 35.8752 | 35.8752 | 0 | 0 | 0 | 0 | 0
|  |  | external costs/procurement (kEUR) | 48 | [15 empty] | 450900 | GNC AIV Support | external costs/procurement (kEUR) |  | B52 | AOCS / GNC - HW procurements
|  |  | travel (kEUR) | [16 empty] | 450900 | GNC AIV Support | travel (kEUR) |  | B51 | AOCS / GNC - Engineering and SW
|  |  | sum ( kEUR) |  |  |  | 0 | 0 | 0 | 0 | 0 | 66.668 | 109.6185 | 109.6185 | 0 | 0 | 0 | 0 | 285.9051 |  |  | sum (kEUR) |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17.9376 | 17.9376 | 34.779 | 35.8752 | 35.8752 | 35.8752 | 35.8752 | 35.8752 | 35.8752 | 0 | 0 | 0 | 0 | 0 | 285.9051
GNC S/S
GNC S/S |  |  | hours |  |  |  | 0 | 6641 | 9021 | 5659 | 2229 | 2717 | 1740 | 1100 | 0 | 0 | 0 | 0 |  |  | GNC S/S | hours |  |  |  |  | 0 | 400 | 1210 | 3003 | 3414 | 3144 | 3177 | 3240 | 3000 | 2690 | 2118 | 1202 | 349 | 360 | 360 | 360 | 360 | 360 | 360 | 0 | 0 | 0 | 0 | 0 | 29107
|  |  | cost for hours (kEUR) |  |  |  | 0 | 661.797 | 898.9716 | 563.9375 | 222.127 | 270.7578 | 173.3966 | 109.6185 | 0 | 0 | 0 | 0 |  |  | GNC S/S | cost for hours (kEUR) |  |  |  |  | 0 | 39.8613 | 120.5804 | 299.2586 | 340.2161 | 313.3097 | 316.5983 | 322.8764 | 298.9596 | 268.0671 | 211.0655 | 119.7832 | 34.779 | 35.8752 | 35.8752 | 35.8752 | 35.8752 | 35.8752 | 35.8752 | 0 | 0 | 0 | 0 | 0 | 2900.6061
|  |  | external costs/procurement cost (kEUR) |  |  |  | 0 | 290.125 | 1022.75 | 991.625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | GNC S/S | external costs/procurement cost (kEUR) |  |  |  |  | 0 | 0 | 0 | 0 | 145.0625 | 145.0625 | 511.375 | 511.375 | 495.8125 | 495.8125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2304.5
|  |  | travle (kEUR) |  |  |  | 0 | 10 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | GNC S/S | travle (kEUR) |  |  |  |  | 0 | 0 | 0 | 0 | 5 | 5 | 5 | 5 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30
|  |  | sum (kEUR) |  |  |  | 0 | 961.922 | 1931.7216 | 1565.5625 | 222.127 | 270.7578 | 173.3966 | 109.6185 | 0 | 0 | 0 | 0 | 5235.1061 |  |  | sum (kEUR) |  |  |  |  | 0 | 39.8613 | 120.5804 | 299.2586 | 490.2786 | 463.3722 | 832.9733 | 839.2514 | 799.7721 | 768.8796 | 211.0655 | 119.7832 | 34.779 | 35.8752 | 35.8752 | 35.8752 | 35.8752 | 35.8752 | 35.8752 | 0 | 0 | 0 | 0 | 0 | 5235.1061
[19 empty] | 5758.6167 |  |  | WP 470100 | Alain confirmed
WP no: 470100 |  |  | hours |  |  | B: 480; B: 360; C: 360 |  | 470100 | Propulsion S/S Def. | hours | [6 empty] | 240 | 240 | 180 | 180 | 180 | 180
Propulsion S/S Def. |  |  | cost for hours (kEUR) |  |  |  | 0 | 47.8335 | 35.8752 | 35.8752 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 470100 | Propulsion S/S Def. | cost for hours (kEUR) |  | B61 | Propulsion - Engineering |  | 0 | 0 | 23.9168 | 23.9168 | 17.9376 | 17.9376 | 17.9376 | 17.9376 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | external costs/procurement (kEUR) | [16 empty] | 470100 | Propulsion S/S Def. | external costs/procurement (kEUR) |  | B62 | Propulsion - HW procurements
|  |  | travel (kEUR) | [16 empty] | 470100 | Propulsion S/S Def. | travel (kEUR) |  | B61 | Propulsion - Engineering
|  |  | sum (kEUR) |  |  |  | 0 | 47.8335 | 35.8752 | 35.8752 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 119.5839 |  |  | sum (kEUR) |  |  |  |  | 0 | 0 | 23.9168 | 23.9168 | 17.9376 | 17.9376 | 17.9376 | 17.9376 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 119.5839
[22 empty] | WP 470210 | Alain confirmed
WP no: 470210 |  |  | hours |  |  | B: 300; C: 180 |  | 470210 | Propulsion Design Consolidation &Analysis | hours | [9 empty] | 150 | 150 | 90 | 90
Propulsion Design |  |  | cost for hours (kEUR) |  |  |  | 0 | 0 | 29.896 | 17.9376 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 470210 | Propulsion Design Consolidation &Analysis | cost for hours (kEUR) |  | B61 | Propulsion - Engineering |  | 0 | 0 | 0 | 0 | 0 | 14.948 | 14.948 | 8.9688 | 8.9688 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Consolidation &Analysis |  |  | external costs/procurement (kEUR) | [16 empty] | 470210 | Propulsion Design Consolidation &Analysis | external costs/procurement (kEUR) |  | B62 | Propulsion - HW procurements
|  |  | travel (kEUR) | [16 empty] | 470210 | Propulsion Design Consolidation &Analysis | travel (kEUR) |  | B61 | Propulsion - Engineering
|  |  | sum (kEUR) |  |  |  | 0 | 0 | 29.896 | 17.9376 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47.8335 |  |  | sum (kEUR) |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 14.948 | 14.948 | 8.9688 | 8.9688 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47.8335
[22 empty] | WP 470220 | Alain confirmed
WP no: 470220 |  |  | hours |  |  | C: 120; C: 120 |  | 470220 | Electrical I/F and Engineering Model Design | hours | [7 empty] | 60 | 60 | 60 | 60
Electrical I/F and |  |  | cost for hours (kEUR) |  |  |  | 0 | 0 | 0 | 11.9584 | 11.9584 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 470220 | Electrical I/F and Engineering Model Design | cost for hours (kEUR) |  | B61 | Propulsion - Engineering |  | 0 | 0 | 0 | 5.9792 | 5.9792 | 5.9792 | 5.9792 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Engineering Model Design |  |  | external costs/procurement (kEUR) | [16 empty] | 470220 | Electrical I/F and Engineering Model Design | external costs/procurement (kEUR) |  | B62 | Propulsion - HW procurements
|  |  | travel ( kEUR) | [16 empty] | 470220 | Electrical I/F and Engineering Model Design | travel (kEUR) |  | B61 | Propulsion - Engineering
|  |  | sum (kEUR) |  |  |  | 0 | 0 | 0 | 11.9584 | 11.9584 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23.9168 |  |  | sum (kEUR) |  |  |  |  | 0 | 0 | 0 | 5.9792 | 5.9792 | 5.9792 | 5.9792 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23.9168
[22 empty] | WP 470230 | Alain confirmed
WP no: 470230 |  |  | hours |  |  | B: 480; C: 240 |  | 470230 | Performance and Analysis | hours | [9 empty] | 240 | 240 | 120 | 120
Performance and Analysis |  |  | cost for hours (kEUR) |  |  |  | 0 | 0 | 47.8335 | 23.9168 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 470230 | Performance and Analysis | cost for hours (kEUR) |  | B61 | Propulsion - Engineering |  | 0 | 0 | 0 | 0 | 0 | 23.9168 | 23.9168 | 11.9584 | 11.9584 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | external costs/procurement (kEUR) | [16 empty] | 470230 | Performance and Analysis | external costs/procurement (kEUR) |  | B62 | Propulsion - HW procurements
|  |  | travel (kEUR) | [16 empty] | 470230 | Performance and Analysis | travel (kEUR) |  | B61 | Propulsion - Engineering
|  |  | sum (kEUR) |  |  |  | 0 | 0 | 47.8335 | 23.9168 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 71.7503 |  |  | sum (kEUR) |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 23.9168 | 23.9168 | 11.9584 | 11.9584 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 71.7503
[22 empty] | WP 470300 | Alain confirmed
WP no: 470300 |  |  | hours |  |  | C: 1560 |  | 470300 | STM Design, manufact. and testing | hours | [9 empty] | 520 | 520 | 520
STM Design, manufact. |  |  | cost for hours (kEUR) |  |  |  | 0 | 0 | 0 | 0 | 155.459 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 470300 | STM Design, manufact. and testing | cost for hours (kEUR) |  | B61 | Propulsion - Engineering |  | 0 | 0 | 0 | 0 | 0 | 51.8197 | 51.8197 | 51.8197 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
and testing |  |  | external costs/procurement (kEUR) |  |  | C: 105 |  | 470300 | STM Design, manufact. and testing | external costs/procurement (kEUR) |  | B62 | Propulsion - HW procurements | [6 empty] | 105
|  |  | travel (kEUR) | [16 empty] | 470300 | STM Design, manufact. and testing | travel (kEUR) |  | B61 | Propulsion - Engineering
|  |  | sum (kEUR) |  |  |  | 0 | 0 | 0 | 0 | 260.459 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 260.459 |  |  | sum (kEUR) |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 156.8197 | 51.8197 | 51.8197 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 260.459
[22 empty] | WP 470410 | Alain confirmed
WP no: 470410 |  |  | hours |  |  | C: 240 |  | 470410 | PFM Procedures, Tooling, Fixture, MGSE Design & Manufacture | hours | [13 empty] | 240
PFM Procedures, Tooling, |  |  | cost for hours (kEUR) |  |  |  | 0 | 0 | 0 | 0 | 23.9168 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 470410 | PFM Procedures, Tooling, Fixture, MGSE Design & Manufacture | cost for hours (kEUR) |  | B61 | Propulsion - Engineering |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23.9168 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Fixture, MGSE Design & |  |  | external costs/procurement (kEUR) |  |  | C: 10 |  | 470410 | PFM Procedures, Tooling, Fixture, MGSE Design & Manufacture | external costs/procurement (kEUR) |  | B62 | Propulsion - HW procurements | [10 empty] | 10
Manufacture |  |  | travel (kEUR) | [16 empty] | 470410 | PFM Procedures, Tooling, Fixture, MGSE Design & Manufacture | travel (kEUR) |  | B61 | Propulsion - Engineering
|  |  | sum (kEUR) |  |  |  | 0 | 0 | 0 | 0 | 33.9168 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33.9168 |  |  | sum (kEUR) |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33.9168 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33.9168
[22 empty] | WP 470420 | Alain confirmed
WP no: 470420 |  |  | hours |  |  | C: 300 |  | 470420 | EM and EGSE | hours | [8 empty] | 150 | 150
EM and EGSE |  |  | cost for hours (kEUR) |  |  |  | 0 | 0 | 0 | 0 | 29.896 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 470420 | EM and EGSE | cost for hours (kEUR) |  | B61 | Propulsion - Engineering |  | 0 | 0 | 0 | 0 | 14.948 | 14.948 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | external costs/procurement (kEUR) |  |  | C: 10 |  | 470420 | EM and EGSE | external costs/procurement (kEUR) |  | B62 | Propulsion - HW procurements | [5 empty] | 10
|  |  | travel (kEUR) | [16 empty] | 470420 | EM and EGSE | travel (kEUR) |  | B61 | Propulsion - Engineering
|  |  | sum (kEUR) |  |  |  | 0 | 0 | 0 | 0 | 39.896 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39.896 |  |  | sum (kEUR) |  |  |  |  | 0 | 0 | 0 | 0 | 24.948 | 14.948 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39.896
[22 empty] | WP 470430 | Alain confirmed
WP no: 470430 |  |  | hours |  |  | C: 480; D: 480 |  | 470430 | PFM AI | hours | [13 empty] | 480 | 480
PFM AI |  |  | cost for hours (kEUR) |  |  |  | 0 | 0 | 0 | 0 | 47.8335 | 47.8335 | 0 | 0 | 0 | 0 | 0 | 0 |  | 470430 | PFM AI | cost for hours (kEUR) |  | B61 | Propulsion - Engineering |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47.8335 | 47.8335 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | external costs/procurement (kEUR) | [16 empty] | 470430 | PFM AI | external costs/procurement (kEUR) |  | B62 | Propulsion - HW procurements
|  |  | travel (kEUR) | [16 empty] | 470430 | PFM AI | travel (kEUR) |  | B61 | Propulsion - Engineering
|  |  | sum (kEUR) |  |  |  | 0 | 0 | 0 | 0 | 47.8335 | 47.8335 | 0 | 0 | 0 | 0 | 0 | 0 | 95.6671 |  |  | sum (kEUR) |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47.8335 | 47.8335 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 95.6671
[22 empty] | WP 470510 | Alain confirmed
WP no: 470510 |  |  | hours |  |  | C: 180 |  | 470510 | S/S Verification and Test | hours | [16 empty] | 180
S/S Verification and Test |  |  | cost for hours (kEUR) |  |  |  | 0 | 0 | 0 | 0 | 17.9376 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 470510 | S/S Verification and Test | cost for hours (kEUR) |  | B61 | Propulsion - Engineering |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17.9376 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Plan |  |  | external costs/procurement (kEUR) | [16 empty] | 470510 | S/S Verification and Test | external costs/procurement (kEUR) |  | B62 | Propulsion - HW procurements
|  |  | travel (kEUR) | [16 empty] | 470510 | S/S Verification and Test | travel (kEUR) |  | B61 | Propulsion - Engineering
|  |  | sum (kEUR) |  |  |  | 0 | 0 | 0 | 0 | 17.9376 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17.9376 |  |  | sum (kEUR) |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17.9376 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17.9376
[22 empty] | WP 470520 | Alain confirmed
WP no: 470520 |  |  | hours |  |  | C: 240 |  | 470520 | GSE Design and Manuf. | hours | [16 empty] | 240
GSE Design and Manuf. |  |  | cost for hours (kEUR) |  |  |  | 0 | 0 |  | 0 | 23.9168 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 470520 | GSE Design and Manuf. | cost for hours (kEUR) |  | B61 | Propulsion - Engineering |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23.9168 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | external costs/procurement (kEUR) |  |  | C: 10 |  | 470520 | GSE Design and Manuf. | external costs/procurement (kEUR) |  | B62 | Propulsion - HW procurements | [13 empty] | 10
|  |  | travel (kEUR) | [16 empty] | 470520 | GSE Design and Manuf. | travel (kEUR) |  | B61 | Propulsion - Engineering
|  |  | sum (kEUR) |  |  |  | 0 | 0 |  | 0 | 33.9168 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33.9168 |  |  | sum (kEUR) |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33.9168 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33.9168
[22 empty] | WP 470530 | Alain confirmed
WP no: 470530 |  |  | hours |  |  | D: 168 |  | 470530 | PFM Testing | hours | [17 empty] | 168
PFM Testing |  |  | cost for hours |  |  |  | 0 | 0 | 0 | 0 | 0 | 16.7417 | 0 | 0 | 0 | 0 | 0 | 0 |  | 470530 | PFM Testing | cost for hours (kEUR) |  | B61 | Propulsion - Engineering |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16.7417 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | external costs/procurement (kEUR) | [16 empty] | 470530 | PFM Testing | external costs/procurement (kEUR) |  | B62 | Propulsion - HW procurements
|  |  | travel (kEUR) | [16 empty] | 470530 | PFM Testing | travel (kEUR) |  | B61 | Propulsion - Engineering
|  |  | sum (kEUR) |  |  |  | 0 | 0 | 0 | 0 | 0 | 16.7417 | 0 | 0 | 0 | 0 | 0 | 0 | 16.7417 |  |  | sum (kEUR) |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16.7417 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16.7417
[22 empty] | WP 472540 | Alain confirmed
WP no: 472540 |  |  | hours |  |  | D: 180 |  | 472540 | Support to Sat AIT | hours | [18 empty] | 180
Support to Sat AIT |  |  | cost for hours |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17.9376 | 0 | 0 | 0 | 0 |  | 472540 | Support to Sat AIT | cost for hours (kEUR) |  | B61 | Propulsion - Engineering |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17.9376 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | external costs/procurement (kEUR) | [16 empty] | 472540 | Support to Sat AIT | external costs/procurement (kEUR) |  | B62 | Propulsion - HW procurements
|  |  | travel (kEUR) | [16 empty] | 472540 | Support to Sat AIT | travel (kEUR) |  | B61 | Propulsion - Engineering
|  |  | sum (kEUR) |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17.9376 | 0 | 0 | 0 | 0 | 17.9376 |  |  | sum (kEUR) |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17.9376 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17.9376
[22 empty] | WP 470550 | Alain confirmed
WP no: 470550 |  |  | hours |  |  | C: 540; D: 540 |  | 470550 | PFM Sub assembly manuf. and test incl. Piping | hours | [17 empty] | 1080
PFM Sub assembly manuf. |  |  | cost for hours |  |  |  | 0 | 0 | 0 | 0 | 53.8127 | 53.8127 | 0 | 0 | 0 | 0 | 0 | 0 |  | 470550 | PFM Sub assembly manuf. and test incl. Piping | cost for hours (kEUR) |  | B61 | Propulsion - Engineering |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 107.6255 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
and test incl. piping |  |  | external costs/procurement (kEUR) |  |  | C: 118 |  | 470550 | PFM Sub assembly manuf. and test incl. Piping | external costs/procurement (kEUR) |  | B62 | Propulsion - HW procurements | [14 empty] | 118
|  |  | travel (kEUR) | [16 empty] | 470550 | PFM Sub assembly manuf. and test incl. Piping | travel (kEUR) |  | B61 | Propulsion - Engineering
|  |  | sum (kEUR) |  |  |  | 0 | 0 | 0 | 0 | 171.8127 | 53.8127 | 0 | 0 | 0 | 0 | 0 | 0 | 225.6255 |  |  | sum (kEUR) |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 225.6255 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 225.6255
[22 empty] | WP 470560 | Alain confirmed
WP no: 470560 |  |  | hours |  |  | B: 600; B: 480; C: 480; C: 550; D: 50 |  | 470560 | Equipment Procurement | hours | [11 empty] | 600 | 480 | 480 | 550 | 50
Equipment Procurement |  |  | cost for hours (kEUR) |  |  |  | 0 | 59.7919 | 47.8335 | 47.8335 | 54.8093 | 4.9827 | 0 | 0 | 0 | 0 | 0 | 0 |  | 470560 | Equipment Procurement | cost for hours (kEUR) |  | B61 | Propulsion - Engineering |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 59.7919 | 47.8335 | 47.8335 | 54.8093 | 4.9827 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | external costs/procurement (kEUR) |  |  | B: 252.5; B: 536; C: 712.7; C: 720.8; D: 217.6 |  | 470560 | Equipment Procurement | external costs/procurement (kEUR) |  | B62 | Propulsion - HW procurements | [8 empty] | 252.5 | 536 | 712.7 | 720.8 | 217.6
|  |  | travel (kEUR) |  |  | B: 12; B: 12; C: 12; C: 12; D: 4 |  | 470560 | Equipment Procurement | travel (kEUR) |  | B61 | Propulsion - Engineering | [8 empty] | 12 | 12 | 12 | 12 | 4
|  |  | sum (kEUR) |  |  |  | 0 | 324.2919 | 595.8335 | 772.5335 | 787.6093 | 226.5827 | 0 | 0 | 0 | 0 | 0 | 0 | 2706.8509 |  |  | sum (kEUR) |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 324.2919 | 595.8335 | 772.5335 | 787.6093 | 226.5827 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2706.8509
Propulsion S/S
Propulsion S/S |  |  | hours |  |  |  | 0 | 1080 | 1620 | 1380 | 4210 | 1238 | 0 | 180 | 0 | 0 | 0 | 0 |  |  | Propulsion S/S | hours |  |  |  |  | 0 | 0 | 240 | 300 | 390 | 1300 | 1150 | 1510 | 690 | 1200 | 1030 | 50 | 420 | 1248 | 180 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9708
|  |  | cost for hours (kEUR) |  |  |  | 0 | 107.6255 | 161.4382 | 137.5214 | 419.54 | 123.3707 | 0 | 17.9376 | 0 | 0 | 0 | 0 |  |  | Propulsion S/S | cost for hours (kEUR) |  |  |  |  | 0 | 0 | 23.9168 | 29.896 | 38.8648 | 129.5492 | 114.6012 | 150.4764 | 68.7607 | 119.5839 | 102.6428 | 4.9827 | 41.8544 | 124.3672 | 17.9376 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 967.4334
|  |  | external costs/procurement (kEUR) |  |  |  | 0 | 252.5 | 536 | 712.7 | 973.8 | 217.6 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Propulsion S/S | external costs/procurement (kEUR) |  |  |  |  | 0 | 0 | 0 | 0 | 10 | 105 | 0 | 252.5 | 536 | 722.7 | 720.8 | 217.6 | 10 | 118 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2692.6
|  |  | travel (kEUR) |  |  |  | 0 | 12 | 12 | 12 | 12 | 4 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Propulsion S/S | travel (kEUR) |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 12 | 12 | 12 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52
|  |  | sum (kEUR) |  |  |  | 0 | 372.1255 | 709.4382 | 862.2214 | 1405.34 | 344.9707 | 0 | 17.9376 | 0 | 0 | 0 | 0 | 3712.0334 |  |  | sum (kEUR) |  |  |  |  | 0 | 0 | 23.9168 | 29.896 | 48.8648 | 234.5492 | 114.6012 | 414.9764 | 616.7607 | 854.2839 | 835.4428 | 226.5827 | 51.8544 | 242.3672 | 17.9376 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3712.0334
[19 empty] | 4083.2367 |  |  | WP 510100 | CS: OK to push to the right, or is it needed for the STM or other? Mia: OK, EGSE should only be needed for PFM AIT
WP no: 510100 |  |  | hours |  |  | C: 400; C: 270 |  | 510100 | Acquisition of EGSE | hours | [13 empty] | 200 | 200 | 135 | 135
Acquisition of EGSE |  |  | cost for hours (kEUR) |  |  |  | 0 | 0 | 0 | 39.8613 | 26.9064 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 510100 | Acquisition of EGSE | cost for hours (kEUR) |  | A5 | (System level) Assembly, Integration and Testing,Verification |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19.9306 | 19.9306 | 13.4532 | 13.4532 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | external costs/procurement(kEUR) |  |  | C: 10 |  | 510100 | Acquisition of EGSE | external costs/procurement (kEUR) |  | A6 | Ground Segment Equipment | [10 empty] | 10
|  |  | travel (kEUR) | [16 empty] | 510100 | Acquisition of EGSE | travel (kEUR) |  | A5 | (System level) Assembly, Integration and Testing,Verification
|  |  | sum (kEUR) |  |  |  | 0 | 0 | 0 | 49.8613 | 26.9064 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 76.7677 |  |  | sum (kEUR) |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29.9306 | 19.9306 | 13.4532 | 13.4532 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 76.7677
[22 empty] | WP 520200 | CS: Shifted BACK from H12022 to H2 2021 Mia: OK
WP no: 520200 |  |  | hours |  |  | C: 1862 |  | 520200 | Sat STM A&I | hours | [10 empty] | 1862
Sat STM A&I |  |  | cost for hours (kEUR) |  |  |  | 0 | 0 | 0 | 0 | 185.5543 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 520200 | Sat STM A&I | cost for hours (kEUR) |  | A5 | (System level) Assembly, Integration and Testing,Verification |  | 0 | 0 | 0 | 0 | 0 | 0 | 185.5543 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | external costs/procurement (kEUR) | [16 empty] | 520200 | Sat STM A&I | external costs/procurement (kEUR) |  | A6 | Ground Segment Equipment
|  |  | travel (kEUR) | [16 empty] | 520200 | Sat STM A&I | travel (kEUR) |  | A5 | (System level) Assembly, Integration and Testing,Verification
|  |  | sum (kEUR) |  |  |  | 0 | 0 | 0 | 0 | 185.5543 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 185.5543 |  |  | sum (kEUR) |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 185.5543 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 185.5543
[22 empty] | WP 490440 | CS: Shifted BACK from H1 2022 to H22022 Mia: OK
Wp no:490440 |  |  | hours |  |  | C: 1060 |  | 490440 | Sat STM Environmental testing | hours | [10 empty] | 530 | 530
Sat STM Environmental |  |  | cost for hours (kEUR) |  |  |  | 0 | 0 | 0 | 0 | 105.6324 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 490440 | Sat STM Environmental testing | cost for hours (kEUR) |  | B71 | Structure - Engineering |  | 0 | 0 | 0 | 0 | 0 | 0 | 52.8162 | 52.8162 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Testing |  |  | external costs/procurement (kEUR) |  |  | C: 68.55 |  | 490440 | Sat STM Environmental testing | external costs/procurement (kEUR) |  | B72 | Structure - HW | [7 empty] | 34.275 | 34.275
|  |  | travel (kEUR) | [16 empty] | 490440 | Sat STM Environmental testing | travel (kEUR) |  | B71 | Structure - Engineering
|  |  | sum (kEUR) |  |  |  | 0 | 0 | 0 | 0 | 174.1824 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 174.1824 |  |  | sum (kEUR) |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 87.0912 | 87.0912 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 174.1824
[22 empty] | WP 550100 | CS: Shifted a bit to the right Mia: OK, but I count that PFM AIT margin is included, so in fact it will be ready before end Q3 2024
WP no: 550100 |  |  | hours |  |  | D: 3500; D: 3500; D: 1835 |  | 550100 | Sat PFM A&I | hours | [17 empty] | 1750 | 1750 | 1750 | 1750 | 917.5 | 917.5
Sat PFM A&I |  |  | cost for hours (kEUR) |  |  |  | 0 | 0 | 0 | 0 | 0 | 348.7863 | 348.7863 | 182.8636 | 0 | 0 | 0 | 0 |  | 550100 | Sat PFM A&I | cost for hours (kEUR) |  | A5 | (System level) Assembly, Integration and Testing,Verification |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 174.3931 | 174.3931 | 174.3931 | 174.3931 | 91.4318 | 91.4318 | 0 | 0 | 0 | 0 | 0
|  |  | external costs/procurement (kEUR) |  |  | D: 104 |  | 550100 | Sat PFM A&I | external costs/procurement (kEUR) |  | A5 | (System level) Assembly, Integration and Testing,Verification | [14 empty] | 52 | 52
|  |  | travel (kEUR) |  |  | D: 15; D: 15; D: 15 |  | 550100 | Sat PFM A&I | travel (kEUR) |  | A5 | (System level) Assembly, Integration and Testing,Verification | [14 empty] | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5
|  |  | sum (kEUR) |  |  |  | 0 | 0 | 0 | 0 | 0 | 467.7863 | 363.7863 | 197.8636 | 0 | 0 | 0 | 0 | 1029.4361 |  |  | sum (kEUR) |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 233.8931 | 233.8931 | 181.8931 | 181.8931 | 98.9318 | 98.9318 | 0 | 0 | 0 | 0 | 0 | 1029.4361
[22 empty] | WP 550200 | CS: Shrunk to 6M instead of 12M and shifted to right Mia: Ok if PFM AIT is finished before Q3. PFM needs to be ready for start of test. 215 h for testing is too small. Moved hours from Q3 to Q4 to have 500h in Q4.
WP no: 550200 |  |  | hours |  |  | D: 890; D: 215 |  | 550200 | PFM Environmental Test Camp. | hours | [22 empty] | 605 | 500
PFM Environmental Test Camp. |  |  | cost for hours (kEUR) |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 88.6914 | 21.4254 | 0 | 0 | 0 |  | 550200 | PFM Environmental Test Camp. | cost for hours (kEUR) |  | A5 | (System level) Assembly, Integration and Testing,Verification |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60.2902 | 49.8266 | 0 | 0 | 0 | 0
|  |  | external costs/procurement (kEUR) |  |  | D: 114 |  | 550200 | PFM Environmental Test Camp. | external costs/procurement (kEUR) |  | A5 | (System level) Assembly, Integration and Testing,Verification | [19 empty] | 114
|  |  | travel (kEUR) | [16 empty] | 550200 | PFM Environmental Test Camp. | travel (kEUR) |  | A5 | (System level) Assembly, Integration and Testing,Verification
|  |  | sum (kEUR) |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 202.6914 | 21.4254 | 0 | 0 | 0 | 224.1168 |  |  | sum (kEUR) |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 174.2902 | 49.8266 | 0 | 0 | 0 | 0 | 224.1168
[22 empty] | WP 730100/200 | CS: Shrunk to 6M instead of 12M and shifted to right Mia: Same as above, PFM test needs to be finalised to start packing and shipping. Too many hours cumulated for OHB Sweden in Q4 2024. Moved hours from Q4 to Q1 to have 902 h in Q1.
WP no: 730100,730200 |  |  | hours |  |  | D: 1443; D/E: 702 |  | 730000 | Phase E Launch Campaign | hours | [23 empty] | 1243 | 902
Phase E |  |  | cost for hours(kEUR) |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 143.7996 | 69.9566 | 0 | 0 |  | 730000 | Phase E Launch Campaign | cost for hours (kEUR) |  | E2 | Mission Operations |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 123.8689 | 89.8872 | 0 | 0 | 0
Launch Campaign |  |  | external costs/procurement (kEUR) |  |  | D: 397.5; D/E: 177.5 |  | 730000 | Phase E Launch Campaign | external costs/procurement (kEUR) |  | E5 | Ground Segment - Procurement | [20 empty] | 397.5 | 177.5
|  |  | travel (kEUR) |  |  | D: 50; D/E: 54 |  | 730000 | Phase E Launch Campaign | travel (kEUR) |  | E2 | Mission Operations | [20 empty] | 50 | 54
|  |  | sum (kEUR) |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 591.2996 | 301.4566 | 0 | 0 | 892.7561 |  |  | sum (kEUR) |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 571.3689 | 321.3872 | 0 | 0 | 0 | 892.7561
Sat STM and PFM AIT
Sat STM and PFM AIT |  |  | hours |  |  |  | 0 | 0 | 0 | 400 | 3192 | 3500 | 3500 | 2725 | 1658 | 702 | 0 | 0 |  |  | Sat STM and PFM AIT | hours |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 2392 | 530 | 0 | 200 | 200 | 135 | 135 | 1750 | 1750 | 1750 | 1750 | 917.5 | 1522.5 | 1743 | 902 | 0 | 0 | 0 | 15677
|  |  | cost for hours (kEUR) |  |  |  | 0 | 0 | 0 | 39.8613 | 318.0931 | 348.7863 | 348.7863 | 271.555 | 165.225 | 69.9566 | 0 | 0 |  |  | Sat STM and PFM AIT | cost for hours (kEUR) |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 238.3705 | 52.8162 | 0 | 19.9306 | 19.9306 | 13.4532 | 13.4532 | 174.3931 | 174.3931 | 174.3931 | 174.3931 | 91.4318 | 151.722 | 173.6956 | 89.8872 | 0 | 0 | 0 | 1562.2634
|  |  | external costs/procurement (kEUR) |  |  |  | 0 | 0 | 0 | 10 | 68.55 | 104 | 0 | 114 | 397.5 | 177.5 | 0 | 0 |  |  | Sat STM and PFM AIT | external costs/procurement (kEUR) |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 34.275 | 34.275 | 0 | 10 | 0 | 0 | 0 | 52 | 52 | 0 | 0 | 0 | 114 | 397.5 | 177.5 | 0 | 0 | 0 | 871.55
|  |  | travel (kEUR) |  |  |  | 0 | 0 | 0 | 0 | 0 | 15 | 15 | 15 | 50 | 54 | 0 | 0 |  |  | Sat STM and PFM AIT | travel (kEUR) |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 50 | 54 | 0 | 0 | 0 | 149
|  |  | sum (kEUR) |  |  |  | 0 | 0 | 0 | 49.8613 | 386.6431 | 467.7863 | 363.7863 | 400.555 | 612.725 | 301.4566 | 0 | 0 | 2582.8134 |  |  | sum (kEUR) |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 272.6455 | 87.0912 | 0 | 29.9306 | 19.9306 | 13.4532 | 13.4532 | 233.8931 | 233.8931 | 181.8931 | 181.8931 | 98.9318 | 273.222 | 621.1956 | 321.3872 | 0 | 0 | 0 | 2582.8134
2841.0948
[22 empty] | WP 620220 | CS: Shifted a bit to the left Niklas A: Added 3months at start to allow pre-development to support CDPI EM. Total hours unchanged
WP no: 620220 |  |  | hours |  |  | B: 1470; C: 1470; C: 1470; D: 1225 |  | 620220 | RAMSES Customization | hours | [6 empty] | 490 | 490 | 490 | 735 | 735 | 735 | 735 | 612.5 | 612.5
RAMSES Customization |  |  | cost for hours (kEUR) |  |  |  | 0 | 0 | 146.4902 | 146.4902 | 146.4902 | 122.0752 | 0 | 0 | 0 | 0 | 0 | 0 |  | 620220 | RAMSES Customization | cost for hours (kEUR) |  | E1 | Ground Control Centre Development |  | 0 | 0 | 48.8301 | 48.8301 | 48.8301 | 73.2451 | 73.2451 | 73.2451 | 73.2451 | 61.0376 | 61.0376 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | external costs/procurement (kEUR) | [16 empty] | 620220 | RAMSES Customization | external costs/procurement (kEUR) |  | E1 | Ground Control Centre Development
|  |  | travel (kEUR) | [16 empty] | 620220 | RAMSES Customization | travel (kEUR) |  | E1 | Ground Control Centre Development
|  |  | sum (kEUR) |  |  |  | 0 | 0 | 146.4902 | 146.4902 | 146.4902 | 122.0752 | 0 | 0 | 0 | 0 | 0 | 0 | 561.5459 |  |  | sum (kEUR) |  |  |  |  | 0 | 0 | 48.8301 | 48.8301 | 48.8301 | 73.2451 | 73.2451 | 73.2451 | 73.2451 | 61.0376 | 61.0376 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 561.5459
[6 empty] | B: 0 |  |  |  | WP 620230 | CS: This WP we need to start early to have the MCS available for the CDPI EM Niklas A: Confirmed OK
WP no: 620230 |  |  | hours |  |  | C: 1280 |  | 620230 | Mission TM/TC Database | hours | [5 empty] | 640 | 640
Mission TM/TC Database |  |  | cost for hours (kEUR) |  |  |  | 0 | 0 | 0 | 127.5561 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 620230 | Mission TM/TC Database | cost for hours (kEUR) |  | E1 | Ground Control Centre Development |  | 0 | 63.7781 | 63.7781 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Conversion |  |  | external costs/procurement (kEUR) | [16 empty] | 620230 | Mission TM/TC Database | external costs/procurement (kEUR) |  | E1 | Ground Control Centre Development
|  |  | travel (kEUR) | [16 empty] | 620230 | Mission TM/TC Database | travel (kEUR) |  | E1 | Ground Control Centre Development
|  |  | sum (kEUR) |  |  |  | 0 | 0 | 0 | 127.5561 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 127.5561 |  |  | sum (kEUR) |  |  |  |  | 0 | 63.7781 | 63.7781 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 127.5561
[22 empty] | WP 620334 | CS: Niklas A: Confirmed OK
WP no: 620334 |  |  | hours |  |  | D: 720 |  | 620334 | Flight Dynamics SW | hours | [11 empty] | 360 | 360
Flight Dynamics SW |  |  | cost for hours (kEUR) |  |  |  | 0 | 0 | 0 | 0 | 0 | 71.7503 | 0 | 0 | 0 | 0 | 0 | 0 |  | 620334 | Flight Dynamics SW | cost for hours (kEUR) |  | E1 | Ground Control Centre Development |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35.8752 | 35.8752 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Verification v.s. ref. |  |  | external costs/procurement (kEUR) | [16 empty] | 620334 | Flight Dynamics SW | external costs/procurement (kEUR) |  | E1 | Ground Control Centre Development
data |  |  | travel (kEUR) | [16 empty] | 620334 | Flight Dynamics SW | travel (kEUR) |  | E1 | Ground Control Centre Development
|  |  | sum (kEUR) |  |  |  | 0 | 0 | 0 | 0 | 0 | 71.7503 | 0 | 0 | 0 | 0 | 0 | 0 | 71.7503 |  |  | sum (kEUR) |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35.8752 | 35.8752 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 71.7503
[22 empty] | WP 620520 | Niklas A: Confirmed OK
WP no: 620520 |  |  | hours |  |  | D: 440 |  | 620520 | OHB Support Centre | hours | [23 empty] | 220 | 220
OHB Support Centre |  |  | cost for hours (kEUR) |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 43.8474 | 0 | 0 | 0 | 0 | 0 |  | 620520 | OHB Support Centre | cost for hours (kEUR) |  | E1 | Ground Control Centre Development |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21.9237 | 21.9237 | 0 | 0 | 0
|  |  | external costs/procurement (kEUR) |  |  | D: 20 |  | 620520 | OHB Support Centre | external costs/procurement (kEUR) |  | E1 | Ground Control Centre Development | [20 empty] | 10 | 10
|  |  | travel (kEUR) | [16 empty] | 620520 | OHB Support Centre | travel (kEUR) |  | E1 | Ground Control Centre Development
|  |  | sum (kEUR) |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 63.8474 | 0 | 0 | 0 | 0 | 0 | 63.8474 |  |  | sum (kEUR) |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31.9237 | 31.9237 | 0 | 0 | 0 | 63.8474
[22 empty] | WP 630300 | CS: This training is for AI&T, correct? Niklas A: Split in two and moved to support CPDI EM & PFM activities
WP no: 630300 |  |  | hours |  |  | D: 80 |  | 630300 | RAMSES Training | hours | [8 empty] | 40 |  |  |  |  | 40
RAMSES Training |  |  | cost for hours (kEUR) |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 7.9723 | 0 | 0 | 0 | 0 | 0 |  | 630300 | RAMSES Training | cost for hours (kEUR) |  | E1 | Ground Control Centre Development |  | 0 | 0 | 0 | 0 | 3.9861 | 0 | 0 | 0 | 0 | 3.9861 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | external costs/procurement (kEUR) | [16 empty] | 630300 | RAMSES Training | external costs/procurement (kEUR) |  | E1 | Ground Control Centre Development
|  |  | travel (kEUR) | [16 empty] | 630300 | RAMSES Training | travel (kEUR) |  | E1 | Ground Control Centre Development
|  |  | sum (kEUR) |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 7.9723 | 0 | 0 | 0 | 0 | 0 | 7.9723 |  |  | sum (kEUR) |  |  |  |  | 0 | 0 | 0 | 0 | 3.9861 | 0 | 0 | 0 | 0 | 3.9861 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.9723
[22 empty] | WP 630300 | Niklas A: Overall duration OK, Profile of effort updated to reflect expected level of maintenance in relation to major activities and deliveries
WP no: 640110 |  |  | hours |  |  | D: 170; D: 250; D: 250; D/E: 250; E: 250; E: 250 |  | 640110 | RAMSES Maintenance | hours | [15 empty] | 125 | 125 | 125 | 125 | 56.6667 | 56.6667 | 125 | 125 | 125 | 125 | 125 | 125 | 56.6667
RAMSES Maintenance |  |  | cost for hours (kEUR) |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 16.941 | 24.9133 | 24.9133 | 24.9133 | 24.9133 | 24.9133 |  | 640110 | RAMSES Maintenance | cost for hours (kEUR) |  | E2 | Mission Operations |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12.4567 | 12.4567 | 12.4567 | 12.4567 | 5.647 | 5.647 | 12.4567 | 12.4567 | 12.4567 | 12.4567 | 12.4567 | 12.4567 | 5.647
|  |  | external costs/procurement (kEUR) | [16 empty] | 640110 | RAMSES Maintenance | external costs/procurement (kEUR) |  | E2 | Mission Operations
|  |  | travel (kEUR) | [16 empty] | 640110 | RAMSES Maintenance | travel (kEUR) |  | E2 | Mission Operations
|  |  | sum (kEUR) |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 16.941 | 24.9133 | 24.9133 | 24.9133 | 24.9133 | 24.9133 | 141.5076 |  |  | sum (kEUR) |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12.4567 | 12.4567 | 12.4567 | 12.4567 | 5.647 | 5.647 | 12.4567 | 12.4567 | 12.4567 | 12.4567 | 12.4567 | 12.4567 | 5.647 | 141.5076
[22 empty] | WP 720300 | CS: This training is for operators, correct? Niklas A: Confirmed OK
WP no: 720300 |  |  | hours |  |  | D: 80 |  | 720300 | RAMSES Training | hours | [23 empty] | 40 | 40
RAMSES Training |  |  | cost for hours (kEUR) |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.9723 | 0 | 0 | 0 |  | 720300 | RAMSES Training | cost for hours (kEUR) |  | E2 | Mission Operations |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.9861 | 3.9861 | 0 | 0 | 0
|  |  | externmal costs/procurement (kEUR) | [16 empty] | 720300 | RAMSES Training | external costs/procurement (kEUR) |  | E2 | Mission Operations
|  |  | travel (kEUR) | [16 empty] | 720300 | RAMSES Training | travel (kEUR) |  | E2 | Mission Operations
|  |  | sum (kEUR) |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.9723 | 0 | 0 | 0 | 7.9723 |  |  | sum (kEUR) |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.9861 | 3.9861 | 0 | 0 | 0 | 7.9723
Ground Segment
Ground Segment |  |  | hours |  |  |  | 0 | 0 | 1470 | 2750 | 1470 | 1945 | 690 | 250 | 330 | 250 | 250 | 250 |  |  | Ground Segment | hours |  |  |  |  | 0 | 640 | 1130 | 490 | 530 | 735 | 735 | 1095 | 1095 | 652.5 | 612.5 | 125 | 125 | 125 | 125 | 56.6667 | 56.6667 | 125 | 125 | 385 | 385 | 125 | 125 | 56.6667 | 9655
|  |  | cost for hours (kEUR) |  |  |  | 0 | 0 | 146.4902 | 274.0463 | 146.4902 | 193.8255 | 68.7607 | 24.9133 | 32.8856 | 24.9133 | 24.9133 | 24.9133 |  |  | Ground Segment | cost for hours (kEUR) |  |  |  |  | 0 | 63.7781 | 112.6081 | 48.8301 | 52.8162 | 73.2451 | 73.2451 | 109.1203 | 109.1203 | 65.0237 | 61.0376 | 12.4567 | 12.4567 | 12.4567 | 12.4567 | 5.647 | 5.647 | 12.4567 | 12.4567 | 38.3665 | 38.3665 | 12.4567 | 12.4567 | 5.647 | 962.1518
|  |  | external costs/procurement (kEUR) |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 |  |  | Ground Segment | external costs/procurement (kEUR) |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 10 | 0 | 0 | 0 | 20
|  |  | travel (kEUR) |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Ground Segment | travel (kEUR) |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | sum (kEUR) |  |  |  | 0 | 0 | 146.4902 | 274.0463 | 146.4902 | 193.8255 | 88.7607 | 24.9133 | 32.8856 | 24.9133 | 24.9133 | 24.9133 | 982.1518 |  |  | sum (kEUR) |  |  |  |  | 0 | 63.7781 | 112.6081 | 48.8301 | 52.8162 | 73.2451 | 73.2451 | 109.1203 | 109.1203 | 65.0237 | 61.0376 | 12.4567 | 12.4567 | 12.4567 | 12.4567 | 5.647 | 5.647 | 12.4567 | 12.4567 | 48.3665 | 48.3665 | 12.4567 | 12.4567 | 5.647 | 982.1518
1080.367
[22 empty] | WP 720110 | CS: Niklas A: Confirmed OK
WP no: 720110 |  |  | hours |  |  | D: 1900 |  | 720110 | Flight Operation Procedure Support | hours | [16 empty] | 633.3333 | 633.3333 | 633.3333
Flight Operation Procedure |  |  | cost for hours |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 189.3411 | 0 | 0 | 0 |  | 720110 | Flight Operation Procedure Support | cost for hours (kEUR) |  | E2 | Mission Operations |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 63.1137 | 63.1137 | 63.1137 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Support |  |  | external costs/procurement (kEUR) | [16 empty] | 720110 | Flight Operation Procedure Support | external costs/procurement (kEUR) |  | E2 | Mission Operations
|  |  | travel (kEUR) | [16 empty] | 720110 | Flight Operation Procedure Support | travel (kEUR) |  | E2 | Mission Operations
|  |  | sum (kEUR) |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 189.3411 | 0 | 0 | 0 | 189.3411 |  |  | sum (kEUR) |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 63.1137 | 63.1137 | 63.1137 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 189.3411
[22 empty] | WP 720110 | CS: Niklas A: Confirmed OK
WP no: 740,740321,740421 |  |  | hours |  |  | D/E: 3280; E: 3280; E: 3280 |  | 740000 | Operation Support | hours | [25 empty] | 3280 | 3280 | 3280
Operation Support |  |  | cost for hours (kEUR) |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 326.8625 | 326.8625 | 326.8625 |  | 740000 | Operation Support | cost for hours (kEUR) |  | E2 | Mission Operations |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 326.8625 | 326.8625 | 326.8625
|  |  | external costs/procurement (kEUR) | [16 empty] | 740000 | Operation Support | external costs/procurement (kEUR) |  | E2 | Mission Operations
|  |  | travel (kEUR) |  |  | D/E: 10; E: 10; E: 10 |  | 740000 | Operation Support | travel (kEUR) |  | E2 | Mission Operations | [22 empty] | 10 | 10 | 10
|  |  | sum (kEUR) | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 336.8625 | 336.8625 | 336.8625 | 1010.5876 |  |  | sum (kEUR) |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 336.8625 | 336.8625 | 336.8625 | 1010.5876
Operation Support
Operation Support |  |  | hours |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1900 | 3280 | 3280 | 3280 |  |  | Operation Support | hours |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 633.3333 | 633.3333 | 633.3333 | 0 | 0 | 0 | 0 | 0 | 0 | 3280 | 3280 | 3280 | 11740
|  |  | cost for hours (kEUR) |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 189.3411 | 326.8625 | 326.8625 | 326.8625 |  |  | Operation Support | cost for hours (kEUR) |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 63.1137 | 63.1137 | 63.1137 | 0 | 0 | 0 | 0 | 0 | 0 | 326.8625 | 326.8625 | 326.8625 | 1169.9287
|  |  | external costs/procurement (kEUR) |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Operation Support | external costs/procurement (kEUR) |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | travel (kEUR) |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 10 | 10 |  |  | Operation Support | travel (kEUR) |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 10 | 10 | 30
|  |  | sum (kEUR) |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 189.3411 | 336.8625 | 336.8625 | 336.8625 | 1199.9287 |  |  | sum (kEUR) |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 63.1137 | 63.1137 | 63.1137 | 0 | 0 | 0 | 0 | 0 | 0 | 336.8625 | 336.8625 | 336.8625 | 1199.9287
[19 empty] | 1319.9216 |  |  | TOTAL
TOTAL |  |  | hours |  |  |  | 2282 | 10591 | 13636 | 12059 | 12971 | 11525 | 7880 | 6205 | 5838 | 6212 | 4369 | 3955 |  | 97523 |  | hours |  |  |  |  | 840 | 2300 | 4117.5 | 4838 | 5269 | 6114 | 8389 | 7310 | 5720 | 5677.5 | 4895.5 | 2447 | 2637.3333 | 5091.3333 | 4023.3333 | 3141.6667 | 3141.6667 | 2377.5 | 2997.5 | 3118 | 2024.5 | 3730 | 3617.5 | 3549.1667 | 97367 | Payment Plan vs consumed costs
|  |  | cost for hours (kEUR) |  |  |  | 227.0445 | 1074.9196 | 1412.744 | 1221.2105 | 1312.0942 | 1142.5841 | 804.7597 | 637.8406 | 601.2679 | 638.5382 | 421.8665 | 399.4446 |  | 9894.3144 |  | cost for hours (kEUR) |  |  |  |  | 85.8351 | 232.3921 | 420.0683 | 491.8685 | 534.819 | 619.026 | 845.737 | 738.2112 | 579.7626 | 575.5273 | 497.5985 | 253.5976 | 272.5649 | 517.1139 | 410.6843 | 322.8234 | 322.8234 | 246.6717 | 308.4567 | 320.4649 | 204.406 | 374.3645 | 363.1536 | 356.3439 | 9894.3144 | Payment # | Milestone | Accumulated received in % of Price | TO + M |  | Consumed cost in % | Difference in %
|  |  | external costs/procurement (kEUR) |  |  |  | 0 | 542.625 | 1558.75 | 1714.325 | 1042.35 | 321.6 | 20 | 114 | 397.5 | 177.5 | 0 | 0 |  | 5888.65 |  | external costs/procurement (kEUR) |  |  |  |  | 0 | 0 | 0 | 0 | 155.0625 | 250.0625 | 545.65 | 798.15 | 1031.8125 | 1228.5125 | 720.8 | 217.6 | 10 | 170 | 52 | 0 | 0 | 0 | 114 | 407.5 | 187.5 | 0 | 0 | 0 | 5888.65 | 1 | Program Kick-Off (KO) | 20 | 0 | 2020-02-01 | 0 | 20
|  |  | travel (kEUR) |  |  |  | 15 | 52 | 37 | 37 | 37 | 29 | 25 | 18 | 53 | 67 | 13 | 10 |  | 393 |  | travel (kEUR) |  |  |  |  | 2 | 8 | 7.5 | 25 | 15 | 12.5 | 12.5 | 24.5 | 29.5 | 29.5 | 17 | 9 | 5 | 12.5 | 9 | 9 | 9 | 9 | 9 | 51.5 | 55.5 | 11.5 | 10 | 10 | 393 | 2 | GNC S/S PDR | 23 | 11 | 2021-01-01 | 12.2252 | 10.7748
|  |  | sum (kEUR) |  |  |  | 242.0445 | 1669.5446 | 3008.494 | 2972.5355 | 2391.4442 | 1493.1841 | 849.7597 | 769.8406 | 1051.7679 | 883.0382 | 434.8665 | 409.4446 |  | 16175.9644 |  | sum (kEUR) |  |  |  |  | 87.8351 | 240.3921 | 427.5683 | 516.8685 | 704.8815 | 881.5885 | 1403.887 | 1560.8612 | 1641.0751 | 1833.5398 | 1235.3985 | 480.1976 | 287.5649 | 699.6139 | 471.6843 | 331.8234 | 331.8234 | 255.6717 | 431.4567 | 779.4649 | 447.406 | 385.8645 | 373.1536 | 366.3439 | 16175.9644 | 3 | Propulsion S/S PDR | 26 | 15 | 2021-05-01 | 17.6752 | 8.3248
[19 empty] | 10% | 17793.5609 | [29 empty] | 10% | 17793.5609 | 4 | Delivery of EM units | 29 | 16 | 2021-06-01 | 26.354 | 2.646
[19 empty] | reserve | [7 empty] | 2020 |  |  |  | 2021 |  |  |  | 2022 |  |  |  | 2023 |  |  |  | 2024 |  |  |  | 2025 |  |  |  |  | 5 | GNC S/S CDR | 48 | 22 | 2021-12-01 | 36.0033 | 11.9967
[7 empty] | H1 - 2020 | H2-2020 | H1-2021 | H2-2021 | H1-2022 | H2-2022 | H1-2023 | H2-2023 | H1-2024 | H2-2024 | H1-2025 | H2-2025 |  | 2020-2025 | [6 empty] | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 |  | 6 | Propulsion S/S CDR | 54 | 24 | 2022-02-01 | 46.1485 | 7.8515
[52 empty] | 7 | GNC S/S SW CDR | 63 | 29 | 2022-07-01 | 65.1207 | -2.1207
[52 empty] | 8 | GNC S/S SW QR | 68 | 35 | 2023-01-01 | 69.867 | -1.867
[52 empty] | 9 | Propulsion S/S DBR | 73 | 35 | 2023-01-01 | 69.867 | 3.133
[5 empty] | Payment Plan vs consumed costs | [46 empty] | 10 | Completion of SAT PFM | 79 | 42 | 2023-08-01 | 77.108 | 1.892
[5 empty] | Payment # | Accumulated received in % of Price | Date | Consumed cost in % |  | Difference in % | [41 empty] | 11 | A&l | 83 | 47 | 2024-01-01 | 81.2106 | 1.7894
[5 empty] | 1 | 20 | 2020-02-01 |  | 0 | 20 | [41 empty] | 12 | Completion of SAT PFM | 90 | 54 | 2024-08-01 | 85.4585 | 4.5415
[5 empty] | 2 | 23 | 2021-01-01 |  | 11.8175 | 11.1825 | [41 empty] | 13 | Environmental Test | 93 | 57 | 2024-11-01 | 90.2771 | 2.7229
[5 empty] | 3 | 26 | 2021-05-01 |  | 24.2165 | 1.7835 | [41 empty] | 14 | Campaign | 97 | 63 | 2025-05-01 | 95.4284 | 1.5716
[5 empty] | 4 | 29 | 2021-06-01 |  | 27.3163 | 1.6837 | [41 empty] | 15 | Completion of the launch | 100 | 71 | 2026-01-01 | 100 | 0
[5 empty] | 5 | 48 | 2021-12-01 |  | 45.7296 | 2.2704
[5 empty] | 6 | 53 | 2022-02-01 |  | 51.2562 | 1.7438
[5 empty] | 7 | 62 | 2022-08-01 |  | 63.5762 | -1.5762
[5 empty] | 8 | 67 | 2023-01-01 |  | 72.8071 | -5.8071
[5 empty] | 9 | 72 | 2023-01-01 |  | 72.8071 | -0.80708
[5 empty] | 10 | 78 | 2023-08-01 |  | 78.8535 | -0.8535
[5 empty] | 11 | 82 | 2024-01-01 |  | 82.8195 | -0.81947
[5 empty] | 12 | 89 | 2024-08-01 |  | 90.2313 | -1.2313
[5 empty] | 13 | 92 | 2024-11-01 |  | 92.9608 | -0.96081
[5 empty] | 14 | 96 | 2025-05-01 |  | 96.5727 | -0.57269
[5 empty] | 15 | 100 | 2025-12-31 |  | 100 | 0
Procurement /Supplier Costs |  |  | (in kEUR)
Propulsion |  |  | NREC | REC
1) | Pressure Transducer
| 1 PFM PT |  |  | 20
| PFM Test Campaign |  | 14
| 1 Dummy |  | 1.6
| Project Office |  | 32
| EQSR light |  | 51
| Sum |  | 98.6 | 20 | 118.6 |  |  |  | 29.65 | 59.3 | 29.65
2) | Service Valve
| 3x (1 PFM+2 FM) SV |  |  | 29
| NREC Eng. |  | 17
| PFM Campaign |  | 1
| Ground Half Coupling |  |  | 22
| Sum |  | 18 | 51 | 69 |  |  |  | 17.25 | 34.5 | 17.25
3) | Harness
| PFM |  |  | 55
| EM |  | 19
| Sum |  | 19 | 55 | 74 |  |  |  | 19 |  | 55
4) | Thrusters
| 8x1N Thruster |  |  | 520
| 22N Thruster |  |  | 200
| Project Office |  |  | 100
| 1 N Mass Dummy |  | 40
| 22 N Mass Dummy |  | 10
| Progress Meetings |  | 218
| Sum |  | 268 | 820 | 1088 |  |  |  | 217.6 | 326.4 | 326.4 | 217.6
| Propellant |  |  | 105
| Fueling of Satellite |  |  | 250
| Sum |  |  | 355 | 355 | [9 empty] | 177.5 | 177.5
5) | Latch Valve
| 2 FM Valves |  |  | 70
| PFM Campaign |  | 10
| Sum |  | 10 | 70 | 80 |  |  |  |  | 40 | 40
6) | Propellant Tank
| 1 PFM tank |  |  | 475
| 1 SM Tank |  | 475
| EQSR meeting |  | 60
|  |  | 535 | 475 | 1010 |  |  | 252.5 | 252.5 | 252.5 | 252.5
GNC
1) | Magnetometer
| 2 (1 PFM+1 FM) Units |  |  | 98
| NREC standard |  | 27
| EM Unit |  | 22
| Mass Dummy |  | 3
| Sum |  | 52 | 98 | 150 |  |  | 37.5 | 75 | 37.5
2) | Magnetorquer
| 3 ( 1PFM+2FM) Units |  |  | 66
| NREC standard |  | 28
| EM Unit |  | 17
| Shock test |  | 5.5
| Mass Dummy |  | 6
| Sum |  | 56.5 | 66 | 122.5 |  |  | 30.625 | 61.25 | 30.625
3) | Sun Sensor
| 12xPFM Coss-R |  |  | 194
| Project Office |  | 43
| PFM Campaign |  | 19
| EQSR Light |  | 52
| EM x1(Coss-R) |  | 8
| Sum |  | 122 | 194 | 316 |  |  | 79 | 158 | 79
4) | Startracker
| 1PFM+1FM Startracker |  |  | 250
| EM |  | 54
| GSE Support |  | 50
| Sum |  | 104 | 250 | 354 |  |  | 54 | 125 | 175
5) | Harness
| PFM harness |  |  | 78
| EM harness |  | 33
| Sum |  | 33 | 78 | 111 |  |  | 33 |  | 78
6) | GNSS
| Redundant PFM |  |  | 351
| EM Unit |  | 45
| Dummy mass |  | 10
| GNC S/S AIT Assistance |  | 12
|  |  | 67 | 351 | 418 |  |  | 22.5 | 209 | 186.5
7) | Reaction Wheels
| 4 Wheels |  |  | 716
| EM Wheel |  | 51
| 4 Dummy Mass |  | 10
| GNC S/S AIT Assistance |  | 12
| Sum |  | 73 | 716 | 789 |  |  | 25.5 | 394.5 | 369
8) | IMU & Gyro modules
| 3 x IMU & Gyro modules |  |  | 24
| 1 EM IMU&Gyro module |  | 8
| 2 USB Evaluation kit |  | 2
|  |  | 10 | 24 | 34 |  |  | 8 |  | 36

## OHB OLD (hidden)
SEM
| FTE hours/ Year |  |  | 1650 | 825
Colour Code
WP per period of 6 months
Labour Hourly Rate
Mgm, PA, Mission Analysis, GNC S/S, Propulsion S/S, Sat STM&PFM AIT, Ground Segment, Preparation&Operation Support (Work Area) per period of 6 months
Sum of each Work Area or all Work Areas for the total contract period
Sum of each Work Area or all Work Areas for the total contract period with 10 %
Total sum per period of 6 months
Payment Plan Data
Procurement Plan/Supplier Costs
[8 empty] | H12020 | H22020 |  | H12021 | H22021 | H12022 | H22022 | H12023 | H22023 | H12024 | H22024 | H12025 | H22025
WP# | Descr | T8 Code | T8 Descr |  |  |  | Phase | A | B |  | B | C | C | D | D | D | D | D/E | E | E
Gross Hourly Rate in Euro in 2019 E.C. | [6 empty] | Project Management = |  |  |  | 123.2804 |  | Engineers= |  | 99.6532
|  |  |  | hours |  |  |  | 225 | 825 |  | 825 | 825 | 825 | 825 | 825 | 825 | 825 | 825 | 225 | 225
110200 | Management & Reporting | A1 | Management | cost for hours (kEUR) |  |  |  | 27.7381 | 101.7063 |  | 101.7063 | 101.7063 | 101.7063 | 101.7063 | 101.7063 | 101.7063 | 101.7063 | 101.7063 | 27.7381 | 27.7381 | 998.5709
110200 | Management & Reporting | A1 | Management | external costs/procurement (kEUR) | [16 empty] | 0
110200 | Management & Reporting | A1 | Management | travel (kEUR) |  |  |  | 5 | 5 |  | 5 | 5 | 5 | 5 | 10 | 3 | 3 | 3 | 3 |  | 52
|  |  |  | sum (kEUR) |  |  |  | 32.7381 | 106.7063 |  | 106.7063 | 106.7063 | 106.7063 | 106.7063 | 111.7063 | 104.7063 | 104.7063 | 104.7063 | 30.7381 | 27.7381 | 1050.5709
|  |  |  | by Q |  |  |  | 16.369 | 53.3531 |  | 53.3531 | 53.3531 | 53.3531 | 53.3531 | 55.8531 | 52.3531 | 52.3531 | 52.3531 | 15.369 | 13.869
|  |  |  | FTE |  |  |  | 0.27273 | 1 |  | 1
WP no: 130220 |  |  |  | hours |  |  |  |  | 220 |  | 220 | 220 | 220 | 220 | 300 | 300 | 300 | 330 | 425 | 200
130220 | S/W PA | A2 | Product Assurance | cost for hours (kEUR) |  |  |  | 0 | 21.9237 |  | 21.9237 | 21.9237 | 21.9237 | 21.9237 | 29.896 | 29.896 | 29.896 | 32.8856 | 42.3526 | 19.9306 | 294.4752
130220 | S/W PA | A2 | Product Assurance | external costs/procurement (kEUR)
130220 | S/W PA | A2 | Product Assurance | travel (kEUR)
|  |  |  | sum (kEUR) |  |  |  | 0 | 21.9237 |  | 21.9237 | 21.9237 | 21.9237 | 21.9237 | 29.896 | 29.896 | 29.896 | 32.8856 | 42.3526 | 19.9306 | 294.4752
WP no: 130210 |  |  |  | hours |  |  |  | 0 | 825 |  | 825 | 825 | 825 | 825 | 825 | 825 | 825 | 825
130210 | H/W and AIT PA | A2 | Product Assurance | cost for hours (kEUR) |  |  |  | 0 | 82.2139 |  | 82.2139 | 82.2139 | 82.2139 | 82.2139 | 82.2139 | 82.2139 | 82.2139 | 82.2139 | 0 | 0 | 739.9251
130210 | H/W and AIT PA | A2 | Product Assurance | external costs/procurement (kEUR) | [16 empty] | 0
130210 | H/W and AIT PA | A2 | Product Assurance | travel (kEUR) |  |  |  |  | 20 |  | 10 | 10 | 20 | 5 | [6 empty] | 65
|  |  |  | sum (kEUR) |  |  |  | 0 | 102.2139 |  | 92.2139 | 92.2139 | 102.2139 | 87.2139 | 82.2139 | 82.2139 | 82.2139 | 82.2139 | 0 | 0 | 804.9251
| PA Sum |  |  | hours |  |  |  | 0 | 1045 |  | 1045 | 1045 | 1045 | 1045 | 1125 | 1125 | 1125 | 1155 | 425 | 200
| PA Sum |  |  | cost for hours (kEUR) |  |  |  | 0 | 104.1376 |  | 104.1376 | 104.1376 | 104.1376 | 104.1376 | 112.1099 | 112.1099 | 112.1099 | 115.0995 | 42.3526 | 19.9306 | 1034.4004
| PA Sum |  |  | external costs/procurement (kUR) |  |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| PA Sum |  |  | travel (kEUR) |  |  |  | 0 | 20 |  | 10 | 10 | 20 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 65
| PA Sum |  |  | sum (kEUR) |  |  |  | 0 | 124.1376 |  | 114.1376 | 114.1376 | 124.1376 | 109.1376 | 112.1099 | 112.1099 | 112.1099 | 115.0995 | 42.3526 | 19.9306 | 1099.4004
| PA Sum |  |  | by Q |  |  |  | 0 | 62.0688 | 0 | 57.0688 | 57.0688 | 62.0688 | 54.5688 | 56.0549 | 56.0549 | 56.0549 | 57.5497 | 21.1763 | 9.9653 | 1209.3404
WP no: 210300 |  |  |  | hours |  |  |  | 2000 | 1000
210300 | Mission Analysis/ Design | A3 | (Project & Mission) Engineering | cost for hours (kEUR) |  |  |  | 199.3064 | 99.6532 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 298.9596
210300 | Mission Analysis/ Design | A3 | (Project & Mission) Engineering | external costs/procurement (kEUR) | [16 empty] | 0 |  | All tests cost need to be added
210300 | Mission Analysis/ Design | A3 | (Project & Mission) Engineering | travel (kEUR) |  |  |  | 10 | 5 | [11 empty] | 15 |  |  | Raw materials
|  |  |  | sum (kEUR) |  |  |  | 209.3064 | 104.6532 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 313.9596 |  |  | Test facilities
WP no: 450100 |  |  |  | hours |  |  |  |  | 970 | [13 empty] | Have 44 WP, cannot fill in the PSS.
450100 | GNC Req. & Eng. | B51 | AOCS / GNC - Engineering and SW | cost for hours (kEUR) |  |  |  | 0 | 96.6636 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 96.6636
450100 | GNC Req. & Eng. | B52 | AOCS / GNC - HW procurements | external costs/procurement (kEUR) | [16 empty] | 0 |  | Escalation rates?
450100 | GNC Req. & Eng. | B51 | AOCS / GNC - Engineering and SW | travel (kEUR) | [16 empty] | 0 |  |  | Not there yet, will need to be escalate to a formula in the contract
|  |  |  | sum (kEUR) |  |  |  | 0 | 96.6636 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 96.6636
Exchange rates
WP no: 450200 |  |  |  | hours |  |  |  |  | 993
450200 | GNC Prel. Design | B51 | AOCS / GNC - Engineering and SW | cost for hours (kEUR) |  |  |  | 0 | 98.9556 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 98.9556 |  | For now this is a calendar milestones payment plan, with specific milestones
450200 | GNC Prel. Design | B52 | AOCS / GNC - HW procurements | external costs/procurement (kEUR) | [16 empty] | 0
450200 | GNC Prel. Design | B51 | AOCS / GNC - Engineering and SW | travel (kEUR) | [16 empty] | 0 |  | 3-4 months is realistic to actually be paid after milestones (45 days)
|  |  |  | sum (kEUR) |  |  |  | 0 | 98.9556 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 98.9556
When we sign contact, we will do in more detail with the planning and costing
WP no: 450300 |  |  |  | hours | [6 empty] | 290 | 350
450300 | GNC System Eng. DD | B51 | AOCS / GNC - Engineering and SW | cost for hours (kEUR) |  |  |  | 0 | 0 |  | 28.8994 | 34.8786 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 63.7781 |  | WP | coming next week.
450300 | GNC System Eng. DD | B52 | AOCS / GNC - HW procurements | external costs/procurement (kEUR) | [16 empty] | 0
450300 | GNC System Eng. DD | B51 | AOCS / GNC - Engineering and SW | travel (kEUR) | [16 empty] | 0 |  | Reserves?
|  |  |  | sum(kEUR) |  |  |  | 0 | 0 |  | 28.8994 | 34.8786 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 63.7781 |  |  | Yes 10%
WP no: 450400 |  |  |  | hours |  |  |  |  | 500 |  | 2670 | [11 empty] | EGSE for prop, AOCS, Check-out system, front end connectors.
450400 | GNC DD | B51 | AOCS / GNC - Engineering and SW | cost for hours(kEUR) |  |  |  | 0 | 49.8266 |  | 266.0741 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 315.9007 |  |  | Other EGSE?
450400 | GNC DD | B52 | AOCS / GNC - HW procurements | external costs/procurement (kEUR) | [16 empty] | 0 |  |  | Needs to be included.
450400 | GNC DD | B51 | AOCS / GNC - Engineering and SW | travel (kEUR) | [16 empty] | 0
|  |  |  | sum (kEUR) |  |  |  | 0 | 49.8266 |  | 266.0741 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 315.9007
WP no: 450510 |  |  |  | hours | [6 empty] | 640
450510 | GNC SW Arch. Design | B51 | AOCS / GNC - Engineering and SW | cost for hours (kEUR) |  |  |  | 0 | 0 |  | 63.7781 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 63.7781
450510 | GNC SW Arch. Design | B52 | AOCS / GNC - HW procurements | external costs/procurement (kEUR) | [16 empty] | 0
450510 | GNC SW Arch. Design | B51 | AOCS / GNC - Engineering and SW | travel (kEUR) | [16 empty] | 0
|  |  |  | sum (kEUR) |  |  |  | 0 | 0 |  | 63.7781 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 63.7781
WP no: 450520 |  |  |  | hours | [6 empty] | 345 | 1671 | 1475 | 500
450520 | GNC SW DD and Unit Test | B51 | AOCS / GNC - Engineering and SW | cost for hours (kEUR) |  |  |  | 0 | 0 |  | 34.3804 | 166.5205 | 146.9885 | 49.8266 | 0 | 0 | 0 | 0 | 0 | 0 | 397.716
450520 | GNC SW DD and Unit Test | B52 | AOCS / GNC - HW procurements | external costs/procurement (kEUR) | [16 empty] | 0
450520 | GNC SW DD and Unit Test | B51 | AOCS / GNC - Engineering and SW | travel (kEUR) | [16 empty] | 0
|  |  |  | sum (kEUR) |  |  |  | 0 | 0 |  | 34.3804 | 166.5205 | 146.9885 | 49.8266 | 0 | 0 | 0 | 0 | 0 | 0 | 397.716
WP no: 450530 |  |  |  | hours | [9 empty] | 1548 | 640
450530 | GNC SW Scenario Tests | B51 | AOCS / GNC - Engineering and SW | cost for hours (kEUR) |  |  |  | 0 | 0 |  | 0 | 0 | 0 | 154.2632 | 63.7781 | 0 | 0 | 0 | 0 | 0 | 218.0412
450530 | GNC SW Scenario Tests | B52 | AOCS / GNC - HW procurements | external costs/procurement (kEUR) | [16 empty] | 0
450530 | GNC SW Scenario Tests | B51 | AOCS / GNC - Engineering and SW | travel (kEUR) | [16 empty] | 0
|  |  |  | sum (kEUR) |  |  |  | 0 | 0 |  | 0 | 0 | 0 | 154.2632 | 63.7781 | 0 | 0 | 0 | 0 | 0 | 218.0412
WP no: 450610 |  |  |  | hours |  |  |  |  | 2140 |  | 2140 | 500
450610 | GNC-level MIL/SIL Sim. | B51 | AOCS / GNC - Engineering and SW | cost for hours (kEUR) |  |  |  | 0 | 213.2579 |  | 213.2579 | 49.8266 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 476.3424
450610 | GNC-level MIL/SIL Sim. | B52 | AOCS / GNC - HW procurements | external costs/procurement (kEUR) | [16 empty] | 0
450610 | GNC-level MIL/SIL Sim. | B51 | AOCS / GNC - Engineering and SW | travel (kEUR) | [16 empty] | 0
|  |  |  | sum (kEUR) |  |  |  | 0 | 213.2579 |  | 213.2579 | 49.8266 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 476.3424
WP no: 450620 |  |  |  | hours |  |  |  |  | 300 |  | 600 | 600 | 444
450620 | GNC Inputs to PIL-S. | B51 | AOCS / GNC - Engineering and SW | cost for hours (kEUR) |  |  |  | 0 | 29.896 |  | 59.7919 | 59.7919 | 44.246 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 193.7258
| GNC Inputs to PIL-S. | B52 | AOCS / GNC - HW procurements | external costs/procurement (kEUR) | [16 empty] | 0
| GNC Inputs to PIL-S. | B51 | AOCS / GNC - Engineering and SW | travel (kEUR) | [16 empty] | 0
|  |  |  | sum (kEUR) |  |  |  | 0 | 29.896 |  | 59.7919 | 59.7919 | 44.246 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 193.7258
WP no: 450630 |  |  |  | hours |  |  |  |  | 500 |  | 600 | 100 | 0
450630 | GNC Inputs to HIL-sim. | B51 | AOCS / GNC - Engineering and SW | cost for hours (kEUR) |  |  |  | 0 | 49.8266 |  | 59.7919 | 9.9653 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 119.5839
450630 | GNC Inputs to HIL-sim. | B52 | AOCS / GNC - HW procurements | external costs/procurement (kEUR) | [16 empty] | 0
450630 | GNC Inputs to HIL-sim. | B51 | AOCS / GNC - Engineering and SW | travel (kEUR) | [16 empty] | 0
|  |  |  | sum (kEUR) |  |  |  | 0 | 49.8266 |  | 59.7919 | 9.9653 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 119.5839
WP no: 450700 |  |  |  | hours |  |  |  |  | 1238 |  | 1236 | 1238
450700 | GNC Equip. Proc. | B51 | AOCS / GNC - Engineering and SW | cost for hours (kEUR) |  |  |  | 0 | 123.3707 |  | 123.1714 | 123.3707 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 369.9127
450700 | GNC Equip. Proc. | B52 | AOCS / GNC - HW procurements | external costs/procurement (kEUR) |  |  |  |  | 290.125 |  | 1022.75 | 991.625 | [8 empty] | 2304.5
450700 | GNC Equip. Proc. | B51 | AOCS / GNC - Engineering and SW | travel (kEUR) |  |  |  |  | 10 |  | 10 | 10 | [8 empty] | 30
|  |  |  | sum (kEUR) |  |  |  | 0 | 423.4957 |  | 1155.9214 | 1124.9957 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2704.4127
WP no: 450800 |  |  |  | hours | [6 empty] | 500 | 1200 | 310
450800 | GNC Verification | B51 | AOCS / GNC - Engineering and SW | cost for hours (kEUR) |  |  |  | 0 | 0 |  | 49.8266 | 119.5839 | 30.8925 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200.303
450800 | GNC Verification | B52 | AOCS / GNC - HW procurements | external costs/procurement (kEUR) | [16 empty] | 0
450800 | GNC Verification | B51 | AOCS / GNC - Engineering and SW | travel (kEUR) | [16 empty] | 0
|  |  |  | sum (kEUR) |  |  |  | 0 | 0 |  | 49.8266 | 119.5839 | 30.8925 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200.303
WP no: 450900 |  |  |  | hours | [9 empty] | 669 | 1100 | 1100
450900 | GNC AIV Support | B51 | AOCS / GNC - Engineering and SW | cost for hours (kEUR) |  |  |  | 0 | 0 |  | 0 | 0 | 0 | 66.668 | 109.6185 | 109.6185 | 0 | 0 | 0 | 0 | 285.9051
450900 | GNC AIV Support | B52 | AOCS / GNC - HW procurements | external costs/procurement (kEUR) | 48 | [15 empty] | 0
450900 | GNC AIV Support | B51 | AOCS / GNC - Engineering and SW | travel (kEUR) | [16 empty] | 0
|  |  |  | sum ( kEUR) |  |  |  | 0 | 0 |  | 0 | 0 | 0 | 66.668 | 109.6185 | 109.6185 | 0 | 0 | 0 | 0 | 285.9051
|  |  |  | hours |  |  |  | 0 | 6641 |  | 9021 | 5659 | 2229 | 2717 | 1740 | 1100 | 0 | 0 | 0 | 0
| GNC S/S |  |  | cost for hours (kEUR) |  |  |  | 0 | 661.797 |  | 898.9716 | 563.9375 | 222.127 | 270.7578 | 173.3966 | 109.6185 | 0 | 0 | 0 | 0 | 2900.6061
| GNC S/S |  |  | external costs/procurement cost (kEUR) |  |  |  | 0 | 290.125 |  | 1022.75 | 991.625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2304.5
| GNC S/S |  |  | travle (kEUR) |  |  |  | 0 | 10 |  | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30
| GNC S/S |  |  | sum (kEUR) |  |  |  | 0 | 961.922 |  | 1931.7216 | 1565.5625 | 222.127 | 270.7578 | 173.3966 | 109.6185 | 0 | 0 | 0 | 0 | 5235.1061
11410.9035
WP no: 470100 |  |  |  | hours |  |  |  |  | 480 |  | 360 | 360
Propulsion S/S Def. | Propulsion S/S Def. | B61 | Propulsion - Engineering | cost for hours (kEUR) |  |  |  | 0 | 47.8335 |  | 35.8752 | 35.8752 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 119.5839
| Propulsion S/S Def. | B62 | Propulsion - HW procurements | external costs/procurement (kEUR) | [16 empty] | 0
| Propulsion S/S Def. | B61 | Propulsion - Engineering | travel (kEUR) | [16 empty] | 0
|  |  |  | sum (kEUR) |  |  |  | 0 | 47.8335 |  | 35.8752 | 35.8752 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 119.5839
WP no: 470210 |  |  |  | hours | [6 empty] | 300 | 180
Propulsion Design | Propulsion Design Consolidation & Analysis | B61 | Propulsion - Engineering | cost for hours (kEUR) |  |  |  | 0 | 0 |  | 29.896 | 17.9376 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47.8335
Consolidation &Analysis | Propulsion Design Consolidation & Analysis | B62 | Propulsion - HW procurements | external costs/procurement (kEUR) | [16 empty] | 0
| Propulsion Design Consolidation & Analysis | B61 | Propulsion - Engineering | travel (kEUR) | [16 empty] | 0
|  |  |  | sum (kEUR) |  |  |  | 0 | 0 |  | 29.896 | 17.9376 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47.8335
WP no: 470220 |  |  |  | hours | [7 empty] | 120 | 120
Electrical I/F and | Electrical I/F and Engineering Model Design | B61 | Propulsion - Engineering | cost for hours (kEUR) |  |  |  | 0 | 0 |  | 0 | 11.9584 | 11.9584 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23.9168
Engineering Model Design | Electrical I/F and Engineering Model Design | B62 | Propulsion - HW procurements | external costs/procurement (kEUR) | [16 empty] | 0
| Electrical I/F and Engineering Model Design | B61 | Propulsion - Engineering | travel ( kEUR) | [16 empty] | 0
|  |  |  | sum (kEUR) |  |  |  | 0 | 0 |  | 0 | 11.9584 | 11.9584 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23.9168
WP no: 470230 |  |  |  | hours | [6 empty] | 480 | 240
Performance and Analysis | Performance and Analysis | B61 | Propulsion - Engineering | cost for hours (kEUR) |  |  |  | 0 | 0 |  | 47.8335 | 23.9168 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 71.7503
| Performance and Analysis | B62 | Propulsion - HW procurements | external costs/procurement (kEUR) | [16 empty] | 0
| Performance and Analysis | B61 | Propulsion - Engineering | travel (kEUR) | [16 empty] | 0
|  |  |  | sum (kEUR) |  |  |  | 0 | 0 |  | 47.8335 | 23.9168 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 71.7503
WP no: 470300 |  |  |  | hours | [8 empty] | 1560
470300 | STM Design, manufact. And testing | B61 | Propulsion - Engineering | cost for hours (kEUR) |  |  |  | 0 | 0 |  | 0 | 0 | 155.459 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 155.459
470300 | STM Design, manufact. And testing | B62 | Propulsion - HW procurements | external costs/procurement (kEUR) | [8 empty] | 105 | [7 empty] | 105
470300 | STM Design, manufact. And testing | B61 | Propulsion - Engineering | travel (kEUR) | [16 empty] | 0
|  |  |  | sum (kEUR) |  |  |  | 0 | 0 |  | 0 | 0 | 260.459 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 260.459
WP no: 470410 |  |  |  | hours | [8 empty] | 240
PFM Procedures, Tooling, | PFM Procedures, Tooling, | B61 | Propulsion - Engineering | cost for hours (kEUR) |  |  |  | 0 | 0 |  | 0 | 0 | 23.9168 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23.9168
Fixture, MGSE Design & | Fixture, MGSE Design & | B62 | Propulsion - HW procurements | external costs/procurement (kEUR) | [8 empty] | 10 | [7 empty] | 10
Manufacture | Manufacture | B61 | Propulsion - Engineering | travel (kEUR) | [16 empty] | 0
|  |  |  | sum (kEUR) |  |  |  | 0 | 0 |  | 0 | 0 | 33.9168 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33.9168
WP no: 470420 |  |  |  | hours | [8 empty] | 300
EM and EGSE | EM and EGSE | B61 | Propulsion - Engineering | cost for hours (kEUR) |  |  |  | 0 | 0 |  | 0 | 0 | 29.896 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29.896
| EM and EGSE | B62 | Propulsion - HW procurements | external costs/procurement (kEUR) | [8 empty] | 10 | [7 empty] | 10
| EM and EGSE | B61 | Propulsion - Engineering | travel (kEUR) | [16 empty] | 0
|  |  |  | sum (kEUR) |  |  |  | 0 | 0 |  | 0 | 0 | 39.896 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39.896
WP no: 470430 |  |  |  | hours | [8 empty] | 480 | 480
PFM AI | PFM AI | B61 | Propulsion - Engineering | cost for hours (kEUR) |  |  |  | 0 | 0 |  | 0 | 0 | 47.8335 | 47.8335 | 0 | 0 | 0 | 0 | 0 | 0 | 95.6671
PFM AI | PFM AI | B62 | Propulsion - HW procurements | external costs/procurement (kEUR) | [16 empty] | 0
PFM AI | PFM AI | B61 | Propulsion - Engineering | travel (kEUR) | [16 empty] | 0
|  |  |  | sum (kEUR) |  |  |  | 0 | 0 |  | 0 | 0 | 47.8335 | 47.8335 | 0 | 0 | 0 | 0 | 0 | 0 | 95.6671
WP no: 470510 |  |  |  | hours | [8 empty] | 180
S/S Verification and Test Plan | S/S Verification and Test Plan | B61 | Propulsion - Engineering | cost for hours (kEUR) |  |  |  | 0 | 0 |  | 0 | 0 | 17.9376 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17.9376
Plan | S/S Verification and Test Plan | B62 | Propulsion - HW procurements | external costs/procurement (kEUR) | [16 empty] | 0
| S/S Verification and Test Plan | B61 | Propulsion - Engineering | travel (kEUR) | [16 empty] | 0
|  |  |  | sum (kEUR) |  |  |  | 0 | 0 |  | 0 | 0 | 17.9376 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17.9376
WP no: 470520 |  |  |  | hours | [8 empty] | 240
GSE Design and Manuf. | GSE Design and Manuf. | B61 | Propulsion - Engineering | cost for hours (kEUR) |  |  |  | 0 | 0 |  |  | 0 | 23.9168 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23.9168
| GSE Design and Manuf. | B62 | Propulsion - HW procurements | external costs/procurement (kEUR) | [8 empty] | 10 | [7 empty] | 10
| GSE Design and Manuf. | B61 | Propulsion - Engineering | travel (kEUR) | [16 empty] | 0
|  |  |  | sum (kEUR) |  |  |  | 0 | 0 |  |  | 0 | 33.9168 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33.9168
WP no: 470530 |  |  |  | hours | [9 empty] | 168
PFM Testing | PFM Testing | B61 | Propulsion - Engineering | cost for hours |  |  |  | 0 | 0 |  | 0 | 0 | 0 | 16.7417 | 0 | 0 | 0 | 0 | 0 | 0 | 16.7417
| PFM Testing | B62 | Propulsion - HW procurements | external costs/procurement (kEUR) | [16 empty] | 0
| PFM Testing | B61 | Propulsion - Engineering | travel (kEUR) | [16 empty] | 0
|  |  |  | sum (kEUR) |  |  |  | 0 | 0 |  | 0 | 0 | 0 | 16.7417 | 0 | 0 | 0 | 0 | 0 | 0 | 16.7417
WP no: 472540 |  |  |  | hours | [11 empty] | 180
Support to Sat AIT | Support to Sat AIT | B61 | Propulsion - Engineering | cost for hours |  |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 17.9376 | 0 | 0 | 0 | 0 | 17.9376
| Support to Sat AIT | B62 | Propulsion - HW procurements | external costs/procurement (kEUR) | [16 empty] | 0
| Support to Sat AIT | B61 | Propulsion - Engineering | travel (kEUR) | [16 empty] | 0
|  |  |  | sum (kEUR) |  |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 17.9376 | 0 | 0 | 0 | 0 | 17.9376
WP no: 470550 |  |  |  | hours | [8 empty] | 540 | 540
470550 | PFM Sub assembly manuf. and test incl. Piping | B61 | Propulsion - Engineering | cost for hours |  |  |  | 0 | 0 |  | 0 | 0 | 53.8127 | 53.8127 | 0 | 0 | 0 | 0 | 0 | 0 | 107.6255
470550 | PFM Sub assembly manuf. and test incl. Piping | B62 | Propulsion - HW procurements | external costs/procurement (kEUR) | [8 empty] | 118 | [7 empty] | 118
470550 | PFM Sub assembly manuf. and test incl. Piping | B61 | Propulsion - Engineering | travel (kEUR) | [16 empty] | 0
|  |  |  | sum (kEUR) |  |  |  | 0 | 0 |  | 0 | 0 | 171.8127 | 53.8127 | 0 | 0 | 0 | 0 | 0 | 0 | 225.6255
WP no: 470560 |  |  |  | hours |  |  |  |  | 600 |  | 480 | 480 | 550 | 50
Equipment Procurement | Equipment Procurement | B61 | Propulsion - Engineering | cost for hours (kEUR) |  |  |  | 0 | 59.7919 |  | 47.8335 | 47.8335 | 54.8093 | 4.9827 | 0 | 0 | 0 | 0 | 0 | 0 | 215.2509
| Equipment Procurement | B62 | Propulsion - HW procurements | external costs/procurement (kEUR) |  |  |  |  | 252.5 |  | 536 | 712.7 | 720.8 | 217.6 | [6 empty] | 2439.6
| Equipment Procurement | B61 | Propulsion - Engineering | travel (kEUR) |  |  |  |  | 12 |  | 12 | 12 | 12 | 4 | [6 empty] | 52
|  |  |  | sum (kEUR) |  |  |  | 0 | 324.2919 |  | 595.8335 | 772.5335 | 787.6093 | 226.5827 | 0 | 0 | 0 | 0 | 0 | 0 | 2706.8509
Propulsion S/S |  |  |  | hours |  |  |  | 0 | 1080 |  | 1620 | 1380 | 4210 | 1238 | 0 | 180 | 0 | 0 | 0 | 0
|  |  |  | cost for hours (kEUR) |  |  |  | 0 | 107.6255 |  | 161.4382 | 137.5214 | 419.54 | 123.3707 | 0 | 17.9376 | 0 | 0 | 0 | 0 | 967.4334
|  |  |  | external costs/procurement (kEUR) |  |  |  | 0 | 252.5 |  | 536 | 712.7 | 973.8 | 217.6 | 0 | 0 | 0 | 0 | 0 | 0 | 2692.6
|  |  |  | travel (kEUR) |  |  |  | 0 | 12 |  | 12 | 12 | 12 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 52
|  |  |  | sum (kEUR) |  |  |  | 0 | 372.1255 |  | 709.4382 | 862.2214 | 1405.34 | 344.9707 | 0 | 17.9376 | 0 | 0 | 0 | 0 | 3712.0334
|  |  |  | Manpower |  |  |  | 0 | 119.6255 | 0 | 173.4382 | 149.5214 | 431.54 | 127.3707 | 0 | 17.9376 |  |  |  |  | 8034.9312
|  |  |  | FTE |  |  |  | 0 | 1.3091 |  | 1.9636 | 1.6727 | 5.103
WP no: 510100 |  |  |  | hours | [7 empty] | 400 | 270
510100 | Acquisition of EGSE | A5 | (System level) Assembly, Integration and Testing,Verification | cost for hours (kEUR) |  |  |  | 0 | 0 |  | 0 | 39.8613 | 26.9064 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 66.7677
510100 | Acquisition of EGSE | A6 | Ground Segment Equipment | external costs/procurement(kEUR) | [7 empty] | 10 | [8 empty] | 10
510100 | Acquisition of EGSE | A5 | (System level) Assembly, Integration and Testing,Verification | travel (kEUR) | [16 empty] | 0
|  |  |  | sum (kEUR) |  |  |  | 0 | 0 |  | 0 | 49.8613 | 26.9064 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 76.7677
WP no: 520200 |  |  |  | hours | [8 empty] | 1862
520200 | Sat STM A&I | A5 | (System level) Assembly, Integration and Testing,Verification | cost for hours (kEUR) |  |  |  | 0 | 0 |  | 0 | 0 | 185.5543 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 185.5543
520200 | Sat STM A&I |  | #N/A | external costs/procurement (kEUR) | [16 empty] | 0
520200 | Sat STM A&I |  | #N/A | travel (kEUR) | [16 empty] | 0
|  |  |  | sum (kEUR) |  |  |  | 0 | 0 |  | 0 | 0 | 185.5543 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 185.5543
Wp no:490440 |  |  |  | hours | [8 empty] | 1060
490440 | Sat STM Environmental testing | B71 | Structure - Engineering | cost for hours (kEUR) |  |  |  | 0 | 0 |  | 0 | 0 | 105.6324 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 105.6324
490440 | Sat STM Environmental testing | B72 | Structure - HW | external costs/procurement (kEUR) | [8 empty] | 68.55 | [7 empty] | 68.55
490440 | Sat STM Environmental testing | B71 | Structure - Engineering | travel (kEUR) | [16 empty] | 0
|  |  |  | sum (kEUR) |  |  |  | 0 | 0 |  | 0 | 0 | 174.1824 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 174.1824
WP no: 550100 |  |  |  | hours | [9 empty] | 3500 | 3500 | 1835
550100 | Sat PFM A&I | A5 | (System level) Assembly, Integration and Testing,Verification | cost for hours (kEUR) |  |  |  | 0 | 0 |  | 0 | 0 | 0 | 348.7863 | 348.7863 | 182.8636 | 0 | 0 | 0 | 0 | 880.4361
550100 | Sat PFM A&I | A5 | (System level) Assembly, Integration and Testing,Verification | external costs/procurement (kEUR) | [9 empty] | 104 | [6 empty] | 104
550100 | Sat PFM A&I | A5 | (System level) Assembly, Integration and Testing,Verification | travel (kEUR) | [9 empty] | 15 | 15 | 15 |  |  |  |  | 45
|  |  |  | sum (kEUR) |  |  |  | 0 | 0 |  | 0 | 0 | 0 | 467.7863 | 363.7863 | 197.8636 | 0 | 0 | 0 | 0 | 1029.4361
WP no: 550200 |  |  |  | hours | [11 empty] | 890 | 215
550200 | PFM Environmental Test Camp. | A5 | (System level) Assembly, Integration and Testing,Verification | cost for hours (kEUR) |  |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 88.6914 | 21.4254 | 0 | 0 | 0 | 110.1168
550200 | PFM Environmental Test Camp. | A5 | (System level) Assembly, Integration and Testing,Verification | external costs/procurement (kEUR) | [11 empty] | 114 |  |  |  |  | 114
550200 | PFM Environmental Test Camp. | A5 | (System level) Assembly, Integration and Testing,Verification | travel (kEUR) | [16 empty] | 0
|  |  |  | sum (kEUR) |  |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 202.6914 | 21.4254 | 0 | 0 | 0 | 224.1168
WP no: 730100,730200 |  |  |  | hours | [12 empty] | 1443 | 702
730000 | Phase E Launch Campaign | E2 | Mission Operations | cost for hours(kEUR) |  |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 143.7996 | 69.9566 | 0 | 0 | 213.7561
730000 | Phase E Launch Campaign | E5 | Ground Segment - Procurement | external costs/procurement (kEUR) | [12 empty] | 397.5 | 177.5 |  |  | 575
730000 | Phase E Launch Campaign | E2 | Mission Operations | travel (kEUR) | [12 empty] | 50 | 54 |  |  | 104
|  |  |  | sum (kEUR) |  |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 591.2996 | 301.4566 | 0 | 0 | 892.7561
Sat STM and PFM AIT |  |  |  | hours |  |  |  | 0 | 0 |  | 0 | 400 | 3192 | 3500 | 3500 | 2725 | 1658 | 702 | 0 | 0
|  |  |  | cost for hours (kEUR) |  |  |  | 0 | 0 |  | 0 | 39.8613 | 318.0931 | 348.7863 | 348.7863 | 271.555 | 165.225 | 69.9566 | 0 | 0 | 1562.2634
|  |  |  | external costs/procurement (kEUR) |  |  |  | 0 | 0 |  | 0 | 10 | 68.55 | 104 | 0 | 114 | 397.5 | 177.5 | 0 | 0 | 871.55
|  |  |  | travel (kEUR) |  |  |  | 0 | 0 |  | 0 | 0 | 0 | 15 | 15 | 15 | 50 | 54 | 0 | 0 | 149
|  |  |  | sum (kEUR) |  |  |  | 0 | 0 |  | 0 | 49.8613 | 386.6431 | 467.7863 | 363.7863 | 400.555 | 612.725 | 301.4566 | 0 | 0 | 2582.8134
5597.7452
WP no: 620220 |  |  |  | hours | [6 empty] | 1470 | 1470 | 1470 | 1225
620220 | RAMSES Customization | E1 | Ground Control Centre Development | cost for hours (kEUR) |  |  |  | 0 | 0 |  | 146.4902 | 146.4902 | 146.4902 | 122.0752 | 0 | 0 | 0 | 0 | 0 | 0 | 561.5459
620220 | RAMSES Customization |  | #N/A | external costs/procurement (kEUR) | [16 empty] | 0
620220 | RAMSES Customization | E1 | Ground Control Centre Development | travel (kEUR) | [16 empty] | 0
|  |  |  | sum (kEUR) |  |  |  | 0 | 0 |  | 146.4902 | 146.4902 | 146.4902 | 122.0752 | 0 | 0 | 0 | 0 | 0 | 0 | 561.5459
0
WP no: 620230 |  |  |  | hours | [7 empty] | 1280
620230 | Mission TM/TC Database conversion | E1 | Ground Control Centre Development | cost for hours (kEUR) |  |  |  | 0 | 0 |  | 0 | 127.5561 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 127.5561
620230 | Mission TM/TC Database conversion |  | #N/A | external costs/procurement (kEUR) | [16 empty] | 0
620230 | Mission TM/TC Database conversion | E1 | Ground Control Centre Development | travel (kEUR) | [16 empty] | 0
|  |  |  | sum (kEUR) |  |  |  | 0 | 0 |  | 0 | 127.5561 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 127.5561
WP no: 620334 |  |  |  | hours | [9 empty] | 720
620334 | Flight Dynamics SW Verification v.s. ref. data | E1 | Ground Control Centre Development | cost for hours (kEUR) |  |  |  | 0 | 0 |  | 0 | 0 | 0 | 71.7503 | 0 | 0 | 0 | 0 | 0 | 0 | 71.7503
620334 | Flight Dynamics SW Verification v.s. ref. data | E1 | Ground Control Centre Development | external costs/procurement (kEUR) | [16 empty] | 0
620334 | Flight Dynamics SW Verification v.s. ref. data | E1 | Ground Control Centre Development | travel (kEUR) | [16 empty] | 0
|  |  |  | sum (kEUR) |  |  |  | 0 | 0 |  | 0 | 0 | 0 | 71.7503 | 0 | 0 | 0 | 0 | 0 | 0 | 71.7503
WP no: 620520 |  |  |  | hours | [10 empty] | 440
620520 | OHB Support Centre | E1 | Ground Control Centre Development | cost for hours (kEUR) |  |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 43.8474 | 0 | 0 | 0 | 0 | 0 | 43.8474
620520 | OHB Support Centre | E1 | Ground Control Centre Development | external costs/procurement (kEUR) | [10 empty] | 20 | [5 empty] | 20
620520 | OHB Support Centre | E1 | Ground Control Centre Development | travel (kEUR) | [16 empty] | 0
|  |  |  | sum (kEUR) |  |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 63.8474 | 0 | 0 | 0 | 0 | 0 | 63.8474
WP no: 630300 |  |  |  | hours | [10 empty] | 80
630300 | RAMSES Training | E1 | Ground Control Centre Development | cost for hours (kEUR) |  |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 7.9723 | 0 | 0 | 0 | 0 | 0 | 7.9723
630300 | RAMSES Training |  | #N/A | external costs/procurement (kEUR) | [16 empty] | 0
630300 | RAMSES Training | E1 | Ground Control Centre Development | travel (kEUR) | [16 empty] | 0
|  |  |  | sum (kEUR) |  |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 7.9723 | 0 | 0 | 0 | 0 | 0 | 7.9723
WP no: 640110 |  |  |  | hours | [10 empty] | 170 | 250 | 250 | 250 | 250 | 250
640110 | RAMSES Maintenance | E2 | Mission Operations | cost for hours (kEUR) |  |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 16.941 | 24.9133 | 24.9133 | 24.9133 | 24.9133 | 24.9133 | 141.5076
| RAMSES Maintenance |  | #N/A | external costs/procurement (kEUR) | [16 empty] | 0
| RAMSES Maintenance | E2 | Mission Operations | travel (kEUR) | [16 empty] | 0
|  |  |  | sum (kEUR) |  |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 16.941 | 24.9133 | 24.9133 | 24.9133 | 24.9133 | 24.9133 | 141.5076
WP no: 720300 |  |  |  | hours | [12 empty] | 80
720300 | RAMSES Training | E2 | Mission Operations | cost for hours (kEUR) |  |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 7.9723 | 0 | 0 | 0 | 7.9723
720300 | RAMSES Training |  | #N/A | externmal costs/procurement (kEUR) | [16 empty] | 0
720300 | RAMSES Training | E2 | Mission Operations | travel (kEUR) | [16 empty] | 0
|  |  |  | sum (kEUR) |  |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 7.9723 | 0 | 0 | 0 | 7.9723
| Ground Segment |  |  | hours |  |  |  | 0 | 0 |  | 1470 | 2750 | 1470 | 1945 | 690 | 250 | 330 | 250 | 250 | 250
| Ground Segment |  |  | cost for hours (kEUR) |  |  |  | 0 | 0 |  | 146.4902 | 274.0463 | 146.4902 | 193.8255 | 68.7607 | 24.9133 | 32.8856 | 24.9133 | 24.9133 | 24.9133 | 962.1518
| Ground Segment |  |  | external costs/procurement (kEUR) |  |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 20
| Ground Segment |  |  | travel (kEUR) |  |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Ground Segment |  |  | sum (kEUR) |  |  |  | 0 | 0 |  | 146.4902 | 274.0463 | 146.4902 | 193.8255 | 88.7607 | 24.9133 | 32.8856 | 24.9133 | 24.9133 | 24.9133 | 982.1518
1543.0335
WP no: 720110 |  |  |  | hours | [12 empty] | 1900
720110 | Flight Operation Procedure Support | E2 | Mission Operations | cost for hours |  |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 189.3411 | 0 | 0 | 0 | 189.3411
720110 | Flight Operation Procedure Support |  | #N/A | external costs/procurement (kEUR) | [16 empty] | 0
720110 | Flight Operation Procedure Support | E2 | Mission Operations | travel (kEUR) | [16 empty] | 0
|  |  |  | sum (kEUR) |  |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 189.3411 | 0 | 0 | 0 | 189.3411
WP no: 740,740321,740421 |  |  |  | hours | [13 empty] | 3280 | 3280 | 3280
740000 | Operation Support | E2 | Mission Operations | cost for hours (kEUR) |  |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 326.8625 | 326.8625 | 326.8625 | 980.5876
740000 | Operation Support |  | #N/A | external costs/procurement (kEUR) | [16 empty] | 0
740000 | Operation Support | E2 | Mission Operations | travel (kEUR) | [13 empty] | 10 | 10 | 10 | 30
|  |  |  | sum (kEUR) | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 336.8625 | 336.8625 | 336.8625 | 1010.5876
| Operation Support |  |  | hours |  |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 1900 | 3280 | 3280 | 3280 | 11740
| Operation Support |  |  | cost for hours (kEUR) |  |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 189.3411 | 326.8625 | 326.8625 | 326.8625 | 1169.9287
| Operation Support |  |  | external costs/procurement (kEUR) |  |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Operation Support |  |  | travel (kEUR) |  |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 10 | 10 | 30
| Operation Support |  |  | sum (kEUR) |  |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 189.3411 | 336.8625 | 336.8625 | 336.8625 | 1199.9287
2431.568
TOTAL |  |  |  | hours |  |  |  | 2282 | 10591 |  | 13636 | 12059 | 12971 | 11525 | 7880 | 6205 | 5838 | 6212 | 4369 | 3955 | 97523 | 97523
|  |  |  | cost for hours (kEUR) |  |  |  | 227.0445 | 1074.9196 |  | 1412.744 | 1221.2105 | 1312.0942 | 1142.5841 | 804.7597 | 637.8406 | 601.2679 | 638.5382 | 421.8665 | 399.4446 | 9894.3144 | 9894.3144
|  |  |  | external costs/procurement (kEUR) |  |  |  | 0 | 542.625 |  | 1558.75 | 1714.325 | 1042.35 | 321.6 | 20 | 114 | 397.5 | 177.5 | 0 | 0 | 5888.65 | 5888.65
|  |  |  | travel (kEUR) |  |  |  | 15 | 52 |  | 37 | 37 | 37 | 29 | 25 | 18 | 53 | 67 | 13 | 10 | 393 | 393
|  |  |  | sum (kEUR) |  |  |  | 242.0445 | 1669.5446 |  | 3008.494 | 2972.5355 | 2391.4442 | 1493.1841 | 849.7597 | 769.8406 | 1051.7679 | 883.0382 | 434.8665 | 409.4446 | 16175.9644 | 16175.9644
[21 empty] | 0.1 | 17793.5609 | 30227.5218
reserve
[8 empty] | H1 - 2020 | H2-2020 |  | H1-2021 | H2-2021 | H1-2022 | H2-2022 | H1-2023 | H2-2023 | H1-2024 | H2-2024 | H1-2025 | H2-2025 |  | 2020-2025
| HOURS / H |  |  | FTE |  |  |  | 2.7661 | 12.8376 | 0 | 16.5285 | 14.617 | 15.7224 | 13.9697 | 9.5515 | 7.5212 | 7.0764 | 7.5297 | 5.2958 | 4.7939
|  |  |  | Ground Segment |  |  |  | 0 | 0 | 0 | 0.14649 | 0.27405 | 0.14649 | 0.19383 | 0.088761 | 0.024913 | 0.22223 | 0.36178 | 0.36178 | 0.36178
1911.5891
Payment Plan vs consumed costs
[6 empty] | Payment # | Accumulated received in % of Price | Date | Consumed cost in % |  |  | Difference in %
[6 empty] | 1 | 20 | 43862 |  |  | 0 | 20
[6 empty] | 2 | 23 | 44197 |  |  | 11.8175 | 11.1825
[6 empty] | 3 | 26 | 44317 |  |  | 24.2165 | 1.7835
[6 empty] | 4 | 29 | 44348 |  |  | 27.3163 | 1.6837
[6 empty] | 5 | 48 | 44531 |  |  | 45.7296 | 2.2704
[6 empty] | 6 | 53 | 44593 |  |  | 51.2562 | 1.7438
[6 empty] | 7 | 62 | 44774 |  |  | 63.5762 | -1.5762
[6 empty] | 8 | 67 | 44927 |  |  | 72.8071 | -5.8071
[6 empty] | 9 | 72 | 44927 |  |  | 72.8071 | -0.80708
[6 empty] | 10 | 78 | 45139 |  |  | 78.8535 | -0.8535
[6 empty] | 11 | 82 | 45292 |  |  | 82.8195 | -0.81947
[6 empty] | 12 | 89 | 45505 |  |  | 90.2313 | -1.2313
[6 empty] | 13 | 92 | 45597 |  |  | 92.9608 | -0.96081
[6 empty] | 14 | 96 | 45778 |  |  | 96.5727 | -0.57269
[6 empty] | 15 | 100 | 46022 |  |  | 100 | 0
Procurement /Supplier Costs |  |  |  | (in kEUR) |  | H1 - 2020 | H2-2020 |  | H1-2021 | H2-2021 | H1-2022 | H2-2022 | H1-2023 | H2-2023 | H1-2024 | H2-2024 | H1-2025 | H2-2025 |  | H2-2025
Propulsion |  |  |  | NREC | REC
1) | Pressure Transducer
| 1 PFM PT |  |  |  | 20
| PFM Test Campaign |  |  | 14
| 1 Dummy |  |  | 1.6
| Project Office |  |  | 32
| EQSR light |  |  | 51
| Sum |  |  | 98.6 | 20 | 118.6 |  |  |  |  | 29.65 | 59.3 | 29.65
2) | Service Valve
| 3x (1 PFM+2 FM) SV |  |  |  | 29
| NREC Eng. |  |  | 17
| PFM Campaign |  |  | 1
| Ground Half Coupling |  |  |  | 22
| Sum |  |  | 18 | 51 | 69 |  |  |  |  | 17.25 | 34.5 | 17.25
3) | Harness
| PFM |  |  |  | 55
| EM |  |  | 19
| Sum |  |  | 19 | 55 | 74 |  |  |  |  | 19 |  | 55
4) | Thrusters
| 8x1N Thruster |  |  |  | 520
| 22N Thruster |  |  |  | 200
| Project Office |  |  |  | 100
| 1 N Mass Dummy |  |  | 40
| 22 N Mass Dummy |  |  | 10
| Progress Meetings |  |  | 218
| Sum |  |  | 268 | 820 | 1088 |  |  |  |  | 217.6 | 326.4 | 326.4 | 217.6
| Propellant |  |  |  | 105
| Fueling of Satellite |  |  |  | 250
| Sum |  |  |  | 355 | 355 | [10 empty] | 177.5 | 177.5
5) | Latch Valve
| 2 FM Valves |  |  |  | 70
| PFM Campaign |  |  | 10
| Sum |  |  | 10 | 70 | 80 | [5 empty] | 40 | 40
6) | Propellant Tank
| 1 PFM tank |  |  |  | 475
| 1 SM Tank |  |  | 475
| EQSR meeting |  |  | 60
|  |  |  | 535 | 475 | 1010 |  |  | 252.5 |  | 252.5 | 252.5 | 252.5
GNC
1) | Magnetometer
| 2 (1 PFM+1 FM) Units |  |  |  | 98
| NREC standard |  |  | 27
| EM Unit |  |  | 22
| Mass Dummy |  |  | 3
| Sum |  |  | 52 | 98 | 150 |  |  | 37.5 |  | 75 | 37.5
2) | Magnetorquer
| 3 ( 1PFM+2FM) Units |  |  |  | 66
| NREC standard |  |  | 28
| EM Unit |  |  | 17
| Shock test |  |  | 5.5
| Mass Dummy |  |  | 6
| Sum |  |  | 56.5 | 66 | 122.5 |  |  | 30.625 |  | 61.25 | 30.625
3) | Sun Sensor
| 12xPFM Coss-R |  |  |  | 194
| Project Office |  |  | 43
| PFM Campaign |  |  | 19
| EQSR Light |  |  | 52
| EM x1(Coss-R) |  |  | 8
| Sum |  |  | 122 | 194 | 316 |  |  | 79 |  | 158 | 79
4) | Startracker
| 1PFM+1FM Startracker |  |  |  | 250
| EM |  |  | 54
| GSE Support |  |  | 50
| Sum |  |  | 104 | 250 | 354 |  |  | 54 |  | 125 | 175
5) | Harness
| PFM harness |  |  |  | 78
| EM harness |  |  | 33
| Sum |  |  | 33 | 78 | 111 |  |  | 33 |  |  | 78
6) | GNSS
| Redundant PFM |  |  |  | 351
| EM Unit |  |  | 45
| Dummy mass |  |  | 10
| GNC S/S AIT Assistance |  |  | 12
|  |  |  | 67 | 351 | 418 |  |  | 22.5 |  | 209 | 186.5
7) | Reaction Wheels
| 4 Wheels |  |  |  | 716
| EM Wheel |  |  | 51
| 4 Dummy Mass |  |  | 10
| GNC S/S AIT Assistance |  |  | 12
| Sum |  |  | 73 | 716 | 789 |  |  | 25.5 |  | 394.5 | 369
8) | IMU & Gyro modules
| 3 x IMU & Gyro modules |  |  |  | 24
| 1 EM IMU&Gyro module |  |  | 8
| 2 USB Evaluation kit |  |  | 2
|  |  |  | 10 | 24 | 34 |  |  | 8 |  |  | 36
OHB
| Original |  |  | H12020 |  | H22020 |  | H12021 |  | H22021 |  | H12022 |  | H22022 |  | H12023 |  | H22023 |  | H12024 |  | H22024 |  | H12025 |  | H22025
| By Quarters | Q1 2020 |  | Q2 2020 | Q3 2020 | Q4 2020 | Q1 2021 | Q2 2021 | Q3 2021 | Q4 2021 | Q1 2022 | Q2 2022 | Q3 2022 | Q4 2022 | Q1 2023 | Q2 2023 | Q3 2023 | Q4 2023 | Q1 2024 | Q2 2024 | Q3 2024 | Q4 2024 | Q1 2025 | Q2 2025 | Q3 2025 | Q4 2025
| Phase | A |  | A | B | B | B | B | C | C | C | C | D | D | D | D | D | D | D | D | D/E | D/E | E | E | E | E
| Milestone Name | Kick Off |  |  |  |  | GNC S/S PDR & Propulsion S/S PDR | Delivery of EM units + GNC S/S CDR |  |  | Propulsion S/S CDR | GNC S/S SW CDR |  |  | GNC S/S SW QR & Propulsion S/S DBR | Completion of SAT PFM A&I |  |  | Completion of SAT PFM Env Test Campaign + Completion of the launch campaign | Completion f in-orbit first check-out of GNC S/S and Propulsion S/S |  |  |  |  | Completion of first orbit raising | Completion of first debris disposal
| hours |  |  | 2282 |  | 10591 |  | 13636 |  | 12059 |  | 12971 |  | 11525 |  | 7880 |  | 6205 |  | 5838 |  | 6212 |  | 4369 |  | 3955 | 97523
| cost for hours (kEUR) |  |  | 227.0445 |  | 1074.9196 |  | 1412.744 |  | 1221.2105 |  | 1312.0942 |  | 1142.5841 |  | 804.7597 |  | 637.8406 |  | 601.2679 |  | 638.5382 |  | 421.8665 |  | 399.4446 | 9894.3144
| external costs/procurement (kEUR) |  |  | 0 |  | 542.625 |  | 1558.75 |  | 1714.325 |  | 1042.35 |  | 321.6 |  | 20 |  | 114 |  | 397.5 |  | 177.5 |  | 0 |  | 0 | 5888.65
| travel (kEUR) |  |  | 15 |  | 52 |  | 37 |  | 37 |  | 37 |  | 29 |  | 25 |  | 18 |  | 53 |  | 67 |  | 13 |  | 10 | 393
| sum (kEUR) |  |  | 242.0445 |  | 1669.5446 |  | 3008.494 |  | 2972.5355 |  | 2391.4442 |  | 1493.1841 |  | 849.7597 |  | 769.8406 |  | 1051.7679 |  | 883.0382 |  | 434.8665 |  | 409.4446 | 16175.9644
| Sum incl Cont. 10% |  |  | 266.249 |  | 1836.4991 |  | 3309.3434 |  | 3269.7891 |  | 2630.5887 |  | 1642.5025 |  | 934.7357 |  | 846.8247 |  | 1156.9446 |  | 971.342 |  | 478.3532 |  | 450.389 | 17793.5609 | 0
|  |  |  | H1 - 2020 |  | H2-2020 |  | H1-2021 |  | H2-2021 |  | H1-2022 |  | H2-2022 |  | H1-2023 |  | H2-2023 |  | H1-2024 |  | H2-2024 |  | H1-2025 |  | H2-2025
| FTE |  |  | 2.5356 |  | 11.7678 | 0 | 15.1511 |  | 13.3989 |  | 14.4122 |  | 12.8056 |  | 8.7556 |  | 6.8944 |  | 6.4867 |  | 6.9022 |  | 4.8544 |  | 4.3944
| Ground Segment |  |  | 0 |  | 0 | 0 | 0.14649 |  | 0.27405 |  | 0.14649 |  | 0.19383 |  | 0.088761 |  | 0.024913 |  | 0.22223 |  | 0.36178 |  | 0.36178 |  | 0.36178
| Launch 2025 same cost |  |  | H12020 |  | H22020 |  | H12021 |  | H22021 |  | H12022 |  | H22022 |  | H12023 |  | H22023 |  | H12024 |  | H22024 |  | H12025 |  | H22025
| By Quarters | Q1 2020 |  | Q2 2020 | Q3 2020 | Q4 2020 | Q1 2021 | Q2 2021 | Q3 2021 | Q4 2021 | Q1 2022 | Q2 2022 | Q3 2022 | Q4 2022 | Q1 2023 | Q2 2023 | Q3 2023 | Q4 2023 | Q1 2024 | Q2 2024 | Q3 2024 | Q4 2024 | Q1 2025 | Q2 2025 | Q3 2025 | Q4 2025
| Phase | A |  | A | A | B | B | B | B | B | B | C | C | C | C | D | D | D | D | D | D | D | D | E | E | E
| Milestone Name | Kick Off | [7 empty] | GNC S/S PDR & Propulsion S/S PDR | Delivery of EM units + GNC S/S CDR |  |  | Propulsion S/S CDR | GNC S/S SW CDR |  |  | GNC S/S SW QR & Propulsion S/S DBR | Completion of SAT PFM A&I |  |  | Completion of SAT PFM Env Test Campaign + Completion of the launch campaign | Completion f in-orbit first check-out of GNC S/S and Propulsion S/S |  | Completion of first orbit raising | Completion of first debris disposal
| hours |  |  |  | 2282 |  |  | 10591 |  |  | 13636 |  | 12059 |  | 12971 |  | 11525 |  | 7880 |  | 6205 |  | 5838 | 6212 | 4369 | 3955 | 97523
| cost for hours (kEUR) |  |  |  | 227.0445 |  |  | 1074.9196 |  |  | 1412.744 |  | 1221.2105 |  | 1312.0942 |  | 1142.5841 |  | 804.7597 |  | 637.8406 |  | 601.2679 | 638.5382 | 421.8665 | 399.4446 | 9894.3144
| external costs/procurement (kEUR) |  |  |  | 0 |  |  | 542.625 |  |  | 1558.75 |  | 1714.325 |  | 1042.35 |  | 321.6 |  | 20 |  | 114 |  | 397.5 | 177.5 | 0 | 0 | 5888.65
| travel (kEUR) |  |  |  | 15 |  |  | 52 |  |  | 37 |  | 37 |  | 37 |  | 29 |  | 25 |  | 18 |  | 53 | 67 | 13 | 10 | 393
| sum (kEUR) |  |  |  | 242.0445 | 0 | 0 | 1669.5446 | 0 | 0 | 3008.494 | 0 | 2972.5355 | 0 | 2391.4442 | 0 | 1493.1841 |  | 849.7597 |  | 769.8406 |  | 1051.7679 | 883.0382 | 434.8665 | 409.4446 | 16175.9644
| Sum incl Cont. 10% | 0 |  | 0 | 266.249 | 0 | 0 | 1836.4991 | 0 | 0 | 3309.3434 | 0 | 3269.7891 | 0 | 2630.5887 | 0 | 1642.5025 | 0 | 934.7357 | 0 | 846.8247 | 0 | 1156.9446 | 971.342 | 478.3532 | 450.389 | 17793.5609 | 0
| cont | 0 |  | 0 | 24.2045 | 0 | 0 | 166.9545 | 0 | 0 | 300.8494 | 0 | 297.2536 | 0 | 239.1444 | 0 | 149.3184 | 0 | 84.976 | 0 | 76.9841 | 0 | 105.1768 | 88.3038 | 43.4867 | 40.9445 | 1617.5964
|  |  |  | H1 - 2020 |  | H2-2020 |  | H1-2021 |  | H2-2021 |  | H1-2022 |  | H2-2022 |  | H1-2023 |  | H2-2023 |  | H1-2024 |  | H2-2024 |  | H1-2025 |  | H2-2025
| FTE |  |  |  | 2.5356 |  |  | 11.7678 |  |  | 15.1511 | 13.3989 |  |  | 14.4122 |  | 12.8056 |  | 8.7556 |  | 6.8944 |  | 6.4867 | 6.9022 | 4.8544 | 4.3944
| Ground Segment |  |  |  | 0 |  |  | 0 |  |  | 146.4902 | 274.0463 |  |  | 146.4902 |  | 193.8255 |  | 88.7607 |  | 24.9133 |  | 222.2267 | 361.7758 | 361.7758 | 361.7758

## Price Table 8 RUAG (hidden)
New Table 8 breakdown
Industrial Price
| Economic Conditions | 2019
| Currency | k€ | please specify currency
[8 empty] | Year | 2020 |  |  |  | 2021 |  |  |  | 2022 |  |  |  | 2023 |  |  |  | 2024 |  |  |  | 2025 |  |  |  | TOTAL
[8 empty] | Phase | Phase A |  |  | Phase B | [5 empty] | Phase C
T8 CODE | Price Breakdown |  |  | CAT | TYPE | CONC | WP# | Q | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
| Space Segment | [6 empty] | Milestone | KO |  |  | MSRR
| Spacecraft | [7 empty] | 2020-02-01 | 2020-04-01 | 2020-06-30 | 2021-01-31
Project Office:
A1 | Management |  |  | MGT | Manpower | MGTManpower | 110000 |  | 10.4498 | 10.4498 | 10.4498 | 10.4498 | 10.4498 | 10.4498 | 10.4498 | 10.4498 | 10.4498 | 10.4498 | 0 | 0 | [12 empty] | 104.4983
A2 | Product Assurance |  |  | MGT | Manpower | MGTManpower | 130000 | [25 empty] | 0
A3 | (Project & Mission) Engineering |  |  | MISSION | Manpower | MISSIONManpower | 120000 140000 200000 310000 |  | 0 | 0 | 10.0832 | 10.0832 | 10.0832 | 10.0832 | 10.0832 | 10.0832 | 10.0832 | 10.0832 | 0 | 0 | [12 empty] | 80.6652
|  |  | Total Cost (k€) | [29 empty] | 0
A4 | Flight Systems Engineering |  |  | MISSION | Manpower | MISSIONManpower | 401000 | - 401422, 401423, 401520, 401533 to 401536 | 32.2661 | 32.2661 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 64.5322
A5 | (System level) Assembly, Integration and Testing,Verification |  |  | MISSION | Manpower | MISSIONManpower | 501000 520000 530000 550000 | includes OHB-Sweden | [24 empty] | 0
A6 | Ground Segment Equipment |  |  | MISSION | Procurement | MISSIONProcurement | 510000 | includes OHB-Sweden (PGSE?), APCO | [24 empty] | 0
|  |  | Total Cost (k€) | [29 empty] | 0
| Platform Module Hardware/Software (HW/SW) | [31 empty] | 0
| OB Flight Software | [31 empty] | 0
B11 | FSW - Manpower (M/y) tech |  |  | TECH | Manpower | TECHManpower | 410000 | [25 empty] | 0
B12 | FSW - Manpower (M/y) mission |  |  | MISSION | Manpower | MISSIONManpower | ADS WP to see | [25 empty] | 0
|  |  | Total Cost (k€) | [29 empty] | 0
| Data Handling | [31 empty] | 0
B21 | Data Handling - Engineering |  |  | MISSION | Manpower | MISSIONManpower | 430000 | includes ADS | [24 empty] | 0
B22 | Data Handling - HW procurements |  |  | MISSION | Procurement | MISSIONProcurement | 430000 | includes ADS | [24 empty] | 0
|  |  | Total Cost (k€) | [29 empty] | 0
| Electrical Power | [31 empty] | 0
B31 | Electrical Power - Engineering and SW |  |  | MISSION | Manpower | MISSIONManpower | 420000 | includes ADS | [24 empty] | 0
B32 | Electrical Power - HW procurements |  |  | MISSION | Procurement | MISSIONProcurement | 420000 | includes ADS | [24 empty] | 0
|  |  | Total Cost (k€) | [29 empty] | 0
| Communications | [31 empty] | 0
B41 | Communications - Engineering and SW |  |  | MISSION | Manpower | MISSIONManpower | 440000 | ADS CS | [24 empty] | 0
B42 | Communications - HW procurements |  |  | MISSION | Procurement | MISSIONProcurement | [26 empty] | 0
|  |  | Total Cost (k€) | [29 empty] | 0
| AOCS / GNC | [31 empty] | 0
B51 | AOCS / GNC - Engineering and SW |  |  | MISSION | Manpower | MISSIONManpower | 450000 | - OHB 450500, 450600, 450800, 45900 | [24 empty] | 0
B52 | AOCS / GNC - HW procurements |  |  | MISSION | Procurement | MISSIONProcurement | [26 empty] | 0
|  |  | Total Cost (k€) | [29 empty] | 0
| Propulsion | [31 empty] | 0
B61 | Propulsion - Engineering |  |  | MISSION | Manpower | MISSIONManpower | 470000 | OHB | [24 empty] | 0
B62 | Propulsion - HW procurements |  |  | MISSION | Procurement | MISSIONProcurement | 470000 | OHB | [24 empty] | 0
|  |  | Total Cost (k€) | [29 empty] | 0
| Structure | [31 empty] | 0
B71 | Structure - Engineering |  |  | TECH | Manpower | TECHManpower | 490100 to 49500 | - 490540 | [24 empty] | 0
B72 | Structure - HW |  |  | TECH | Procurement | TECHProcurement | 490100 to 49500 | - 490540 | [24 empty] | 0
|  |  | Total Cost (k€) | [29 empty] | 0
| Thermal Control | [31 empty] | 0
B81 | Thermal Control - Engineering |  |  | TECH | Manpower | TECHManpower | 490600 | [25 empty] | 0
B82 | Thermal Control - HW |  |  | TECH | Procurement | TECHProcurement | 490600 | [25 empty] | 0
|  |  | Total Cost (k€) | [29 empty] | 0
| Mechanisms | [31 empty] | 0
B91 | Mechanisms - HW procurements |  |  | MISSION | Procurement | MISSIONProcurement | 490540 | [25 empty] | 0
|  |  | Total Cost (k€) | [29 empty] | 0
| Service Module HW/SW | [31 empty] | 0
| Rendezvous GNC, Sensors and Processing (RVSP) | [31 empty] | 0
C11 | RVSP - Engineering and SW |  |  | TECH | Manpower | TECHManpower | 460100 to 460900 461000 41100to412000 461000 SYD +OHB 450500 450600 450800 450900 | [25 empty] | 0
C12 | RVSP - HW procurements |  |  | TECH | Procurement | TECHProcurement | 460100 to 460900 461000 SYD | + 401422, 401423, 401520, 401533 to 401536 | [24 empty] | 0
|  |  | Total Cost (k€) | [29 empty] | 0
| Capture System (CS) | [31 empty] | 0
C21 | CS - Engineering and SW |  |  | TECH | Manpower | TECHManpower | 480000 | CS EPFL RUAG | 60.1287 | 60.1287 | 43.0043 | 43.0043 | 43.0043 | 43.0043 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 292.2748
C22 | CS - HW procurements |  |  | TECH | Procurement | TECHProcurement | 480000 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0
|  |  | Total Cost (k€) | [29 empty] | 0
C3 | Service Module Validation |  |  | TECH | Procurement | TECHProcurement | 540000 | [25 empty] | 0
| Risk Contingency (e.g. Technical, Management Reserve) | [31 empty] | 0
0
D | Launcher |  |  | MISSION | Procurement | MISSIONProcurement | 320000 | [25 empty] | 0
0
0
| Ground Segment & Operations | [31 empty] | 0
E1 | Ground Control Centre Development |  |  | MISSION | Manpower | MISSIONManpower | 610000 62000-620100 INCL. OHB 630000 | [25 empty] | 0
E2 | Mission Operations |  |  | MISSION | Manpower | MISSIONManpower | 710000 720000 730000 740000 750000 640000 | [25 empty] | 0
E3 | Ground observations & tools |  |  | TECH | Manpower | TECHManpower | 650000 | [25 empty] | 0
E4 | Ground Stations |  |  | MISSION | Procurement | MISSIONProcurement | 620100 | [25 empty] | 0
E5 | Ground Segment - Procurement |  |  | MISSION | Procurement | MISSIONProcurement | included in Flight SE and Ground Control Center Development | [25 empty] | 0
F | Contingency | [7 empty] | 20.5689 | 20.5689 | 12.7075 | 12.7075 | 12.7075 | 12.7075 | 4.1066 | 4.1066 | 4.1066 | 4.1066 | 0 | 0 | [12 empty] | 108.3941
| TOT EX Contingency | [7 empty] | 102.8446 | 102.8446 | 63.5373 | 63.5373 | 63.5373 | 63.5373 | 20.533 | 20.533 | 20.533 | 20.533 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 541.9704 | 0
| TOT with contingency | [7 empty] | 123.4135 | 123.4135 | 76.2448 | 76.2448 | 76.2448 | 76.2448 | 24.6396 | 24.6396 | 24.6396 | 24.6396 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 650.3645
|  |  |  | MGT | Manpower | MGTManpower |  |  | 10.4498 | 10.4498 | 10.4498 | 10.4498 | 10.4498 | 10.4498 | 10.4498 | 10.4498 | 10.4498 | 10.4498 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 104.4983
|  |  |  | MISSION | Manpower | MISSIONManpower |  |  | 32.2661 | 32.2661 | 10.0832 | 10.0832 | 10.0832 | 10.0832 | 10.0832 | 10.0832 | 10.0832 | 10.0832 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 145.1974
|  |  |  | TECH | Manpower | TECHManpower |  |  | 60.1287 | 60.1287 | 43.0043 | 43.0043 | 43.0043 | 43.0043 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 292.2748
|  |  |  | MISSION | Procurement | MISSIONProcurement |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | TECH | Procurement | TECHProcurement |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[9 empty] | 102.8446 | 102.8446 | 63.5373 | 63.5373 | 63.5373 | 63.5373 | 20.533 | 20.533 | 20.533 | 20.533 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 541.9704
Note on H10: Brigitte Allegra: Work Package number

## RUAG (hidden)
New Table 8 breakdown
Industrial Price
|  |  | Economic Conditions | 2019
|  |  | Currency | CHF | [5 empty] | CHF SOR submission | [12 empty] | KEUR 2025 Launch
|  |  | Exchange rate NC/EUR | 1.15 | (PSS A2) |  |  |  |  | 2020 |  |  |  | 2021 |  |  |  | 2022 |  |  |  |  | 2020 |  |  |  | 2021 |  |  |  | 2022
[10 empty] | Phase A |  |  | Phase B | [9 empty] | Phase A |  |  | Phase B
|  |  | Price Breakdown |  |  | LEVEL | TYPE | WP# |  | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 |  | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
|  |  | Space Segment | [6 empty] | Phase A Q1: KO; Phase B Q4: MSRR |  | KO |  |  | MSRR
|  |  | Spacecraft | [6 empty] | Phase A Q1: 2020-02-01; Phase A Q2: 2020-04-01; Phase A Q3: 2020-06-30; Phase B Q4: 2021-01-31 |  | 2020-02-01 | 2020-04-01 | 2020-06-30 | 2021-01-31
|  |  | Grabbing Feature AM Interface |  | RUAG SPACE | Start | End | WP#
T8 Code | T8 Descr | 110800 | Project Management |  |  | 2020-02-03 | 2022-05-23 | WP110800 | [CHF] | bar: Phase A Q1 to Phase B Q2
A1 | Management | 110800 | Project Management |  |  | Project Management | Manpower |  | 109627 | 10962.7 | 10962.7 | 10962.7 | 10962.7 | 10962.7 | 10962.7 | 10962.7 | 10962.7 | 10962.7 | 10962.7 |  |  | 109627 | 9.5328 | 9.5328 | 9.5328 | 9.5328 | 9.5328 | 9.5328 | 9.5328 | 9.5328 | 9.5328 | 9.5328 |  |  | 95.3278
A1 | Management | 110800 | Profit |  |  | Profit | Profit |  | 8770 | 877 | 877 | 877 | 877 | 877 | 877 | 877 | 877 | 877 | 877 |  |  | 8770 | 0.76261 | 0.76261 | 0.76261 | 0.76261 | 0.76261 | 0.76261 | 0.76261 | 0.76261 | 0.76261 | 0.76261 |  |  | 7.6261
A1 | Management | 110800 | Provision |  |  | Escalation | reserve |  | 1776 | 177.6 | 177.6 | 177.6 | 177.6 | 177.6 | 177.6 | 177.6 | 177.6 | 177.6 | 177.6 |  |  | 1776 | 0.15443 | 0.15443 | 0.15443 | 0.15443 | 0.15443 | 0.15443 | 0.15443 | 0.15443 | 0.15443 | 0.15443 |  |  | 1.5443
[5 empty] | Total Cost |  |  | 104498 | 120173 | [12 empty] | 0 | [12 empty] | 0
|  | 480211 | Preliminary Design Damping Structure |  |  | 2020-02-03 | 2020-07-17 | WP480211 | [CHF] | [12 empty] | 0 | [12 empty] | 0 | bar: Phase A Q1 to Phase A Q2
C21 | CS - Engineering and SW | 480211 | Egineering - Design |  |  | Enineering -Design | Manpower |  | 125526 | Phase A Q1: 62763; Phase A Q2: 62763 | 125526 | 54.5765 | 54.5765 | [10 empty] | 109.153
C21 | CS - Engineering and SW | 480211 | Travel & Subsistence |  |  | Travel | Aux |  | 633 | Phase A Q1: 316.5; Phase A Q2: 316.5 | 633 | 0.27522 | 0.27522 | [10 empty] | 0.55043
C21 | CS - Engineering and SW | 480211 | Profit |  |  | Profit | Profit |  | 10093 | Phase A Q1: 5046.5; Phase A Q2: 5046.5 | 10093 | 4.3883 | 4.3883 | [10 empty] | 8.7765
C21 | CS - Engineering and SW | 480211 | Provision |  |  | Escalation | reserve |  | 2044 | Phase A Q1: 1022; Phase A Q2: 1022 | 2044 | 0.8887 | 0.8887 | [10 empty] | 1.7774
[5 empty] | Total Cost |  |  | 120257 | 138295 | [12 empty] | 0 | [12 empty] | 0
|  | 480221 | Detailed Design Damping Structure |  |  | 2020-07-20 | 2021-06-21 | WP480221 | [CHF] | [12 empty] | 0 | [12 empty] | 0 | bar: Phase A Q3 to Phase B Q2
C21 | CS - Engineering and SW | 480221 | Engineering |  |  | Enineering -Design | Manpower |  | 179827 | Phase A Q3: 44956.75; Phase B Q4: 44956.75; Phase B Q1: 44956.75; Phase B Q2: 44956.75 | 179827 |  |  | 39.0928 | 39.0928 | 39.0928 | 39.0928 | [6 empty] | 156.3713
C21 | CS - Engineering and SW | 480221 | Travel & Subsistence |  |  | Travel | Aux |  | 633 | Phase A Q3: 158.25; Phase B Q4: 158.25; Phase B Q1: 158.25; Phase B Q2: 158.25 | 633 |  |  | 0.13761 | 0.13761 | 0.13761 | 0.13761 | [6 empty] | 0.55043
C21 | CS - Engineering and SW | 480221 | Profit |  |  | Profit | Profit |  | 14437 | Phase A Q3: 3609.25; Phase B Q4: 3609.25; Phase B Q1: 3609.25; Phase B Q2: 3609.25 | 14437 |  |  | 3.1385 | 3.1385 | 3.1385 | 3.1385 | [6 empty] | 12.5539
C21 | CS - Engineering and SW | 480221 | Provision |  |  | Escalation | reserve |  | 2923 | Phase A Q3: 730.75; Phase B Q4: 730.75; Phase B Q1: 730.75; Phase B Q2: 730.75 | 2923 |  |  | 0.63543 | 0.63543 | 0.63543 | 0.63543 | [6 empty] | 2.5417
[5 empty] | Total Cost |  |  | 172017 | 197819 | [12 empty] | 0 | [12 empty] | 0
|  | 401411 | Satellite configuration system optimisation and demisability |  |  | 2020-02-03 | 2020-07-17 | WP401411 | [CHF] | [12 empty] | 0 | [12 empty] | 0 | bar: Phase A Q1 to Phase A Q2
A4 | Flight Systems Engineering | 401411 | Engineering |  |  | Enineering -Design | Manpower |  | 67699 | Phase A Q1: 33849.5; Phase A Q2: 33849.5 | 67699 | 29.4343 | 29.4343 | [10 empty] | 58.8687
A4 | Flight Systems Engineering | 401411 | Travel & Subsistence |  |  | Travel | Aux |  | 0 | Phase A Q1: 0; Phase A Q2: 0 | 0 | 0 | 0 | [10 empty] | 0
A4 | Flight Systems Engineering | 401411 | Profit |  |  | Profit | Profit |  | 5416 | Phase A Q1: 2708; Phase A Q2: 2708 | 5416 | 2.3548 | 2.3548 | [10 empty] | 4.7096
A4 | Flight Systems Engineering | 401411 | Provision |  |  | Escalation | reserve |  | 1097 | Phase A Q1: 548.5; Phase A Q2: 548.5 | 1097 | 0.47696 | 0.47696 | [10 empty] | 0.95391
[5 empty] | Total Cost |  |  | 64532 | 74212 | [12 empty] | 0 | [12 empty] | 0
|  |  | Industrialization |  |  | 2020-07-20 | 2022-05-23 | WP180410 | [CHF] | [12 empty] | 0 | [12 empty] | 0 | bar: Phase A Q3 to Phase B Q2
A3 | (Project & Mission) Engineering | 140410 | Engineering |  |  | Enineering -Design | Manpower |  | 84624 | 0 | 0 | 10578 | 10578 | 10578 | 10578 | 10578 | 10578 | 10578 | 10578 |  |  | 84624 |  |  | 9.1983 | 9.1983 | 9.1983 | 9.1983 | 9.1983 | 9.1983 | 9.1983 | 9.1983 |  |  | 73.5861
A3 | (Project & Mission) Engineering | 140410 | Travel & Subsistence |  |  | Travel | Aux |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
A3 | (Project & Mission) Engineering | 140410 | Profit |  |  | Profit | Profit |  | 6770 |  |  | 846.25 | 846.25 | 846.25 | 846.25 | 846.25 | 846.25 | 846.25 | 846.25 |  |  | 6770 |  |  | 0.73587 | 0.73587 | 0.73587 | 0.73587 | 0.73587 | 0.73587 | 0.73587 | 0.73587 |  |  | 5.887
A3 | (Project & Mission) Engineering | 140410 | Provision |  |  | Escalation | reserve |  | 1371 |  |  | 171.375 | 171.375 | 171.375 | 171.375 | 171.375 | 171.375 | 171.375 | 171.375 |  |  | 1371 |  |  | 0.14902 | 0.14902 | 0.14902 | 0.14902 | 0.14902 | 0.14902 | 0.14902 | 0.14902 |  |  | 1.1922
[5 empty] | Total Cost (k€) |  |  | 80665 | 92765
Risk Contingency (e.g. Technical, Management Reserve)
[8 empty] | 541969 | 623264 | [12 empty] | 623266 | [12 empty] | 541.9704
Ground Segment & Operations
|  |  | Ground Control Centre Development |  |  | MISSION | Manpower
|  |  | Ground Control Centre Operations |  |  | MISSION | Manpower
|  |  | Ground observations & tools |  |  | TECH | Manpower
|  |  | Ground Stations |  |  | MISSION | Procurement
Simulator(s)
Contingency
Note on I7: Brigitte Allegra: Work Package number

## Price Table 8 Syderal (hidden)
New Table 8 breakdown
Industrial Price
| Economic Conditions | 2019
| Currency | k€ | please specify currency
[8 empty] | Year | 2020 |  |  |  | 2021 |  |  |  | 2022 |  |  |  | 2023 |  |  |  | 2024 |  |  |  | 2025 |  |  |  | TOTAL
[8 empty] | Phase | Phase A |  |  | Phase B | [5 empty] | Phase C
T8 CODE | Price Breakdown |  |  | CAT | TYPE | CONC | WP# | Q | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
| Space Segment | [6 empty] | Milestone | KO |  |  | MSRR
Spacecraft
Project Office:
A1 | Management |  |  | MGT | Manpower | MGTManpower | 110000 |  |  | 26.7611 | 26.7611 | 26.7611 | 26.7611 | 26.7611 | 26.7611 | 26.7611 | 26.7611 | 26.7611 | 26.7611 | 26.7611 | 26.7611 | [11 empty] | 321.1327
A2 | Product Assurance |  |  | MGT | Manpower | MGTManpower | 130000 |  |  | 16.7424 | 16.7424 | 16.7424 | 16.7424 | 16.7424 | 16.7424 | 16.7424 | 16.7424 | 16.7424 | 16.7424 | 16.7424 | 16.7424 | [11 empty] | 200.9087
A3 | (Project & Mission) Engineering |  |  | MISSION | Manpower | MISSIONManpower | 120000 140000 200000 310000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | 0
|  |  | Total Cost (k€) | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | 0
A4 | Flight Systems Engineering |  |  | MISSION | Manpower | MISSIONManpower | 401000 | - 401422, 401423, 401520, 401533 to 401536 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | 0
A5 | (System level) Assembly, Integration and Testing,Verification |  |  | MISSION | Manpower | MISSIONManpower | 501000 520000 530000 550000 | includes OHB-Sweden |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | 0
A6 | Ground Segment Equipment |  |  | MISSION | Procurement | MISSIONProcurement | 510000 | includes OHB-Sweden (PGSE?), APCO |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | 0
|  |  | Total Cost (k€) | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | 0
| Platform Module Hardware/Software (HW/SW) | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | 0
| OB Flight Software | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | 0
B11 | FSW - Manpower (M/y) tech |  |  | TECH | Manpower | TECHManpower | 410000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | 0
B12 | FSW - Manpower (M/y) mission |  |  | MISSION | Manpower | MISSIONManpower | ADS WP to see |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | 0
|  |  | Total Cost (k€) | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | 0
| Data Handling | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | 0
B21 | Data Handling - Engineering |  |  | MISSION | Manpower | MISSIONManpower | 430000 | includes ADS |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | 0
B22 | Data Handling - HW procurements |  |  | MISSION | Procurement | MISSIONProcurement | 430000 | includes ADS |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | 0
|  |  | Total Cost (k€) | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | 0
| Electrical Power | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | 0
B31 | Electrical Power - Engineering and SW |  |  | MISSION | Manpower | MISSIONManpower | 420000 | includes ADS |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | 0
B32 | Electrical Power - HW procurements |  |  | MISSION | Procurement | MISSIONProcurement | 420000 | includes ADS |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | 0
|  |  | Total Cost (k€) | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | 0
| Communications | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | 0
B41 | Communications - Engineering and SW |  |  | MISSION | Manpower | MISSIONManpower | 440000 | ADS CS |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | 0
B42 | Communications - HW procurements |  |  | MISSION | Procurement | MISSIONProcurement |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | 0
|  |  | Total Cost (k€) | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | 0
| AOCS / GNC | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | 0
B51 | AOCS / GNC - Engineering and SW |  |  | MISSION | Manpower | MISSIONManpower | 450000 | - OHB 450500, 450600, 450800, 45900 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | 0
B52 | AOCS / GNC - HW procurements |  |  | MISSION | Procurement | MISSIONProcurement |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | 0
|  |  | Total Cost (k€) | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | 0
| Propulsion | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | 0
B61 | Propulsion - Engineering |  |  | MISSION | Manpower | MISSIONManpower | 470000 | OHB |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | 0
B62 | Propulsion - HW procurements |  |  | MISSION | Procurement | MISSIONProcurement | 470000 | OHB |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | 0
|  |  | Total Cost (k€) | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | 0
| Structure | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | 0
B71 | Structure - Engineering |  |  | TECH | Manpower | TECHManpower | 490100 to 49500 | - 490540 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | 0
B72 | Structure - HW |  |  | TECH | Procurement | TECHProcurement | 490100 to 49500 | - 490540 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | 0
|  |  | Total Cost (k€) | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | 0
| Thermal Control | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | 0
B81 | Thermal Control - Engineering |  |  | TECH | Manpower | TECHManpower | 490600 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | 0
B82 | Thermal Control - HW |  |  | TECH | Procurement | TECHProcurement | 490600 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | 0
|  |  | Total Cost (k€) | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | 0
| Mechanisms | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | 0
B91 | Mechanisms - HW procurements |  |  | MISSION | Procurement | MISSIONProcurement | 490540 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | 0
|  |  | Total Cost (k€) | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | 0
| Service Module HW/SW | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | 0
| Rendezvous GNC, Sensors and Processing (RVSP) | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | 0
C11 | RVSP - Engineering and SW |  |  | TECH | Manpower | TECHManpower | 460100 to 460900 461000 41100to412000 461000 SYD +OHB 450500 450600 450800 450900 |  |  | 214.607 | 214.607 | 267.5127 | 267.5127 | 145.7642 | 145.7642 | 183.2153 | 183.2153 | 56.9007 | 56.9007 | 79.5998 | 79.5998 | [11 empty] | 1895.1993
C12 | RVSP - HW procurements |  |  | TECH | Procurement | TECHProcurement | 460100 to 460900 461000 SYD | + 401422, 401423, 401520, 401533 to 401536 |  | 0 | 0 | 38.9947 | 0 | 76.4602 | 0 | 144.1274 | 0 | 0 | 0 | 77.9894 | 0 | [11 empty] | 337.5717
|  |  | Total Cost (k€) | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | 0
| Capture System (CS) | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | 0
C21 | CS - Engineering and SW |  |  | TECH | Manpower | TECHManpower | 480000 | CS EPFL |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | 0
C22 | CS - HW procurements |  |  | TECH | Procurement | TECHProcurement | 480000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | 0
|  |  | Total Cost (k€) | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | 0
C3 | Service Module Validation |  |  | TECH | Procurement | TECHProcurement | 540000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | 0
| Risk Contingency (e.g. Technical, Management Reserve) | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | 0
0
D | Launcher |  |  | MISSION | Procurement | MISSIONProcurement | 320000 | [25 empty] | 0
0
0
| Ground Segment & Operations | [31 empty] | 0
E1 | Ground Control Centre Development |  |  | MISSION | Manpower | MISSIONManpower | 610000 62000-620100 INCL. OHB 630000 | [25 empty] | 0
E2 | Mission Operations |  |  | MISSION | Manpower | MISSIONManpower | 710000 720000 730000 740000 750000 640000 | [25 empty] | 0
E3 | Ground observations & tools |  |  | TECH | Manpower | TECHManpower | 650000 | [25 empty] | 0
E4 | Ground Stations |  |  | MISSION | Procurement | MISSIONProcurement | 620100 | [25 empty] | 0
E5 | Ground Segment - Procurement |  |  | MISSION | Procurement | MISSIONProcurement | included in Flight SE and Ground Control Center Development | [25 empty] | 0
F | Contingency | [7 empty] | 0 | 51.6221 | 51.6221 | 70.0022 | 62.2032 | 53.1456 | 37.8535 | 74.1692 | 45.3438 | 20.0808 | 20.0808 | 40.2185 | 24.6207 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 550.9625
| TOT EX Contingency | [7 empty] | 0 | 258.1104 | 258.1104 | 350.0108 | 311.0161 | 265.7278 | 189.2676 | 370.8462 | 226.7188 | 100.4042 | 100.4042 | 201.0927 | 123.1033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2754.8124 | 0
| TOT with contingency | [7 empty] | 0 | 309.7325 | 309.7325 | 420.013 | 373.2193 | 318.8733 | 227.1211 | 445.0154 | 272.0625 | 120.485 | 120.485 | 241.3112 | 147.7239 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3305.7749
|  |  |  | MGT | Manpower | MGTManpower |  |  | 0 | 43.5035 | 43.5035 | 43.5035 | 43.5035 | 43.5035 | 43.5035 | 43.5035 | 43.5035 | 43.5035 | 43.5035 | 43.5035 | 43.5035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 522.0414
|  |  |  | MISSION | Manpower | MISSIONManpower |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | TECH | Manpower | TECHManpower |  |  | 0 | 214.607 | 214.607 | 267.5127 | 267.5127 | 145.7642 | 145.7642 | 183.2153 | 183.2153 | 56.9007 | 56.9007 | 79.5998 | 79.5998 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1895.1993
|  |  |  | MISSION | Procurement | MISSIONProcurement |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | TECH | Procurement | TECHProcurement |  |  | 0 | 0 | 0 | 38.9947 | 0 | 76.4602 | 0 | 144.1274 | 0 | 0 | 0 | 77.9894 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 337.5717
[9 empty] | 0 | 258.1104 | 258.1104 | 350.0108 | 311.0161 | 265.7278 | 189.2676 | 370.8462 | 226.7188 | 100.4042 | 100.4042 | 201.0927 | 123.1033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2754.8124
Note on H10: Brigitte Allegra: Work Package number

## Syderal (hidden)
[5 empty] | 2020 | 2021 |  |  |  | 2022 |  |  |  | 2023
|  |  |  | Launch 2025 Timeline | Phase A |  |  | Phase B
T8 Code | T8 Descr | WP number | WP name | Manpower, Procurement and TOTAL per WP | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | TOT | Hours
A1 | Management | 110600 | RVSPU Project Management | Manpower | 26.7611 | 26.7611 | 26.7611 | 26.7611 | 26.7611 | 26.7611 | 26.7611 | 26.7611 | 26.7611 | 26.7611 | 26.7611 | 26.7611 | 321.1327 | 1920
|  | 110600 |  | Procurement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 110600 |  | TOTAL (=MAN+PROC) | 26.7611 | 26.7611 | 26.7611 | 26.7611 | 26.7611 | 26.7611 | 26.7611 | 26.7611 | 26.7611 | 26.7611 | 26.7611 | 26.7611 | 321.1327
A2 | Product Assurance | 130500 | RVSPU Product Assurance Management | Manpower | 16.7424 | 16.7424 | 16.7424 | 16.7424 | 16.7424 | 16.7424 | 16.7424 | 16.7424 | 16.7424 | 16.7424 | 16.7424 | 16.7424 | 200.9087 | 1430
|  | 130500 |  | Procurement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 130500 |  | TOTAL | 16.7424 | 16.7424 | 16.7424 | 16.7424 | 16.7424 | 16.7424 | 16.7424 | 16.7424 | 16.7424 | 16.7424 | 16.7424 | 16.7424 | 200.9087
C11 | RVSP - Engineering and SW | 461010 | RVSPU-EBB Preliminary Design | Manpower | 214.607 | 214.607 | 267.5127 | 267.5127 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 964.2393 | 6940
C12 | RVSP - HW procurements | 461010 |  | Procurement | 0 | 0 | 38.9947 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38.9947
|  | 461010 |  | TOTAL | 214.607 | 214.607 | 306.5073 | 267.5127 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1003.234
C11 | RVSP - Engineering and SW | 461020 | RVSPU-EQM design, production and test | Manpower | 0 | 0 | 0 | 0 | 145.7642 | 145.7642 | 183.2153 | 183.2153 | 0 | 0 | 0 | 0 | 657.9589 | 4780
C12 | RVSP - HW procurements | 461020 |  | Procurement | 0 | 0 | 0 | 0 | 76.4602 | 0 | 144.1274 | 0 | 0 | 0 | 0 | 0 | 220.5876
|  | 461020 |  | TOTAL | 0 | 0 | 0 | 0 | 222.2243 | 145.7642 | 327.3427 | 183.2153 | 0 | 0 | 0 | 0 | 878.5465
C11 | RVSP - Engineering and SW | 461030 | RVSPU-PFM design, production and test | Manpower | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56.9007 | 56.9007 | 79.5998 | 79.5998 | 273.0011 | 2040
C12 | RVSP - HW procurements | 461030 |  | Procurement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 77.9894 | 0 | 77.9894
|  | 461030 |  | TOTAL | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56.9007 | 56.9007 | 157.5892 | 79.5998 | 350.9904
[5 empty] | 258.1104 | 258.1104 | 350.0108 | 311.0161 | 265.7278 | 189.2676 | 370.8462 | 226.7188 | 100.4042 | 100.4042 | 201.0927 | 123.1033 | 2754.8124 | 17110
[5 empty] | 2020 |  |  |  | 2021 |  |  |  | 2022
|  |  |  | SOR Submission Timeline | Phase A |  |  | Phase B
|  | WP number | WP name | Manpower, Procurement and TOTAL per WP | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
| A1 | 110600 | RVSPU Project Management | Manpower | 26761.0619 | 26761.0619 | 26761.0619 | 26761.0619 | 26761.0619 | 26761.0619 | 26761.0619 | 26761.0619 | 26761.0619 | 26761.0619 | 26761.0619 | 26761.0619
|  |  |  | Procurement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | TOTAL (=MAN+PROC) | 26761.0619 | 26761.0619 | 26761.0619 | 26761.0619 | 26761.0619 | 26761.0619 | 26761.0619 | 26761.0619 | 26761.0619 | 26761.0619 | 26761.0619 | 26761.0619
| A2 | 130500 | RVSPU Product Assurance Management | Manpower | 16742.3894 | 16742.3894 | 16742.3894 | 16742.3894 | 16742.3894 | 16742.3894 | 16742.3894 | 16742.3894 | 16742.3894 | 16742.3894 | 16742.3894 | 16742.3894
|  |  |  | Procurement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | TOTAL | 16742.3894 | 16742.3894 | 16742.3894 | 16742.3894 | 16742.3894 | 16742.3894 | 16742.3894 | 16742.3894 | 16742.3894 | 16742.3894 | 16742.3894 | 16742.3894
| C11 | 461010 | RVSPU-EBB Preliminary Design | Manpower | 214606.9912 | 214606.9912 | 267512.6549 | 267512.6549 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| C12 |  |  | Procurement | 0 | 0 | 38994.6903 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | TOTAL | 214606.9912 | 214606.9912 | 306507.3451 | 267512.6549 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| C11 | 461020 | RVSPU-EQM design, production and test | Manpower | 0 | 0 | 0 | 0 | 145764.1593 | 145764.1593 | 183215.3097 | 183215.3097 | 0 | 0 | 0 | 0
| C12 |  |  | Procurement | 0 | 0 | 0 | 0 | 76460.177 | 0 | 144127.4336 | 0 | 0 | 0 | 0 | 0
|  |  |  | TOTAL | 0 | 0 | 0 | 0 | 222224.3363 | 145764.1593 | 327342.7434 | 183215.3097 | 0 | 0 | 0 | 0
| C11 | 461030 | RVSPU-PFM design, production and test | Manpower | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56900.708 | 56900.708 | 79599.823 | 79599.823
| C12 |  |  | Procurement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 77989.3805 | 0
|  |  |  | TOTAL | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56900.708 | 56900.708 | 157589.2035 | 79599.823
[5 empty] | 258110.4425 | 258110.4425 | 350010.7965 | 311016.1062 | 265727.7876 | 189267.6106 | 370846.1947 | 226718.7611 | 100404.1593 | 100404.1593 | 201092.6549 | 123103.2743