## Slide 1
Distinct programs evolving in time and tailored to the LVMH
1. Natural compounds proposed by RemeDys for direct nutra- or cosmeceutical development. Time to self-GRAS is 18-20 months
- Oleanolic acid – activates the GPCR, TGR5
- Gossypetin – AMPK activator
2. Screening against targets with proven activity on the mitochondria. Remedys executes the project and provides expertise. Time-frame is 24-36 months:
- Mito stress inducer – primary screen in the worm with secondary assays in cells;
- TGR5 agonist - virtual screen followed by cell-based co-transfection assay;
- SPT1 inhibitor – cell-based screen coupled with MS lipidomics to detect ceramides
- SARM1 inhibitor – virtual screen followed by enzymatic assay (NAD boosting in skin nerves)
3. New target identification from genetic reference populations and human validation to fill the pipeline. Remedys executes and provides expertise. Execution within 36-42 months
- Genomics and TIDVAL – 6 months
- Screening – same time-frame as #2; potentially faster, given experience acquired
Jump-start
(learning)
Consolidating
expertise
Filling the
pipeline

## Slide 2
How a Program for LVMH can be executed within Remedys
Critical Path
Screening and
Production Stream
Regulatory Stream
Safety Stream
PoC clinical trial
Plan assuming the natural cpd is not previously studied.
If already a GRAS timelines to be reduced by~ 1.5 yrs
2023
2024
2025
In Silico Screen
In Vitro Screen
In Vivo POC
Definition of intended use (Beverage, Milk powders,…)
Intake Assessment
Stability Testing (1 Year Shelf-life)
Ready to commercialize as food supplement
Safety testing strategy
Bacterial Reverse Mutation Test
In Vitro Mammalian Cell Micronucleus Test
Repeated Dose 90-Day Oral Toxicity Study in Rodents
ADME studies
Safe dose defined (NOAEL)
Study Design
Site Selection & Protocol
Ethics Preparation
Clinical Trial Execution
CT Report
CT Results
GMP batch produced
→ 1.5 Year Shelf-life
→ 2 Year Shelf-life
Safety Report
Go/NoGo for Food or Exit
Ethics Submission
Year 2
Year 3
Year 4
Go/NoGo
Molecules of natural origin against new targets for MASH
Year 1
28-Day non-GLP rat safety
2 Batches
3 independent Batches
QC Certification (GFSI?)
OECD 408
OECD 487
OECD 471
Self-GRAS
1
2
3
Numbers refer to previous slides

## Slide 3
How a Program for LVMH can be executed within Remedys
Critical Path
Screening and
Production Stream
Regulatory Stream
Safety Stream
PoC clinical trial
Plan assuming the natural cpd is not previously studied.
If already a GRAS timelines to be reduced by~ 1.5 yrs
2023
2024
2025
In Silico Screen
In Vitro Screen
In Vivo POC
Definition of intended use (Beverage, Milk powders,…)
Intake Assessment
Stability Testing (1 Year Shelf-life)
Ready to commercialize as food supplement
Safety testing strategy
Bacterial Reverse Mutation Test
In Vitro Mammalian Cell Micronucleus Test
Repeated Dose 90-Day Oral Toxicity Study in Rodents
ADME studies
Safe dose defined (NOAEL)
Study Design
Site Selection & Protocol
Ethics Preparation
Clinical Trial Execution
CT Report
CT Results
GMP batch produced
→ 1.5 Year Shelf-life
→ 2 Year Shelf-life
Safety Report
Go/NoGo for Food or Exit
Ethics Submission
Year 2
Year 3
Year 4
Go/NoGo
Molecules of natural origin against new targets for MASH
Year 1
28-Day non-GLP rat safety
2 Batches
3 independent Batches
QC Certification (GFSI?)
OECD 408
OECD 487
OECD 471
Self-GRAS